## 4W
District | VDC | Ward | Partner Organisation | Implementing Partner | Funding Organisation | Activity Type | Activity Sub-Type | Activity Name | Activity Detail | Units | Funding Status | Activity Status | Total Planned | Total Reached | Activity Start Date | Activity End Date | Comments
Bhaktapur | Anantalingeshwor N.P. | 13 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | individual data is about those who involved in CFW activities (Worker) |  | Yes | Completed | 50 | 39 | 2016-07-10 | 2016-07-24
Bhaktapur | Anantalingeshwor N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-08 | 2016-08-14
Bhaktapur | Anantalingeshwor N.P. | 10,11,12 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-31 | 2016-08-06 | Implemented by TRACE (Consultancy),7 days mason training
Bhaktapur | Anantalingeshwor N.P. | 10,13 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 2 | 0 |  |  | PASSA training at Ward level
Bhaktapur | Anantalingeshwor N.P. | ALL | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 2 | 0
Bhaktapur | Anantalingeshwor N.P. |  | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distric Level PASSA Roll out has been conducetd for 21 volunteers of 21 ward of Ero working areas | # of participants | Yes | Completed | 2 | 2 | 2016-09-28 | 2016-10-02 | Distric Level PASSA Roll out has been conducetd for 21 volunteers of 21 ward of Ero working areas
Bhaktapur | Bhaktapur N.P. | 1,2,3,5,7,9,10,11,12,13 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 10 | 0 |  |  | PASSA training at Ward level
Bhaktapur | Changunarayan N.P. | 10 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 1 | 2016-10-23 | 2016-10-25 | community level PASSA rollout , this meeting is planned for 3 days in district . Participant have planned for 40 participant but due to community people's daily work they droped the meeting from next days
Bhaktapur | Changunarayan N.P. | 17 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | In total 23 house 8 house owner Is participated in CFW and within 8 House 3 house has been compeletd |  | Yes | Ongoing | 20 | 8 | 2016-11-13
Bhaktapur | Changunarayan N.P. | 1, 8,9,10,11,12,13,14,15,16 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-07 | 2016-07-13 | event place is Changu
Bhaktapur | Changunarayan N.P. | 1,2,3,4 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-23 | 2016-07-29
Bhaktapur | Changunarayan N.P. | 1,2,3,4,6,9,10,11 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 8 | 0 |  |  | PASSA training at Ward level
Bhaktapur | Changunarayan N.P. | 3,4 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-29 | 2016-07-05 | Event plance is Bageshwori(6 number of mason trainee was from changunarayen and 24 are from Nagarkot but the event was same)
Bhaktapur | Changunarayan N.P. | 5,6,7,17 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-15 | 2016-07-21
Bhaktapur | Changunarayan N.P. |  | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distric Level PASSA Roll out has been conducetd for 21 volunteers of 21 ward of Ero working areas | # of participants | Yes | Completed | 9 | 9 | 2016-09-28 | 2016-10-02 | Distric Level PASSA Roll out has been conducetd for 21 volunteers of 21 ward of Ero working areas
Bhaktapur | Changunarayan N.P. |  | GON | GON | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2015-07-20 | 2015-07-25 | Changunarayan N.P.
Bhaktapur | MadhyapurThimi N.P. |  | ISAP |  | PWJ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2015-12-24 | 2015-12-28
Bhaktapur | Nagarkot N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 20 | 2016-12-15 | 2016-12-15
Bhaktapur | Nagarkot N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 5 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Ongoing | 23 | 14 | 2016-11-07
Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 7 | DCA | FSCN | DCA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Community orientation program on safe and resilient shelter construction | # of participants | Yes | Completed | 200 | 208 | 2016-07-17 | 2016-01-19
Bhaktapur | Nagarkot N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 7 | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Completed | 20 | 20 | 2016-11-21 | 2016-11-27
Bhaktapur | Nagarkot N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 35 | 2016-12-26 | 2016-12-26
Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information center at municipality office | # of households supported | Yes | Ongoing | 200 | 0 | 2016-12-01 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12
Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 46 | 2016-07-12 | 2016-07-12
Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 34 | 2016-07-13 | 2016-07-13
Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 72 | 2016-12-27 | 2016-12-27
Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 43 | 2016-07-21 | 2016-07-21
Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Bhaktapur | Nagarkot N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 36 | 2016-07-14 | 2016-07-14
Bhaktapur | Nagarkot N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Bhaktapur | Nagarkot N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-29 | 2016-06-04
Bhaktapur | Nagarkot N.P. | 1,2,3,10 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Completed | 55 | 52 | 2016-09-25 | 2016-10-25
Bhaktapur | Nagarkot N.P. | 1,2,3,4,5,6,7, | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 25 | 2016-06-21 | 2016-06-27 | Event place is sudal
Bhaktapur | Nagarkot N.P. | 11,12,13 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Ongoing | 114 | 29 | 2016-11-10
Bhaktapur | Nagarkot N.P. | 7,8,9,10,11,12,13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 24 | 2016-06-29 | 2016-07-05 | event place is Bageshwori
Bhaktapur | Nagarkot N.P. | ALL | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 10 | 0
Bhaktapur | Nagarkot N.P. | All | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0
Bhaktapur | Nagarkot N.P. |  | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distric Level PASSA Roll out has been conducetd for 21 volunteers of 21 ward of Ero working areas | # of participants | Yes | Completed | 10 | 10 | 2016-09-28 | 2016-10-02 | Distric Level PASSA Roll out has been conducetd for 21 volunteers of 21 ward of Ero working areas
Dhading | Aginchok | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 109 | 2016-09-18 | 2016-09-18
Dhading | Aginchok | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13
Dhading | Aginchok | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 68 | 2016-09-17 | 2016-09-17
Dhading | Aginchok | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Aginchok | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 76 | 2016-09-16 | 2016-09-16
Dhading | Aginchok | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Aginchok | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 56 | 2016-09-15 | 2016-09-15
Dhading | Aginchok | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Aginchok | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 41 | 2016-09-13 | 2016-09-13
Dhading | Aginchok | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Aginchok | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 32 | 2016-09-12 | 2016-09-12
Dhading | Aginchok | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Aginchok | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 52 | 2016-09-11 | 2016-09-11
Dhading | Aginchok | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Aginchok | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 41 | 2016-09-14 | 2016-09-14
Dhading | Aginchok | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Aginchok | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 59 | 2016-09-10 | 2016-09-10
Dhading | Aginchok | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Aginchok | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Aginchok |  | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 75 | 75 | 2016-10-22 | 2016-10-28
Dhading | Aginchok |  | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 75 | 75 | 2016-10-22 | 2016-10-28 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baireni | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baireni |  | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 22 | 2016-05-08 | 2016-06-23 | Submit next round of 4W
Dhading | Baseri | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 57 | 2016-09-13 | 2016-09-13
Dhading | Baseri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Baseri | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 42 | 2016-09-12 | 2016-09-12
Dhading | Baseri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 46 | 2016-09-11 | 2016-09-11
Dhading | Baseri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Baseri | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 63 | 2016-09-18 | 2016-09-18
Dhading | Baseri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Baseri | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 9 | 9 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 59 | 2016-09-19 | 2016-09-19
Dhading | Baseri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Baseri | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 77 | 2016-09-14 | 2016-09-14
Dhading | Baseri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Baseri | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 103 | 2016-09-17 | 2016-09-17
Dhading | Baseri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Baseri | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 74 | 2016-09-16 | 2016-09-16
Dhading | Baseri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Baseri | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24
Dhading | Baseri | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 56 | 2016-09-15 | 2016-09-15
Dhading | Baseri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Baseri | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Baseri | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Baseri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Benighat | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Bhumesthan | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 90 | 2016-04-02 | 2016-04-02
Dhading | Budhathum | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Budhathum | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 60 | 2016-04-01 | 2016-04-01
Dhading | Budhathum | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Budhathum | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 48 | 2016-03-27 | 2016-03-27
Dhading | Budhathum | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Budhathum | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 3 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-04-21 | 2016-06-05 | District Small Cottage Industry
Dhading | Budhathum | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 54 | 2016-03-25 | 2016-03-25
Dhading | Budhathum | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Budhathum | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 4 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05
Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 42 | 2016-03-26 | 2016-03-26
Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House | After completion of mason training house is constructed | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-08-15 | Mason training and democonstruction held Deurali tole of this vdc.
Dhading | Budhathum | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 5 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05
Dhading | Budhathum | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 92 | 2016-03-31 | 2016-03-31
Dhading | Budhathum | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Budhathum | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 6 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05
Dhading | Budhathum | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 73 | 2016-03-30 | 2016-03-30
Dhading | Budhathum | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Budhathum | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 14 | 14 | 2016-04-21 | 2016-06-05
Dhading | Budhathum | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 58 | 2016-03-28 | 2016-03-28
Dhading | Budhathum | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Budhathum | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30
Dhading | Budhathum | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 77 | 2016-03-29 | 2016-03-29
Dhading | Budhathum | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Budhathum | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Budhathum | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Budhathum | 9 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05
Dhading | Chainpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 2 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 2 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 3 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 3 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 4 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 4 | CA | FOCUS | CA | Technical Assistance | Demonstration Construction | House | House constructed for Single and Disabled male | # of constructions | Yes | Completed | 1 | 1 | 2016-11-14 | 2016-12-28 | House is made for single and disable male
Dhading | Chainpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 4 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 5 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 14 | 14 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 5 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 14 | 14 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 6 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 6 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 7 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 7 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 8 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 8 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 9 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 10 | 10 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Chainpur | 9 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-10-22 | 2016-11-12
Dhading | Chainpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 2 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 4 | 4 | 2016-04-05 | 2016-05-20
Dhading | ChhatreDyaurali | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 4 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-04-05 | 2016-05-20
Dhading | ChhatreDyaurali | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 6 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-04-05 | 2016-05-20
Dhading | ChhatreDyaurali | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 8 | 8 | 2016-04-05 | 2016-05-20
Dhading | ChhatreDyaurali | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-04-05 | 2016-05-20
Dhading | ChhatreDyaurali | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ChhatreDyaurali | 9 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-04-05 | 2016-05-20
Dhading | ChhatreDyaurali |  | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 60 | 49 | 2015-11-24 | 2015-11-28 | Ward wise data not avialbale
Dhading | Darkha | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 94 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 19 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10
Dhading | Darkha | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 84 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 8 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 7 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Darkha | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 156 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 147 | 6 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 147 | 7 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Darkha | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 65 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 204 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 204 | 4 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Darkha | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 141 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 133 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 133 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Darkha | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 109 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 2 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8
Dhading | Darkha | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 36 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 245 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 11 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 2 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Darkha | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 36 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 26 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 248 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 242 | 12 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 242 | 1 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 12 | 12
Dhading | Darkha | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 26 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 127 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Planned | 1 | 0
Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 10 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 2 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Darkha | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Dhading | Darkha | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 1 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 2 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 3 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 4 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 5 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 6 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 7 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 7 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 8 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhola | 9 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11
Dhading | Dhola | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-20
Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 35 | 2016-04-01
Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 2 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 9 | 9 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 2 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 25 | 2016-04-01
Dhading | Dhussa | 2 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 3 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 3 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 28 | 2016-04-01
Dhading | Dhussa | 3 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 4 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 4 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 31 | 2016-04-01
Dhading | Dhussa | 4 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 5 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 5 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 22 | 2016-04-01
Dhading | Dhussa | 5 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 6 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 26 | 26 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 6 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 20 | 2016-04-01
Dhading | Dhussa | 6 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 26 | 26 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 7 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 7 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 40 | 2016-04-01
Dhading | Dhussa | 7 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 32 | 2016-04-01
Dhading | Dhussa | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 40 | 2016-04-01
Dhading | Dhussa | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28
Dhading | Dhussa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhussa | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | BBS orintation 2 session in eah ward | # of participants | Yes | Ongoing | 600 | 150 | 2016-04-01
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 144 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 143 | 7 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 40 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 1 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 33 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 303 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 256 | 10 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 256 | 27 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 33 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 2 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 9 | 9 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 123 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 87 | 7 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 87 | 15 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 3 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 35 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 232 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 230 | 5 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 230 | 25 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 35 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-22 | 2016-02-22 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Dhuwakot | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 7 | 7 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 136 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 16 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 17 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 5 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 84 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 85 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 85 | 10 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 6 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 135 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 12 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 7 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 99 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 93 | 5 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 93 | 40 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 127 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 3 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 14 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 17 | 17
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Dhading | Dhuwakot | 9 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gajuri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12
Dhading | Goganpani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-08 | 2015-12-12
Dhading | Goganpani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12
Dhading | Goganpani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Goganpani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Goganpani |  | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 31 | 31 | 2015-12-08 | 2015-12-12 | Ward wise data not avialbale
Dhading | Gumdi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Gumdi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Gumdi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Gumdi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Gumdi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Gumdi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 5 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-03-28 | District Small Cottage Industry
Dhading | Gumdi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Gumdi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 6 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 4 | 4 | 2016-02-13 | 2016-03-28
Dhading | Gumdi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Gumdi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-02-13 | 2016-03-28
Dhading | Gumdi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Gumdi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-03-28
Dhading | Gumdi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Gumdi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Gumdi | 9 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-03-28
Dhading | Jeewanpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 5 | 5 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 2 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 2 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 7 | 7 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 6 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 1 | 1 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-30 | 2015-12-09
Dhading | Jeewanpur | 9 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-03-10
Dhading | Jeewanpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jeewanpur |  | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 22 | 2016-04-27 | 2016-06-11 | Submit next round of 4W
Dhading | Jharlang | 1 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Jharlang | 1 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 2 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 12 | 12 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Jharlang | 2 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 3 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 28 | 28 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 3 | UMN | HIMS | UMN | Technical Assistance | Demonstration Construction | House | Demo house construction is copleted in Myminee tole of Jharlang-9 | # of constructions | Yes | Completed | 1 | 1 | 2016-06-01 | 2017-01-20
Dhading | Jharlang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Jharlang | 3 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 28 | 28 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 4 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Jharlang | 4 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 5 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Jharlang | 5 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 6 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Jharlang | 6 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 7 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Jharlang | 7 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 8 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Jharlang | 8 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 9 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Jharlang | 9 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training
Dhading | Jharlang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jharlang |  | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Ward wise data are not available
Dhading | Jharlang |  | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Ward wise data are not available
Dhading | Jogimara | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 1 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 5 | 2017-01-17 | 2017-01-23
Dhading | Jogimara | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 6 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 4 | 2017-01-17 | 2017-01-23
Dhading | Jogimara | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 7 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 7 | 2017-01-17 | 2017-01-23
Dhading | Jogimara | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 8 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 5 | 2017-01-17 | 2017-01-23
Dhading | Jogimara | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jogimara | 9 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 3 | 2017-01-17 | 2017-01-23
Dhading | Jogimara | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 216 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 194 | 5 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 194 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 16 | 16 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 116 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 194 | 7 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 194 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 3 | 3 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 174 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 157 | 10 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 157 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 5 | 5 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 35 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 97 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 278 | 18 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 278 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 35 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 2 | 2 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 82 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 175 | 14 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 175 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 123 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 252 | 1 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 252 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 137 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 130 | 11 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 130 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 288 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 246 | 7 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 246 | 31 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 14 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 145 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 13 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 225 | 0 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 14 | 2015-10-01 | 2020-09-30
Dhading | Jyamrung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 170 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 232 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 232 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 1 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 1 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 104 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 282 | 1 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 282 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 2 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 12 | 12 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 2 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 17 | 17 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 156 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 324 | 1 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 324 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 3 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 3 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 17 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 316 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 305 | 21 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 305 | 35 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 12 | 12 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 17 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 22 | 22 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 159 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 6 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 15 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 10 | 10 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 5 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 106 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 339 | 10 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 339 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 6 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 16 | 16 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 79 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 126 | 11 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 126 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 12 | 12 | 2015-11-25 | 2015-11-29
Dhading | Kalleri | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 7 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 5 | 5 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 144 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 5 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 225 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 45 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 9 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 9 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd
Dhading | Kalleri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kalleri | 4, 5, 6 and 7 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-30 | 2016-06-05 | Funded by Korean Red Cross
Dhading | Kalleri | All | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 9 | 0 | 2016-08-29 | 2016-09-02 | 7 days training on EQ resistant mason training was conducted by TRACE (consultant)
Dhading | Kalleri | All | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-13 | 2016-05-19 | Funded by Luxembourg Red Cross
Dhading | Kalleri |  | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-11-25 | 2015-11-29 | Ward wise data not avialbale
Dhading | Katunje | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 1 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Katunje | 2 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 2 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 12 | 12 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Katunje | 3 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 23 | 23
Dhading | Katunje | 4 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 4 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 13 | 13 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Katunje | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 8 | 8 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 5 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 11 | 11 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 37 | 37
Dhading | Katunje | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 6 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 33 | 33 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Katunje | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 7 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 12 | 12 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Katunje | 8 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 8 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 22 | 22 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 8 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Katunje | 9 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 9 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Katunje | 9 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Katunje | 1, 2, 4 and 5 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-13 | 2016-05-19 | Funded by Luxembourg Red Cross
Dhading | Katunje | 2, 4, 5 and 6 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-06 | 2016-06-12 | Funded by Luxembourg Red Cross
Dhading | Kewalpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kewalpur |  | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 60 | 58 | 2015-11-24 | 2015-11-28 | Ward wise data not avialbale
Dhading | Khalte | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 57 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 147 | 3 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 147 | 10 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 1 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 1 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 8 | 8 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 133 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 117 | 4 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 117 | 15 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 2 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 5 | 5 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 2 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 90 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 168 | 5 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 168 | 8 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 3 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 3 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 77 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 223 | 7 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 223 | 5 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 4 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 206 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 251 | 6 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 251 | 20 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 19 | 19 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 224 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 293 | 6 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 293 | 69 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 9 | 9 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 7 | 7 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 29 | 29 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 120 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 1 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 107 | 12 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN)
Dhading | Khalte | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 28 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 1 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 15 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-05
Dhading | Khalte | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 33 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 48 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 116 | 2 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 116 | 12 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 33 | 2015-10-01 | 2020-09-30
Dhading | Khalte | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 1 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 15 | 15 | 2016-10-22 | 2016-11-12
Dhading | Khari | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 1 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-10-22 | 2016-11-12
Dhading | Khari | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 2 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Khari | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 2 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Khari | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 3 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 11 | 11 | 2016-10-22 | 2016-11-12
Dhading | Khari | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 3 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-10-22 | 2016-11-12
Dhading | Khari | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 4 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Khari | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 4 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Khari | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 5 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12
Dhading | Khari | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 5 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12
Dhading | Khari | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 6 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12
Dhading | Khari | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 6 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12
Dhading | Khari | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 7 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12
Dhading | Khari | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 7 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12
Dhading | Khari | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 8 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Khari | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 8 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12
Dhading | Khari | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 9 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12
Dhading | Khari | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Khari | 9 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12
Dhading | Khari | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kiranchok | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 31 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 130 | 5 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 130 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 1 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 19 | 19 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 198 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 271 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 271 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 2 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 11 | 11 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 174 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 261 | 18 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 261 | 50 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 3 | HELVETAS | MSED | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 102 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 275 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 275 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 5 | 5 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 4 | HELVETAS | MSED | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 159 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 381 | 6 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 381 | 29 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | HELVETAS | MSED | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 9 | 9 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 5 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 5 | HELVETAS | MSED | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 33 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 228 | 38 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 228 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 288 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 396 | 24 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 396 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 7 | HELVETAS | MSED | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 38 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 188 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 226 | 7 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 226 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 38 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 108 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 183 | 10 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 183 | 0 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-04
Dhading | Kumpur | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Dhading | Kumpur | 9 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED)
Dhading | Kumpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 1 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 11 | 11 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 1 | UMN | NRDS | UMN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-12-10
Dhading | Lapa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Lapa | 1 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 2 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8
Dhading | Lapa | 2 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 3 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Lapa | 3 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 4 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 3 | 3 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Lapa | 4 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 5 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 5 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 6 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Lapa | 6 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 7 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Lapa | 7 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 8 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 8 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 9 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Lapa | 9 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day
Dhading | Lapa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Lapa |  | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Ward wise data are not available
Dhading | Lapa |  | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Ward wise data are not available
Dhading | Mahadevsthan | 1 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 27 | 27 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 1 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 2 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 2 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 3 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 3 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 4 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 4 | UMN | PRAYAS-N | UMN | Technical Assistance | Demonstration Construction | House | Demo house construction is copleted in Talti tole of Mahadevsthan-4 | # of constructions | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-12-15
Dhading | Mahadevsthan | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 4 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 5 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 5 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 6 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 26 | 26 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 6 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 26 | 26 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 7 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 7 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 8 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 8 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 9 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 14 | 14 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mahadevsthan | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-12-03 | 2015-12-07
Dhading | Mahadevsthan | 9 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 14 | 14 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Mahadevsthan | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 1 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 2 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 2 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 13 | 13 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 3 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 11 | 11 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 4 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 5 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 4 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 6 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 7 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 8 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 4 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Maidi | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12
Dhading | Maidi | 9 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 4 | 2016-12-05 | 2017-01-23
Dhading | Maidi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 92 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 4 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 5 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 97 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 96 | 11 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 96 | 7 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 143 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 137 | 24 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 137 | 7 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 153 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 139 | 11 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 139 | 8 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 221 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 12 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 123 | 4 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Marpak | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 105 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 71 | 5 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 71 | 5 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Marpak | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 137 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 156 | 12 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 156 | 1 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 15 | 15
Dhading | Marpak | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 40 | 3 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 40 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 38 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 275 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 167 | 8 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 167 | 3 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Marpak | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 38 | 2015-10-01 | 2020-09-30
Dhading | Marpak | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 38 | 2016-03-23 | 2016-03-23
Dhading | Mulpani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Mulpani | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 88 | 2016-03-24 | 2016-03-24
Dhading | Mulpani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Mulpani | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 2 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 7 | 7 | 2016-02-12 | 2016-03-26
Dhading | Mulpani | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 16 | 16 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 83 | 2016-03-26 | 2016-03-26
Dhading | Mulpani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8
Dhading | Mulpani | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 58 | 2016-03-25 | 2016-03-25
Dhading | Mulpani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Mulpani | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 48 | 2016-03-28 | 2016-03-28
Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House | After completion of mason training house is constructed in Mathilo Mulabari | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-08-15
Dhading | Mulpani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 5 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-02-12 | 2016-03-26
Dhading | Mulpani | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 9 | 9 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 35 | 2016-03-31 | 2016-03-31
Dhading | Mulpani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Mulpani | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 60 | 2016-03-29 | 2016-03-29
Dhading | Mulpani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Mulpani | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 78 | 2016-03-27 | 2016-03-27
Dhading | Mulpani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Mulpani | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-02-12 | 2016-03-26
Dhading | Mulpani | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14
Dhading | Mulpani | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 44 | 2016-04-01 | 2016-04-01
Dhading | Mulpani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Mulpani | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Mulpani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Mulpani |  | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 10 | 10 | 2016-02-12 | 2016-03-26 | District Small Cottage Industry
Dhading | Nalang | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 37 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 1 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 1 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 8 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 76 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 156 | 8 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 156 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 144 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 286 | 10 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 286 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 6 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 46 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 5 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 50 | 29 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 2 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 70 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 107 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 5 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 23 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 204 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 393 | 28 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 393 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 3 | 4 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 23 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 56 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 206 | 7 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 206 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Planned | 3 | 0 | 2016-11-23 |  | Reached figure will confirm in next round
Dhading | Nalang | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 45 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 4 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 3 | 1 | 2016-11-23 | 2016-11-29
Dhading | Nalang | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 34 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 132 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Planned | 3 | 0 | 2016-11-23 |  | Reached figure will confirm in next round
Dhading | Nalang | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 34 | 2015-10-01 | 2020-09-30
Dhading | Nalang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2015-12-12
Dhading | Naubise | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-12-08 | 2015-12-12
Dhading | Naubise | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 9 | 9 | 2015-12-08 | 2015-12-12
Dhading | Naubise | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 9 | 9 | 2015-12-08 | 2015-12-12
Dhading | Naubise | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Naubise | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Naubise |  | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 29 | 29 | 2015-12-08 | 2015-12-12 | Ward wise data not avialbale
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 47 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 539 | 11 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 539 | 100 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 58 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 366 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 825 | 20 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 825 | 70 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 58 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 2 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-05-24
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 140 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 413 | 10 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 413 | 402 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Retrofitting training | Engineers, sub-engineers |  | # of trainees | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 9 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Short training | Social mobilizer |  | # of trainees | Yes | Ongoing | 256 | 35 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 512 | 223 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Ongoing | 32 | 33 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 3 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-03-15 | 2016-05-24
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 35 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 180 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 642 | 1 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 642 | 80 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 35 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 4 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-03-15 | 2016-05-24
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 5 | ACTED | ACTED | ACTED | Others | Others | (Please specify in Activity Detail) | Social Mobilization Training on Enrollment |  | Yes | Completed | 25 | 24 | 2016-04-27 | 2016-04-29
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 349 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 292 | 18 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 292 | 132 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 3 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 35 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 377 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 355 | 20 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 355 | 12 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 35 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 19 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 449 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 807 | 2 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 807 | 70 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 19 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2016-05-24
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 17 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 188 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 707 | 10 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 707 | 60 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 17 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-03-15 | 2016-05-24 | District Small Cottage Industry
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 61 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 15 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 611 | 21 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 611 | 52 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 61 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 22 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 154 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 511 | 13 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 511 | 48 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 22 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 15 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 140 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 391 | 15 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 391 | 20 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 15 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 22 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 182 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 673 | 28 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 673 | 100 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 22 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 12 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-05-24
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 11 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 384 | 80 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 324 | 4 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 324 | 6 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 11 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Nilkantha N.P. |  | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 19 | 2015-12-06 | 2016-01-23 | Submit next round of 4W
Dhading | Nilkantha N.P. |  | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 20 | 2016-12-06 | 2016-01-22 | Submit next round of 4W
Dhading | Phulkhark | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 116 | 2016-09-19 | 2016-09-19
Dhading | Phulkhark | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Phulkhark | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 92 | 2016-09-18 | 2016-09-18
Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-12
Dhading | Phulkhark | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 87 | 2016-09-17 | 2016-09-17
Dhading | Phulkhark | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Phulkhark | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 80 | 2016-09-15 | 2016-09-15
Dhading | Phulkhark | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Phulkhark | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 89 | 2016-09-16 | 2016-09-16
Dhading | Phulkhark | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Phulkhark | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 49 | 2016-09-13 | 2016-09-13
Dhading | Phulkhark | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Phulkhark | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 61 | 2016-09-11 | 2016-09-11
Dhading | Phulkhark | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 86 | 2016-09-12 | 2016-09-12
Dhading | Phulkhark | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Phulkhark | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 67 | 2016-09-14 | 2016-09-14
Dhading | Phulkhark | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Phulkhark | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Phulkhark | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Phulkhark |  | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 1 | 1 | 2016-09-25 | 2016-10-01
Dhading | Phulkhark |  | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Pida | 1 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 1 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 2 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 19 | 19 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 2 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 19 | 19 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 3 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 3 | UMN | PRAYAS-N | UMN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-06-03
Dhading | Pida | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 3 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 4 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 4 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 5 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 5 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 6 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 6 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 7 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 7 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 9 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida | 9 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day
Dhading | Pida | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Pida |  | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Ward wise data are not available
Dhading | Pida |  | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Ward wise data are not available
Dhading | ReeGaun | 1 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13
Dhading | ReeGaun | 1 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 2 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 2 | UMN | NRDS | UMN | Technical Assistance | Demonstration Construction | House | Demo house construction is copleted in Salleri tole of Reegaun-2 | # of constructions | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-12-15
Dhading | ReeGaun | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | ReeGaun | 2 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 3 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 2 | 2 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | ReeGaun | 3 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 4 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 28 | 28 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | ReeGaun | 4 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 28 | 28 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 5 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | ReeGaun | 5 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 6 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | ReeGaun | 6 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 7 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 21 | 21 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | ReeGaun | 7 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 21 | 21 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 8 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | ReeGaun | 8 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 9 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | ReeGaun | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | ReeGaun | 9 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10
Dhading | ReeGaun | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 5 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-05-29 | 2016-06-13
Dhading | Salang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 6 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-05-29 | 2016-06-13
Dhading | Salang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 7 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-05-29 | 2016-06-13
Dhading | Salang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 8 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-05-29 | 2016-06-13
Dhading | Salang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salang | 9 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-05-29 | 2016-06-13
Dhading | Salang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 15 | 15
Dhading | Salyankot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8
Dhading | Salyankot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Salyankot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Salyankot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Salyankot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Salyankot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Salyankot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyankot | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Salyankot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 66 | 2016-01-21 | 2016-01-21
Dhading | Salyantar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Salyantar | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 93 | 2016-03-16 | 2016-03-16
Dhading | Salyantar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Salyantar | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 58 | 2016-03-17 | 2016-03-17
Dhading | Salyantar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Salyantar | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 45 | 2016-03-18 | 2016-03-18
Dhading | Salyantar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Salyantar | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 94 | 2016-03-13 | 2016-03-13
Dhading | Salyantar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Salyantar | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 47 | 2016-03-14 | 2016-03-14
Dhading | Salyantar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13
Dhading | Salyantar | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 15 | 15 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 32 | 2016-03-15 | 2016-03-15
Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House | After completion of mason training house is constructed at Bagaicha tole | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-08-15
Dhading | Salyantar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10
Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 85 | 2016-03-11 | 2016-03-11
Dhading | Salyantar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Salyantar | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17
Dhading | Salyantar | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 56 | 2016-03-23 | 2016-03-23
Dhading | Salyantar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Salyantar | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Salyantar | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only.
Dhading | Salyantar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Satyadevi | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Satyadevi | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 | ACTION-N is Local partner of Oxfam
Dhading | Satyadevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 45 | 2016-04-01
Dhading | Satyadevi | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 | PARYAS-N is local partner of Oxfam
Dhading | Satyadevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 45 | 2016-04-01
Dhading | Satyadevi | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13
Dhading | Satyadevi | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 45 | 2016-04-01
Dhading | Satyadevi | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Satyadevi | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Satyadevi | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Satyadevi | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Satyadevi | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Satyadevi | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Satyadevi | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Satyadevi | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Satyadevi | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-10-14
Dhading | Satyadevi | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Satyadevi | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11
Dhading | Satyadevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Satyadevi | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | BBS orintation 2 session in eah ward | # of participants | Yes | Ongoing | 600 | 150 | 2016-04-01
Dhading | Semjong | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 73 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 117 | 3 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 117 | 7 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 1 | 1 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 1 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman
Dhading | Semjong | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 24 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 11 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 2 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 2 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman
Dhading | Semjong | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 120 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 91 | 11 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 91 | 9 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 1 | 1 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 106 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 13 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 16 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 10 | 10 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman
Dhading | Semjong | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 190 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 139 | 12 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 139 | 12 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3
Dhading | Semjong | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 6 | 6 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 8 | 8 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman
Dhading | Semjong | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 98 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 9 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 12 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Semjong | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 7 | 7 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 6 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 6 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman
Dhading | Semjong | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 117 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 4 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 11 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Semjong | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 2 | 2 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 175 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 8 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Semjong | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 148 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 14 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 15 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Semjong | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Dhading | Semjong | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 2015-12-06
Dhading | Semjong | 9 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 2 | 2 | 2016-02-22 | 2016-03-21
Dhading | Semjong | 9 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-29
Dhading | Semjong | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 119 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 118 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 118 | 4 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Sertung | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 26 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 1 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 123 | 4 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Sertung | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 69 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 2 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 7 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Sertung | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 88 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 2 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 68 | 2 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Sertung | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 77 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 3 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 1 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Sertung | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 34 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 5 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 60 | 20 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Sertung | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 34 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 97 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 7 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 47 | 25 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10
Dhading | Sertung | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 34 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 29 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 9 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 88 | 15 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5
Dhading | Sertung | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 5 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 26 | 1 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 26 | 2 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Sertung | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Dhading | Sertung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tasarpu | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12
Dhading | Tasarpu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 15 | 15 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 11 | 11 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 12 | 12 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Thakre | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-21 | 2015-12-25
Dhading | Thakre | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 38 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 37 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 37 | 9 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Tipling | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 55 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 47 | 4 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Tipling | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 101 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 5 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 3 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Tipling | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 86 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 78 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 78 | 5 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Tipling | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 38 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 65 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 65 | 10 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Tipling | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 33 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 91 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 67 | 25 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 67 | 7 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8
Dhading | Tipling | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 33 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 91 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 164 | 10 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 164 | 5 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 15 | 15
Dhading | Tipling | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 110 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 3 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Tipling | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 544 | 197 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 143 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Tipling | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tipling | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Tripureswor | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 9 | 9 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2
Dhading | Tripureswor | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-10-14
Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Tripureswor | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 3 | 3 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1
Dhading | Tripureswor | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7
Dhading | Tripureswor | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6
Dhading | Tripureswor | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01
Dhading | Tripureswor | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4
Dhading | Tripureswor | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28
Dhading | Tripureswor | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dhading | Tripureswor | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | BBS orintation 2 session in eah ward | # of participants | Yes | Ongoing | 600 | 150 | 2016-04-01
Dolakha | Alampu | 1 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 1 | IOM | CWIN-TUKI | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 58 | 45 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 78 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 1 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 48 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 48 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 1 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 58 | 45 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 2 | IOM | CWIN-TUKI | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 118 | 109 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 101 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 118 | 109 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 3 | IOM | CWIN-TUKI | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 122 | 82 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 104 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 122 | 82 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 4 | IOM |  | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 43 | 48 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 116 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 36 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 36 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 43 | 48 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 71 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 5 | IOM |  | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 84 | 95 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 317 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 69 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 69 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 84 | 95 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 6 | IOM |  | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 50 | 49 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 105 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 42 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 50 | 49 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 7 | IOM |  | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 45 | 46 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 72 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 38 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 38 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 46 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 8 | IOM |  | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 96 | 78 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 233 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 81 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 81 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 96 | 78 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25
Dolakha | Alampu | 9 | IOM |  | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 66 | 65 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 120 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 56 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 56 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 66 | 65 | 2016-05-01 | 2016-05-26
Dolakha | Alampu | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Alampu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Alampu | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Alampu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 58
Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 212 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 1 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 118 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 118 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 1 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 229 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 163 | 23 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 163 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-01 | 2016-01-27
Dolakha | Babare | 2 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 209 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 114 | 14 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 114 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 281 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 23 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 23 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 49 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 81 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 95 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 95 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 87 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 85 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 93 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 8 | 8 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2016-10-21 | 2016-10-27
Dolakha | Babare | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Babare | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhedapu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 72 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 544 | 58 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 544 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 62 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 62 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 200 | 87 | 2015-12-19 | 2016-09-30
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 194 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 384 | 34 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 384 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-27 | 2016-04-16
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 2 | NRCS | NRCS | SRC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 16 | 16 | 2015-12-22 | 2015-12-26
Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 200 | 20 | 2015-12-19 | 2016-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 131 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 250 | 31 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 250 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 189 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 389 | 27 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 389 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 43 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 43 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 46 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 190 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 190 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 86 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 560 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 560 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 29 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 6 | IOM | REDR-I |  | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Completed | 18 | 18 | 2015-12-16 | 2015-12-21
Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 29 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 50
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 83 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 327 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 327 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 16 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 16 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 158 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 402 | 25 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 402 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 64 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 348 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 348 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 144 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 476 | 46 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 544 | 290 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Retrofitting training | Engineers, sub-engineers |  | # of trainees | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 476 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 31 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Social mobilizer |  | # of trainees | Yes | Ongoing | 256 | 63 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Ongoing | 32 | 63 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 31 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 256 | 63 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 129 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 518 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 518 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 129 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 345 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 345 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 37 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 37 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 64 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 414 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 414 | 305 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 16 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 16 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhimeswor N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 570
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 40 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 44 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 23 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 89 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 89 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 17 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 17 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 68 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 20 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 122 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 122 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 16 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | CW | RRN | DEC-II | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 20 | 0 | 2017-01-01
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 16 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Bhirkot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 42
Dolakha | Bhusaphedi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 1 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 2 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 3 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 4 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 5 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 6 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 7 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 11 | 11 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 8 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03
Dolakha | Bhusaphedi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bhusaphedi | 9 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-09-19 | 2016-09-25
Dolakha | Bhusaphedi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 93 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 111 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 132 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 132 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 93 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 45 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 65 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 45 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 53 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 51 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 82 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 82 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 53 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 48 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 59 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 68 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 48 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 39 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 100 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 44 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 44 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 39 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 40 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 124 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 61 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 40 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 52 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 48 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 82 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 82 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 52 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 62 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 124 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 88 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 62 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 10 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 39 | 2016-04-08 | 2016-04-29
Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 32 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 52 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 52 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 39 | 2016-04-11 | 2016-04-27
Dolakha | Bigu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 16 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bigu | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 16 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Bocha | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Bocha | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 5 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Bocha | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 5 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Bocha | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Bocha | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Bocha | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Bocha | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bocha | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Dolakha | Bocha |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 72
Dolakha | Bulung | 1 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 1 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 1 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 1 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 61 | 0 | 2016-08-29
Dolakha | Bulung | 2 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 2 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 2 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 2 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 53 | 0 | 2016-08-29
Dolakha | Bulung | 3 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 3 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 3 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 3 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 64 | 0 | 2016-08-29
Dolakha | Bulung | 4 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 4 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 4 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 4 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 65 | 0 | 2016-08-29
Dolakha | Bulung | 5 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 5 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 5 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 5 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 70 | 0 | 2016-08-29
Dolakha | Bulung | 6 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 6 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 6 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 6 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 48 | 0 | 2016-08-29
Dolakha | Bulung | 7 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 7 | CARITAS-N |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08
Dolakha | Bulung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 7 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 7 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 7 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 78 | 0 | 2016-08-29
Dolakha | Bulung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 96 | 71 | 2016-06-15 | 2016-06-16
Dolakha | Bulung | 8 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 8 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 8 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 8 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 35 | 0 | 2016-08-29
Dolakha | Bulung | 9 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 9 | CARITAS-N |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08
Dolakha | Bulung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 9 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19
Dolakha | Bulung | 9 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 11 | 2015-12-14 | 2016-02-15
Dolakha | Bulung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Bulung | 9 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 36 | 0 | 2016-08-29
Dolakha | Chankhu | 1 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 1 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 2 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 3 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 4 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 4 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 5 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 5 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 6 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 6 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 7 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 7 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 8 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 8 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 9 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chankhu | 9 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Chankhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03 | 19-25 Apr First Session, 27 Apr-3 May Second Session
Dolakha | Chhetrapa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 3 | 3
Dolakha | Chhetrapa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 6 | 6
Dolakha | Chhetrapa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 4 | 4
Dolakha | Chhetrapa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 1 | 1 | 2016-12-01
Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 7 | 7
Dolakha | Chhetrapa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 5 | 5 | 2016-12-01
Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 10 | 10
Dolakha | Chhetrapa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 4 | 4
Dolakha | Chhetrapa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 5 | 5
Dolakha | Chhetrapa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03
Dolakha | Chhetrapa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chhetrapa | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 4 | 4
Dolakha | Chhetrapa |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 132
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 160 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 1 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 113 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 113 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 137 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 117 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 246 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 94 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 132 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 64 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 70 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 80 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 80 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 95 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chilankha | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 61 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 84 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 84 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 80 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 22 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 104 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 165 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 91 | 17 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 91 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-07 | 2016-02-02
Dolakha | Chyama | 4 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 4 | REDC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 26 | 2016-09-18 | 2016-09-24
Dolakha | Chyama | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 62 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 78 | 14 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 78 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 77 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 75 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 67 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 114 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 114 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 115 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 77 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 8 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 8 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 188 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 69 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 69 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Chyama | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Chyama | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 7 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dandakharka | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 1 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 2 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 3 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 4 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 5 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 6 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 7 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 8 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Dudhpokhari | 9 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22
Dolakha | Dudhpokhari | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Fasku | 1 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Fasku | 2 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Fasku | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Fasku | 3 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Fasku | 4 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 5 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Fasku | 5 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 5 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Fasku | 6 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 7 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Fasku | 8 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29
Dolakha | Fasku | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Dolakha | Fasku | 9 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-05 | 2016-11-11
Dolakha | Fasku |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 49
Dolakha | Gairimudi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gairimudi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GauriSankar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GauriSankar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GauriSankar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 2 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GauriSankar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 3 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 4 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 4 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 5 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 5 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 6 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 6 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GauriSankar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 7 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 8 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 8 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 9 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Gaurisankar | 9 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15
Dolakha | GauriSankar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | GhangSukathokar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 1 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 2 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-06 | 2016-02-02
Dolakha | Hawa | 3 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 3 | REDC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 28 | 2016-09-18 | 2016-09-24
Dolakha | Hawa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 4 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 5 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 6 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 7 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 8 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Hawa | 9 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Hawa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 175 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 235 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 235 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 141 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 113 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 113 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | CW | RRN | DEC-II | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 10 | 0 | 2017-01-01
Dolakha | Japhe | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 101 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 119 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 119 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | CW | RRN | DEC-II | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 10 | 0 | 2017-01-01
Dolakha | Japhe | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 165 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 116 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 116 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 88 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 81 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 94 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 94 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 137 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 201 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 64 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 282 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 101 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Japhe | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 50
Dolakha | Japhe |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 174
Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 71 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 57 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 45 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 37 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 37 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 96 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 44 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 44 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 106 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 50 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 111 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 49 | 21 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 49 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 82 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 36 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 36 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 51 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 93 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 93 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 131 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 42 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 147 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 53 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 53 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhule | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 12 | 12 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jhyaku | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 13 | 13 | 2015-07-20 | 2015-07-24
Dolakha | Jhyaku | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jiri N.P. |  | BC |  | BC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  | Note that the implementing party will be Jiri Technical School
Dolakha | Jiri N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 196
Dolakha | Jugu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 15 | 15 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 1 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 1 | 1 | 2016-12-01
Dolakha | Jugu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 2 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 2 | 2 | 2016-12-01
Dolakha | Jugu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 2 | 2 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 3 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 3 | 3 | 2016-12-01
Dolakha | Jugu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 4 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 1 | 1 | 2016-12-01
Dolakha | Jugu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 6 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 1 | 1 | 2016-12-01
Dolakha | Jugu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 7 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 3 | 3 | 2016-12-01
Dolakha | Jugu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 3 | 3 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 8 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 4 | 4 | 2016-12-01
Dolakha | Jugu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 4 | 4 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24
Dolakha | Jugu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Jugu | 9 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Ongoing | 2 | 2 | 2016-12-01
Dolakha | Jugu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 2 | 2 | 2015-07-20 | 2015-07-24
Dolakha | Kabhre | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2016-04-19 | 2016-05-03 | 19-25 Apr First Session, 27 Apr-3 May Second Session
Dolakha | Kabhre | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 21 | 21 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 14 | 14 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 14 | 14 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 3 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2017-01-07 | 2017-02-15
Dolakha | Kabhre | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 12 | 12 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 4 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 4 | 4 | 2017-01-07 | 2017-02-15
Dolakha | Kabhre | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 9 | 9 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 5 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2017-01-07 | 2017-02-15
Dolakha | Kabhre | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 15 | 15 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 6 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 5 | 5 | 2017-01-07 | 2017-02-15
Dolakha | Kabhre | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 8 | 8 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 7 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2017-01-07 | 2017-02-15
Dolakha | Kabhre | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre | 9 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 5 | 5 | 2017-01-07 | 2017-02-15
Dolakha | Kabhre | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kabhre | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-05-03
Dolakha | Kabhre |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 93
Dolakha | Kalingchok | 1 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 90 | 87 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 1 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 90 | 87 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 2 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 80 | 79 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 2 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 80 | 79 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 3 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 110 | 105 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 3 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 110 | 105 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 4 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 95 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 4 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 95 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 5 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 85 | 82 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 5 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 85 | 82 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 6 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 55 | 53 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 6 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 55 | 53 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 7 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 75 | 73 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 7 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 75 | 73 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 8 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 40 | 36 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 8 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 36 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 9 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 45 | 43 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok | 9 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 43 | 2015-12-19 | 2016-09-30
Dolakha | Kalingchok | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Kalingchok |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 25
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 147 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 70 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 70 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 111 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 110 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 110 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Katakuti | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 172 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 172 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 242 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 242 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 4 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Katakuti | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 208 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 208 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 153 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 265 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 265 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 157 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 120 | 32 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 120 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 7 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Katakuti | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 106 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 80 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 80 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Dolakha | Katakuti | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Katakuti |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 128
Dolakha | Khare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khare |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 50
Dolakha | Khopachagu | 1 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 90 | 90 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 1 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 2 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 37 | 37 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 2 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 3 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 12 | 12 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 3 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 4 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 24 | 24 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 4 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 5 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 16 | 16 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 5 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 6 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 25 | 25 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 6 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 7 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 20 | 20 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 7 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 8 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 21 | 21 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 8 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 9 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 25 | 25 | 2016-07-28 | 2016-07-30
Dolakha | Khopachagu | 9 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Khopachagu | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Khopachagu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 109 | 92 | 2016-03-09 | 2016-03-09
Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 17 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 65 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 65 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 109 | 92 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 86 | 63 | 2016-03-04 | 2016-03-04
Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 58 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 86 | 62 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 89 | 64 | 2016-03-10 | 2016-03-10
Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 82 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 75 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 89 | 65 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 109 | 81 | 2016-03-11 | 2016-03-11
Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 127 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 60 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 109 | 81 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 101 | 130 | 2016-03-03 | 2016-03-03
Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 187 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 50 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 161 | 128 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 14 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 107 | 79 | 2016-03-02 | 2016-03-02
Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 84 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 39 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 39 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 107 | 79 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 215 | 175 | 2016-03-01 | 2016-03-01
Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 232 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 17 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 57 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 215 | 174 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 13 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 245 | 159 | 2016-03-14 | 2016-03-15
Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 227 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 77 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 245 | 160 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 115 | 95 | 2016-03-08 | 2016-03-08
Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 142 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 48 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 48 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | IOM |  | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 115 | 95 | 2016-03-01 | 2016-03-25
Dolakha | Laduk | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15
Dolakha | Laduk | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Laduk | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Laduk |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 45
Dolakha | LakuriDada | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 1 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | LakuriDada | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 1 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | LakuriDada | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | LakuriDada | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | LakuriDada | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | LakuriDada | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | LakuriDada | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | LakuriDada | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Dolakha | LakuriDada | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | LakuriDada | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 37
Dolakha | LakuriDada |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 176
Dolakha | Lamabagar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 2 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 3 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 4 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 4 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 5 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 5 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 6 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 6 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 7 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 8 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 8 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 9 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamabagar | 9 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Lamabagar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 31 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 85 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 85 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 89 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 114 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 26 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 61 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 190 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 198 | 21 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 198 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 196 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 124 | 25 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 124 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 113 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 162 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 162 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 127 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 138 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 138 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | CA | CEEPAARD | CA | Technical Assistance | Demonstration Construction | House | Single room demo house built with mud, stone and timber | # of constructions | Yes | Planned | 1 | 0 | 2016-12-01
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 144 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 215 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 215 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-03 | 2016-01-30 | Three model house build in Suspachhemawati, Lapilang and Bhimeshwor are of two rooms model house and Eight demo houses built in other eight VDCs are of single room demo house.
Dolakha | Lamidada | 8 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 195 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 187 | 17 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 187 | 30 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Lamidada |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 54
Dolakha | Lapilang | 1 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 1 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 6 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 2 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 2 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 3 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 3 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 4 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-23 | 2016-04-15
Dolakha | Lapilang | 4 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 5 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 5 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 6 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 6 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 7 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 7 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 8 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 8 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 9 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 9 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27
Dolakha | Lapilang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Lapilang | 4,5,6 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-19 | 2016-07-25
Dolakha | Lapilang | 1,2,3 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-10 | 2016-07-16 | Improved cooking stove training
Dolakha | Lapilang | 7,8,9 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-08-02 | 2016-08-08 | One of the trainee got sick during the training, so could not complete the training
Dolakha | Lapilang | ALL | NRCS | NRCS | SRC | Others | Others | (Please specify in Activity Detail) | Improved cooking stove training |  | Yes | Completed | 20 | 19 | 2016-11-13 | 2016-11-19
Dolakha | Lapilang | All | NRCS | NRCS | SRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2015-12-27 | 2016-01-20
Dolakha | Lapilang | ALL | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-11-11 | 2016-11-17 | Mason training for urban context
Dolakha | Lapilang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 52
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 267 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 88 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 158 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 103 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 103 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 15 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 52 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 151 | 3 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 151 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 4 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 260 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 260 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 21 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 171 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 171 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 59 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 133 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 133 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 12 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 66 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 97 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 97 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 14 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 14 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 32 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 18 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 16 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 16 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Magapauwa |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 46
Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 154 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 157 | 19 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 157 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 93 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 147 | 9 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 147 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 115 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 223 | 11 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 223 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 95 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 160 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 160 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 237 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 225 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 76 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 107 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 76 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 7 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 114 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 155 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 155 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 480 | 133 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 124 | 4 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 124 | 38 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Malu | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Dolakha | Malu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 47
Dolakha | Marbu | 1 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 1 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 1 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 8 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 2 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 2 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 2 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 3 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 3 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 3 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 4 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 4 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 4 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 8 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 5 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 5 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 5 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 6 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 6 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 6 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 7 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 7 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 7 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 8 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 8 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 8 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 9 | HELVETAS | KITES |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 9 | HELVETAS | KITES |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Marbu | 9 | HELVETAS | KITES |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15
Dolakha | Marbu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 1 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 2 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 3 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 4 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 5 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-13 | 2016-02-10
Dolakha | Melung | 6 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 6 | REDC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 28 | 2016-09-25 | 2016-10-01
Dolakha | Melung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 7 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 8 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Melung | 9 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Melung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Mirge |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 22
Dolakha | Namdu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26 | 4-10 May First Session, 12-18 May Second Session, 20-26 Third Session
Dolakha | Namdu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 9 | 9 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 14 | 14 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 11 | 11 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 11 | 11 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 14 | 14 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 11 | 11 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 12 | 12 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 14 | 14 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 6 | 6 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26
Dolakha | Namdu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Namdu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26
Dolakha | Namdu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 138
Dolakha | Orang | 1 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 1 | CARITAS-N |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08
Dolakha | Orang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 1 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 1 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 1 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 70 | 0 | 2016-08-29
Dolakha | Orang | 2 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 2 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 2 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 26 | 0 | 2016-08-29
Dolakha | Orang | 3 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 3 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 3 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 3 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 50 | 0 | 2016-08-29
Dolakha | Orang | 4 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 4 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 4 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 56 | 0 | 2016-08-29
Dolakha | Orang | 5 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 5 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 5 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 5 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 53 | 0 | 2016-08-29
Dolakha | Orang | 6 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 6 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 6 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 48 | 0 | 2016-08-29
Dolakha | Orang | 7 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 7 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 7 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 86 | 0 | 2016-08-29
Dolakha | Orang | 8 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 2 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 8 | CARITAS-N |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08
Dolakha | Orang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 8 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 8 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 8 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 65 | 0 | 2016-08-29
Dolakha | Orang | 9 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 9 | CARITAS-N |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19
Dolakha | Orang | 9 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 9 | 2015-12-14 | 2016-02-15
Dolakha | Orang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Orang | 9 | CARITAS-N |  |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 34 | 0 | 2016-08-29
Dolakha | Pawati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Pawati |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 83
Dolakha | Pawati |  | BC | PLAN | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0
Dolakha | Sahare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 1 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 2 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 3 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 4 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 5 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-08 | 2016-02-05
Dolakha | Sahare | 6 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 6 | REDC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 32 | 2016-09-25 | 2016-10-01
Dolakha | Sahare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 7 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 8 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | 9 | MC |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 3 | 0
Dolakha | Sahare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sahare | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 12
Dolakha | Sailungeswor | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 1 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 2 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 3 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 4 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 5 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 6 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 7 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 8 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor | 9 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18
Dolakha | Sailungeswor | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sailungeswor |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 73
Dolakha | Sundrawati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-10 | 2016-02-12
Dolakha | Sundrawati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sundrawati | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 24
Dolakha | Sundrawati |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 41
Dolakha | Sunkhani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 4 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2015-08-27 | 2015-09-08
Dolakha | Sunkhani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 5 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-04 | 2016-02-04
Dolakha | Sunkhani | 5 | PLAN |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2015-08-27 | 2015-09-08
Dolakha | Sunkhani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Sunkhani |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 45
Dolakha | Suri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 1 | LWF | HURADEC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 19 | 19 | 2017-11-29 | 2017-12-05
Dolakha | Suri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 2 | LWF | HURADEC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 11 | 11 | 2017-11-29 | 2017-12-05
Dolakha | Suri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Suri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 84 | 36 | 2016-06-13 | 2016-06-13
Dolakha | SusmaChhemawati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 9 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-22 | 2016-04-15
Dolakha | SusmaChhemawati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | SusmaChhemawati | 1,2,3 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-15 | 2016-07-21
Dolakha | SusmaChhemawati | 4,5,7 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-24 | 2016-08-01
Dolakha | SusmaChhemawati | 6,8,9 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-07 | 2016-07-13
Dolakha | SusmaChhemawati | All | NRCS | NRCS | SRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2015-12-28 | 2016-01-21
Dolakha | SusmaChhemawati | ALL | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-11-09 | 2016-11-15
Dolakha | SusmaChhemawati |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 96
Dolakha | Syama | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Dolakha | Syama | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Gorkha | AaruArbang | 1 | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 50 | 50 | 2015-12-01 | 2016-01-30
Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 72 | 0
Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 72 | 0
Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 72 | 0
Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 2 | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 50 | 50 | 2016-08-15 | 2016-10-03
Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 126 | 0
Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 126 | 0
Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 126 | 0
Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 49 | 0
Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 49 | 0
Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 49 | 0
Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 113 | 0
Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 113 | 0
Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 113 | 0
Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 174 | 0
Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 174 | 0
Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 174 | 0
Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 152 | 0
Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 152 | 0
Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 152 | 0
Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 19 | 2017-01-04 | 2017-01-10
Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 101 | 0
Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 101 | 0
Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 101 | 0
Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 21 | 2016-12-03 | 2016-12-09
Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 164 | 0
Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 164 | 0
Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 164 | 0
Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-03 | 2017-02-09
Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-05 | 2017-05-01
Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 139 | 0
Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 139 | 0
Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 139 | 0
Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruArbang | All | HELVETAS | Kantipur | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-13 | 2016-10-03
Gorkha | AaruArbang | All | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-13 | 2016-09-18
Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 181 | 0
Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 181 | 0
Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 181 | 0
Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-12-08 | 2016-12-14
Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 21 | 0
Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 21 | 0
Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 21 | 0
Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 178 | 0
Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 178 | 0
Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 178 | 0
Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-12-08 | 2016-12-14
Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 108 | 0
Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 108 | 0
Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 108 | 0
Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-12-08 | 2016-12-14
Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-02-25 | 2017-04-20
Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 73 | 0
Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 73 | 0
Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 73 | 0
Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-28 | 2017-02-03
Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 34 | 0
Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 34 | 0
Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 34 | 0
Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-12-24 | 2016-12-30
Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 67 | 0
Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 67 | 0
Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 67 | 0
Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 50
Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 50
Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 50
Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-12-24 | 2016-12-30
Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 55 | 0
Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 55 | 0
Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 55 | 0
Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-12-24 | 2016-12-30
Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | AaruChanuate |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 91
Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 226 | 0
Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 226 | 0
Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 226 | 0
Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 5 | 2016-12-10 | 2016-12-16
Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 121 | 0
Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 121 | 0
Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 121 | 0
Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-12-10 | 2016-12-16
Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 82 | 0
Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 82 | 0
Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 82 | 0
Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-12-14 | 2016-12-20
Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 123 | 0
Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 123 | 0
Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 123 | 0
Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-12-10 | 2016-12-16
Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-07 | 2017-05-01
Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 89 | 0
Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 89 | 0
Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 89 | 0
Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-12-10 | 2016-12-16
Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 85 | 0
Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 85 | 0
Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 85 | 0
Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-12-14 | 2016-12-20
Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-07 | 2017-05-01
Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 100 | 0
Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 100 | 0
Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 100 | 0
Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-12-03 | 2016-12-09
Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 148 | 0
Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 148 | 0
Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 148 | 0
Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-12-03 | 2016-12-09
Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 182 | 0
Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 182 | 0
Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 182 | 0
Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 17 | 2017-02-12 | 2017-02-18
Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Aarupokhari | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-02 | 2016-08-06
Gorkha | Aarupokhari | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 120 | 120 | 2016-06-02 | 2016-08-06
Gorkha | Asrang | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 1 | CA | PANCHA KANYA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 6 | 2016-05-01 | 2016-05-15
Gorkha | Asrang | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Asrang | All | PAF | SDSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Asrang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 52
Gorkha | Asrang |  | PA | GORETO GORKHA | PA-UK | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 10 | 10 | 2016-02-07 | 2016-02-11
Gorkha | Asrang |  | PA | GORETO GORKHA | PA-UK | Training | Vocational training | Plumber (CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2015-12-13 | 2016-01-13
Gorkha | Asrang |  | CA | GORETO GORKHA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0
Gorkha | Asrang |  | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households |  | Planned | 60 | 0
Gorkha | Baguwa | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Ward no. 1 Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Dudh Kanya Devi Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Shiva Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Eakikrit Milan Basti Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Machha Pokhari Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Chandi Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-06-17
Gorkha | Baguwa | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Shiva Mandir Purna Nirman Samudaik Samiti
Gorkha | Baguwa | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Nawa Jagaran Purna Nirman Samudaik Samiti
Gorkha | Baguwa | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-03-07 | 2016-03-11
Gorkha | Baguwa |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 75
Gorkha | Bakrang | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 9 | 9 | 2016-10-10 | 2016-11-25
Gorkha | Bakrang | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-14 | 2016-07-20
Gorkha | Bakrang | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-02 | 2016-08-08
Gorkha | Bakrang | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-09 | 2016-08-15
Gorkha | Bakrang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 268
Gorkha | Bhirkot | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Bhirkot | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 9 | 9 | 2016-10-10 | 2016-11-25 | Dissegrated data were not in hand
Gorkha | Bhirkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-15 | 2016-06-21
Gorkha | Bhirkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-24 | 2016-06-30
Gorkha | Bhirkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-04 | 2016-07-10
Gorkha | Bhirkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-05 | 2016-07-11
Gorkha | Bhirkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-14 | 2016-07-20
Gorkha | Bhirkot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 484
Gorkha | Bhumlichok | 5 | ACN | ACN | INFUK-GZB-Others | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-08-20 | 2016-08-27 | We are planning to give this training for skill manpower
Gorkha | Bhumlichok | All | PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Bhumlichok | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 17 | 2016-01-25 | 2016-01-29
Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 17 | 0
Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 17 | 0
Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 17 | 0
Gorkha | Bihi | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0
Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0
Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0
Gorkha | Bihi | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 32 | 0
Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 32 | 0
Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 32 | 0
Gorkha | Bihi | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0
Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0
Gorkha | Bihi | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0
Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0
Gorkha | Bihi | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Bihi | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 16 | 0
Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 16 | 0
Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 16 | 0
Gorkha | Bihi | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 26 | 0
Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 26 | 0
Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 26 | 0
Gorkha | Bihi | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 40 | 0
Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 40 | 0
Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 40 | 0
Gorkha | Bihi | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 37 | 0
Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 37 | 0
Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 37 | 0
Gorkha | Bihi | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2017-01-01 | 2017-01-07
Gorkha | Bihi | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Borlang | 1 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04
Gorkha | Borlang | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04
Gorkha | Borlang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 89
Gorkha | Borlang |  | PA | GORETO GORKHA | PA-UK | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 14 | 14 | 2016-02-07 | 2016-02-11
Gorkha | Borlang |  | PA | GORETO GORKHA | PA-UK | Training | Vocational training | Plumber (CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 | 2015-12-13 | 2016-01-13
Gorkha | Borlang |  | CA | GORETO GORKHA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0
Gorkha | Borlang |  | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 60 | 0
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-06 | 2017-05-01
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 262 | 0
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 262 | 0
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 262 | 0
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-05-09 | 2016-05-13
Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-02-08 | 2016-03-15 | 30 days vocational training
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 203 | 0
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 203 | 0
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 203 | 0
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-05-09 | 2016-05-13
Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-02-08 | 2016-03-15 | 30 days vocational training
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 311 | 0
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 311 | 0
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 311 | 127 | 2016-02-17 | 2016-02-28
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2015-11-24 | 2015-11-28
Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-02-08 | 2016-03-15 | 30 days vocational training
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 249 | 0
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 249 | 0
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 249 | 213 | 2016-02-01 | 2016-02-14
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 16 | 16 | 2015-11-24 | 2015-11-28
Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 3 | 2015-11-12 | 2015-12-16 | 30 days vocational training
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 184 | 0
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 184 | 0
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 184 | 0
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 9 | 2016-03-14 | 2016-03-18
Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-11-12 | 2015-12-16 | 30 days vocational training
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 164 | 0
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 164 | 0
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 164 | 0
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-14 | 2016-03-18
Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-11-12 | 2015-12-16 | 30 days vocational training
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 79 | 0
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 79 | 0
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 79 | 0
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 6 | 2016-02-08 | 2016-02-12
Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 5 | 2016-03-28 | 2016-05-03 | 30 days vocational training
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 158 | 0
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 158 | 0
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 158 | 0
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-02-08 | 2016-02-12
Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-28 | 2016-05-03 | 30 days vocational training
Gorkha | Bunkot | 9 | JICA | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 183 | 0
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 183 | 0
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 183 | 0
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2016-02-08 | 2016-02-12
Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-03-28 | 2016-05-03 | 30 days vocational training
Gorkha | Bunkot | ALL | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 1
Gorkha | Chhaikampar | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 89
Gorkha | Chhaikampar | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 48
Gorkha | Chhaikampar | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 45
Gorkha | Chhaikampar | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 77
Gorkha | Chhaikampar | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 66
Gorkha | Chhaikampar | 6 | PIN | PIN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-07-15 | 2015-10-06
Gorkha | Chhaikampar | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 65
Gorkha | Chhaikampar | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 57
Gorkha | Chhaikampar | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 77
Gorkha | Chhaikampar | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 61
Gorkha | Chhaikampar | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Chhaikampar | All | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 269 | 0
Gorkha | Chhoprak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 109 | 109 | 2016-06-09 | 2016-08-12
Gorkha | Chhoprak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 2 | 2 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Chhoprak | 6 | ROTARY | CDRA | ROTARY | Reconstruction through contractors | Construction | Private house |  | # of constructions |  | Planned | 50 | 0
Gorkha | Chhoprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 17 | 17 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08
Gorkha | Chhoprak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 10 | 10 | 2016-06-09 | 2016-06-09
Gorkha | Chhoprak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-07-18
Gorkha | Chhoprak |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 52
Gorkha | Chhoprak |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0
Gorkha | Chhoprak |  | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 45 | 0
Gorkha | Chhoprak |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Chumchet | 3 | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 30 | 0
Gorkha | Chumchet | ALL | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Completed | 30 | 29 | 2016-12-15 | 2016-12-22
Gorkha | Chumchet |  | SP | UVN |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households |  | Planned | 33 | 0
Gorkha | Chumchet |  | SP | UVN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  | Hand over to vulnerabl benificiaries ( total Cost 8 Lakhs Per House Expect transportation)
Gorkha | Darbhung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 36 | 2016-06-23 | 2016-06-23
Gorkha | Darbhung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 44 | 2016-06-24 | 2016-06-24
Gorkha | Darbhung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 89 | 2016-07-19 | 2016-07-20
Gorkha | Darbhung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 111 | 2016-06-23 | 2016-07-01
Gorkha | Darbhung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 28 | 2016-07-14 | 2016-07-14
Gorkha | Darbhung | 2 and 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 48 | 2016-07-01 | 2016-07-01
Gorkha | Darbhung | 2,4, 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 41 | 2016-07-13 | 2016-07-13
Gorkha | Darbhung | 3 and 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 57 | 2016-07-07 | 2016-07-08
Gorkha | Darbhung | 3,4 and 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 66 | 2016-07-14 | 2016-07-14
Gorkha | Darbhung | 5 and 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 27 | 2016-07-15 | 2016-07-15
Gorkha | Darbhung | 5 and 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 9 | 2016-07-22 | 2016-07-22
Gorkha | Darbhung | 6,7 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 35 | 2016-07-21 | 2016-07-21
Gorkha | Darbhung | 7 and 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 37 | 2016-07-13 | 2016-07-13
Gorkha | Darbhung | 7 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 14 | 2016-07-15 | 2016-07-15
Gorkha | Darbhung | 8 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-07-14 | 2016-07-14
Gorkha | Darbhung | All | PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Deurali | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 40 | 2016-08-25 | 2016-08-25
Gorkha | Deurali | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  | Organized in Pandrung; People from Deurali participated
Gorkha | Deurali | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 77 | 2016-08-24 | 2016-08-25
Gorkha | Deurali | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 125 | 2016-08-11 | 2016-09-07
Gorkha | Deurali | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 210 | 180 | 2016-08-11 | 2016-09-01
Gorkha | Deurali | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 |  |  | Organized in Pandrung; People from Deurali participated
Gorkha | Deurali | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 250 | 197 | 2016-08-23 | 2016-09-02
Gorkha | Deurali | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  | Organized in Pandrung; People from Deurali participated
Gorkha | Deurali | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 93 | 2016-08-04 | 2016-08-05
Gorkha | Deurali | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 144 | 2016-08-10 | 2016-09-02
Gorkha | Deurali | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 93 | 2016-08-16 | 2016-08-17
Gorkha | Deurali | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 112 | 2016-08-12 | 2016-08-26
Gorkha | Deurali | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Deurali | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Deurali |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 325
Gorkha | Deurali |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 46 | 46 |  |  | Extracted from JICA Pandrung Database
Gorkha | Dhawa | All | PAF | SDSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 50 | 0
Gorkha | Dhawa | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2016-03-04 | 2016-03-08
Gorkha | Dhawa |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 132
Gorkha | Dhuwakot | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Dhuwakot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 400
Gorkha | Fujel | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 400 | 345 | 2016-05-18 | 2016-05-31
Gorkha | Fujel | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-05-25 | 2016-05-25
Gorkha | Fujel | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 44 | 2016-05-11 | 2016-05-11
Gorkha | Fujel | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 126 | 2016-05-10 | 2016-05-17
Gorkha | Fujel | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 83 | 2016-05-04 | 2016-05-04
Gorkha | Fujel | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 91 | 2016-05-10 | 2016-05-11
Gorkha | Fujel | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 88 | 2016-05-04 | 2016-05-05
Gorkha | Fujel | 2 and 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 200 | 187 | 2016-05-26 | 2016-05-31
Gorkha | Fujel | 4 and 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 68 | 2016-05-12 | 2016-05-19
Gorkha | Fujel | 4,5 and 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 40 | 2016-05-18 | 2016-05-18
Gorkha | Fujel | 4,6 and 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 40 | 2016-05-13 | 2016-05-13
Gorkha | Fujel | 4,7 and 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 38 | 2016-05-12 | 2016-05-12
Gorkha | Fujel | 5,6 and 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 45 | 2015-05-06 | 2015-05-06
Gorkha | Fujel | 8 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 43 | 2016-05-06 | 2016-05-06
Gorkha | Fujel | All | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 968 | 968 | 2016-05-24 | 2016-06-23
Gorkha | Fujel |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 148
Gorkha | Gakhu | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 34 | 34 | 2016-08-12 | 2016-08-12
Gorkha | Gakhu | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 56 | 56 | 2016-07-26 | 2016-07-26
Gorkha | Gakhu | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 24 | 24 | 2016-07-23 | 2016-07-23
Gorkha | Gakhu | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-07-25 | 2016-07-25
Gorkha | Gakhu | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 146 | 146 | 2016-08-12 | 2016-08-12
Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Gakhu | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 94 | 94 | 2016-08-11 | 2016-08-11
Gorkha | Gakhu | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 192 | 192 | 2016-08-10 | 2016-08-10
Gorkha | Gakhu | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-08-07 | 2016-08-07
Gorkha | Gakhu | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gakhu | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 57 | 57 | 2016-08-07 | 2016-08-07
Gorkha | Gakhu | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-05 | 2016-08-05
Gorkha | Gakhu | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-10-10 | 2016-11-25
Gorkha | Gakhu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 97
Gorkha | Gakhu |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Ghairung | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 145
Gorkha | Ghairung | 1 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Ghairung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 140 | 148 | 2016-01-24 | 2016-04-19
Gorkha | Ghairung | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 86
Gorkha | Ghairung | 2 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Ghairung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 58 | 2016-02-19 | 2016-02-19
Gorkha | Ghairung | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 228 | 228
Gorkha | Ghairung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Ghairung | 3 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8
Gorkha | Ghairung | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 130 | 136 | 2016-02-18 | 2016-04-13
Gorkha | Ghairung | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 224 | 224
Gorkha | Ghairung | 4 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 7
Gorkha | Ghairung | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 61 | 2016-02-25 | 2016-02-25
Gorkha | Ghairung | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 189
Gorkha | Ghairung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Ghairung | 5 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Ghairung | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 130 | 164 | 2016-02-10 | 2016-04-28
Gorkha | Ghairung | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 161
Gorkha | Ghairung | 6 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Ghairung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-02-12 | 2016-02-12
Gorkha | Ghairung | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 157
Gorkha | Ghairung | 7 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5
Gorkha | Ghairung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 90 | 110 | 2015-12-19 | 2016-04-07
Gorkha | Ghairung | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 190
Gorkha | Ghairung | 8 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5
Gorkha | Ghairung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 45 | 2016-02-11 | 2016-02-11
Gorkha | Ghairung | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 171
Gorkha | Ghairung | 9 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 7
Gorkha | Ghairung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 84 | 2016-02-26 | 2016-04-27
Gorkha | Ghairung | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghairung | 1 and 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-04-20 | 2016-04-20
Gorkha | Ghairung | 2 and 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 47 | 2016-04-21 | 2016-04-21
Gorkha | Ghairung | 5, 2, 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 43 | 2016-04-08 | 2016-04-08
Gorkha | Ghairung | 6 and 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 70 | 69 | 2016-04-22 | 2016-04-26
Gorkha | Ghairung | All | PAF | LLCSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Ghairung | All | OXFAM-GB | TMUC |  | Others | Others | (Please specify in Activity Detail) | Model Panel Construction (no. of constructions) |  | Yes | Planned | 3 | 0 |  |  | EQ Resilient Technique incorporated Pollutry farms
Gorkha | Ghairung | All | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1053 | 0 |  |  | Information Center
Gorkha | Ghairung | All | OXFAM-GB | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 60
Gorkha | Ghairung | All | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 986 | 986 | 2016-03-05 | 2016-05-15
Gorkha | Ghairung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 115
Gorkha | Ghyachok | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 1 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 1 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 2 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 2 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 3 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 3 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 4 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 4 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 5 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 5 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 6 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 6 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 8 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Ghyachok | 9 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity.
Gorkha | Ghyachok | All | PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0
Gorkha | Ghyalchok | 2 | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-12-01 | 2016-10-01
Gorkha | Ghyalchok | 9 | HELVETAS | Kantipur | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Ghyalchok | 9 | HELVETAS | Kantipur | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Ghyalchok | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 48 | 48 | 2016-01-25 | 2016-01-29
Gorkha | Gorakha N.P. | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 261 | 0
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 261 | 0
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 462 | 0
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 1 | CARE-N | CARE-N | ADH | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 26 | 26 | 2016-05-15 | 2016-05-21
Gorkha | Gorakha N.P. | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 175 | 0
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 175 | 0
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 369 | 0
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Demonstration Construction | House | Compressed stabilized earthen block technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2015-12-05 | 2016-12-01
Gorkha | Gorakha N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2015-12-05 | 2016-12-01
Gorkha | Gorakha N.P. | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 157 | 0
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 157 | 0
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 574 | 0
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 612 | 0
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 261 | 0
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 521 | 0
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 24 | 2017-03-07 | 2017-03-14
Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 18 | 2016-05-09 | 2016-06-14
Gorkha | Gorakha N.P. | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 340 | 0
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 340 | 0
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 175 | 0
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 338 | 0
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 253 | 0
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 253 | 0
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 157 | 0
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 606 | 0
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-10 | 2017-02-16
Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 338 | 0
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 338 | 0
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 612 | 0
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 460 | 0
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2017-02-10 | 2017-02-16
Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 18 | 2016-05-09 | 2016-06-16
Gorkha | Gorakha N.P. | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 606 | 0
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 606 | 0
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 340 | 0
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 484 | 0
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-20 | 2017-02-26
Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 660 | 0
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 660 | 0
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 253 | 0
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 328 | 0
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 24 | 2017-02-21 | 2017-02-27
Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 10 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 10 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 484 | 0
Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 10 | ACN | ACN | CEDAR | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Completed | 15 | 13 | 2016-04-06 | 2016-04-13 | This training we focused for our own technical staff.
Gorkha | Gorakha N.P. | 11 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 11 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 328 | 0
Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 24 | 2016-09-01 | 2017-03-31
Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 12 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 12 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 462 | 0
Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 18 | 2017-03-01 | 2017-03-09
Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 18 | 2016-05-09 | 2016-06-16
Gorkha | Gorakha N.P. | 13 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 13 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 369 | 0
Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0
Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 17 | 2017-03-01 | 2017-03-09
Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 14 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 50 | 45 | 2016-06-24 | 2016-06-30
Gorkha | Gorakha N.P. | 14 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 14 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 574 | 0
Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0
Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 20 | 2017-03-03 | 2017-03-11
Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. | 15 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 50 | 45 | 2016-06-24 | 2016-06-30
Gorkha | Gorakha N.P. | 15 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 15 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 521 | 0
Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0
Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 20 | 2017-03-03 | 2017-03-11
Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Gorakha N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 578
Gorkha | Gorakha N.P. |  | JICA |  |  | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 276 | 189 | 2016-07-28 | 2016-09-06
Gorkha | Gumda | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 37 | 37 | 2016-07-09 | 2016-07-09
Gorkha | Gumda | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 36 | 36 | 2016-06-04 | 2016-07-10
Gorkha | Gumda | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 37 | 37 | 2016-06-04 | 2016-07-11
Gorkha | Gumda | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 59 | 59 | 2016-06-04 | 2016-07-15
Gorkha | Gumda | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 75 | 75 | 2016-06-04 | 2016-07-15
Gorkha | Gumda | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 85 | 85 | 2016-06-04 | 2016-06-04
Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Gumda | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 70 | 70 | 2016-06-04 | 2016-07-18
Gorkha | Gumda | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-06-04 | 2016-07-17
Gorkha | Gumda | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Gumda | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-06-04 | 2016-07-13
Gorkha | Gumda | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-28 | 2016-06-03
Gorkha | Gumda | All | PAF | HADC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Gumda | ALL | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 606 | 34 | 2016-11-01
Gorkha | Gumda |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Hansapur | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Hansapur | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Muktichetra CBRC
Gorkha | Hansapur | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Hansapur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Hansapur-2, Saraswoti CBRC
Gorkha | Hansapur | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Hansapur | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Lapsibot CBRC
Gorkha | Hansapur | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6
Gorkha | Hansapur | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Kafaldanda CBRC
Gorkha | Hansapur | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Hansapur | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Janakalyan CBRC
Gorkha | Hansapur | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Hansapur | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Khalanga CBRC
Gorkha | Hansapur | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Hansapur | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Sitaldanda CBRC
Gorkha | Hansapur | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Hansapur | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Budhisinghtar CBRC
Gorkha | Hansapur | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Hansapur | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Dhadinggara CBRC
Gorkha | Hansapur | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Sungure CBRC
Gorkha | Hansapur |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 236
Gorkha | Hansapur |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 65
Gorkha | Harmhi | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 42 | 42 | 2016-08-31 | 2016-09-07
Gorkha | Harmhi | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-31 | 2016-08-06
Gorkha | Harmhi | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 66 | 66 | 2016-09-01 | 2016-09-01
Gorkha | Harmhi | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-31 | 2016-08-06
Gorkha | Harmhi | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-08-30 | 2016-08-30
Gorkha | Harmhi | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-07-31 | 2016-08-13
Gorkha | Harmhi | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 50 | 50 | 2016-09-02 | 2016-09-02
Gorkha | Harmhi | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-07-31 | 2016-08-06
Gorkha | Harmhi | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 49 | 49 | 2016-09-07 | 2016-09-07
Gorkha | Harmhi | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-31 | 2016-08-06
Gorkha | Harmhi | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 50 | 50 | 2016-08-29 | 2016-08-29
Gorkha | Harmhi | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-07 | 2016-08-13
Gorkha | Harmhi | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 43 | 43 | 2016-09-03 | 2016-09-03
Gorkha | Harmhi | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-07 | 2016-08-13
Gorkha | Harmhi | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 90 | 90 | 2016-08-28 | 2016-08-28
Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-31 | 2016-08-13
Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Harmhi | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Harmhi | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 160 | 160 | 2016-07-27 | 2016-07-27
Gorkha | Harmhi | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-07-31 | 2016-08-13
Gorkha | Harmhi | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-01-21 | 2016-03-31
Gorkha | Harmhi | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-15 | 2016-06-21
Gorkha | Harmhi | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-24 | 2016-06-30
Gorkha | Harmhi | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-13 | 2016-07-19
Gorkha | Harmhi |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 94
Gorkha | Harmhi |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Jaubari | 1 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-08 | 2016-05-12
Gorkha | Jaubari | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Jaubari | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Laliguras CBRC
Gorkha | Jaubari | 2 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-08 | 2016-05-12
Gorkha | Jaubari | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Jaubari | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-12 | Janajagaran CBRC
Gorkha | Jaubari | 3 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-08 | 2016-05-12
Gorkha | Jaubari | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Jaubari | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-11 | Shreesatya CBRC
Gorkha | Jaubari | 4 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-02 | 2016-05-06
Gorkha | Jaubari | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Jaubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Langdi CBRC
Gorkha | Jaubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Balkanya CBRC
Gorkha | Jaubari | 5 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-05-02 | 2016-05-06
Gorkha | Jaubari | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Jaubari | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Gaikure CBRC
Gorkha | Jaubari | 6 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-04-27 | 2016-05-01
Gorkha | Jaubari | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Jaubari | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-12 | Sundarbazar CBRC
Gorkha | Jaubari | 7 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-04-27 | 2016-05-01
Gorkha | Jaubari | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Jaubari | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-12 | Paropakar CBRC
Gorkha | Jaubari | 8 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-04-27 | 2016-05-01
Gorkha | Jaubari | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Jaubari | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Amar CBRC
Gorkha | Jaubari | 9 | LWR | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Ongoing | 100 | 99 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save
Gorkha | Jaubari | 9 | LWR | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Ongoing | 100 | 40
Gorkha | Jaubari | 9 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-04-27 | 2016-05-01
Gorkha | Jaubari | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Jaubari | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Janajagaran CBRC
Gorkha | Jaubari | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Finamtar CBRC
Gorkha | Jaubari | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 9 | 9 | 2016-10-10 | 2016-11-25
Gorkha | Jaubari |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78
Gorkha | Kashigaun | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-07-15 | 2016-08-11
Gorkha | Kashigaun | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 54 | 54 | 2016-07-15 | 2016-08-12
Gorkha | Kashigaun | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-07-15 | 2016-08-08
Gorkha | Kashigaun | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 354 | 31 | 2016-11-01
Gorkha | Kashigaun | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 35 | 35 | 2016-07-15 | 2016-08-09
Gorkha | Kashigaun | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 58 | 58 | 2016-07-15 | 2016-08-06
Gorkha | Kashigaun | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 32 | 32 | 2016-07-15 | 2016-08-07
Gorkha | Kashigaun | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 41 | 41 | 2016-07-15 | 2016-08-10
Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Kashigaun | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 58 | 58 | 2016-07-15 | 2016-08-04
Gorkha | Kashigaun | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kashigaun | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 52 | 52 | 2016-07-15 | 2016-08-05
Gorkha | Kashigaun | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-08 | 2016-07-14
Gorkha | Kashigaun | All | PAF | SSICDC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 50 | 0
Gorkha | Kashigaun |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Kerabari | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Kerabari | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Mandali CBRC
Gorkha | Kerabari | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Kerabari | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jai Santoshi Mata CBRC
Gorkha | Kerabari | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Himchuli CBRC
Gorkha | Kerabari | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Kerabari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Annapurna CBRC
Gorkha | Kerabari | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9
Gorkha | Kerabari | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Shiva Shakti CBRC
Gorkha | Kerabari | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Kerabari | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Deurali CBRC
Gorkha | Kerabari | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Kerabari | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Gyampeshori CBRC
Gorkha | Kerabari | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Kerabari | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Kerabari-8 CBRC
Gorkha | Kerabari | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7
Gorkha | kerabari | All | PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0
Gorkha | Kerabari |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 80
Gorkha | Kerauja | 1 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 81
Gorkha | Kerauja | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 65 | 65 | 2016-09-08 | 2016-09-08
Gorkha | Kerauja | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-22 | 2016-07-28
Gorkha | Kerauja | 2 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 105
Gorkha | Kerauja | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 43 | 43 | 2016-09-09 | 2016-09-09
Gorkha | Kerauja | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-07-22 | 2016-07-28
Gorkha | Kerauja | 3 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 56
Gorkha | Kerauja | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 21 | 21 | 2016-09-12 | 2016-09-12
Gorkha | Kerauja | 4 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 58
Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 46 | 46 | 2016-09-09 | 2016-09-09
Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-07-22 | 2016-07-28
Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Kerauja | 5 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 96
Gorkha | Kerauja | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 23 | 23 | 2016-09-16 | 2016-09-16
Gorkha | Kerauja | 6 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 73
Gorkha | Kerauja | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 35 | 35 | 2016-09-17 | 2016-09-17
Gorkha | Kerauja | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-22 | 2016-07-28
Gorkha | Kerauja | 7 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 61
Gorkha | Kerauja | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 59 | 59 | 2016-09-15 | 2016-09-15
Gorkha | Kerauja | 8 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 75
Gorkha | Kerauja | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 69 | 69 | 2016-09-14 | 2016-09-14
Gorkha | Kerauja | 9 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 65
Gorkha | Kerauja | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 18 | 18 | 2016-09-13 | 2016-09-13
Gorkha | Kerauja | All | PIN | UNIFICATION-N | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 476 | 469 | 2016-06-26 | 2016-06-29 | 30 beneficiares were not present during distribution
Gorkha | Kerauja | All | PIN | UNIFICATION-N | ECHO | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 384 | 358 | 2016-09-01 | 2016-11-01
Gorkha | Kerauja | All | OXFAM-GB | GORETO GORKHA |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 465 | 465 | 2015-12-25 | 2016-01-15 | CGI (2B PHH)
Gorkha | Kerauja | All | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 844 | 0
Gorkha | Kerauja | All | OXFAM-GB | GORETO GORKHA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0
Gorkha | Kerauja |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Kharibot | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 42 | 2016-03-10 | 2016-03-10
Gorkha | Kharibot | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 49 | 2016-03-03 | 2016-03-03
Gorkha | Kharibot | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 78 | 2016-03-16 | 2016-03-17
Gorkha | Kharibot | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 41 | 2016-03-18 | 2016-03-18
Gorkha | Kharibot | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 44 | 2016-03-11 | 2016-03-11
Gorkha | Kharibot | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 46 | 2016-03-20 | 2016-03-20
Gorkha | Kharibot | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-01-01 | 2016-01-01
Gorkha | Kharibot | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 43 | 2016-03-30 | 2016-03-30
Gorkha | Kharibot | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-03-31 | 2016-03-31
Gorkha | Kharibot | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Kharibot | 1 &2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 33 | 2015-03-04 | 2016-03-04
Gorkha | Kharibot | 1 to 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 30 | 30 | 2016-04-02 | 2016-04-02
Gorkha | Kharibot | 4 & 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 45 | 2016-03-19 | 2016-03-21
Gorkha | Kharibot | All | PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0
Gorkha | Kharibot | All | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 553 | 533 | 2016-04-07 | 2016-04-26
Gorkha | Kharibot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 81
Gorkha | Khoplang | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 54 | 54 | 2016-06-25 | 2016-08-11
Gorkha | Khoplang | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 139 | 139 | 2016-06-25 | 2016-08-10
Gorkha | Khoplang | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-06-25 | 2016-08-09
Gorkha | Khoplang | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 292 | 292 | 2016-06-25 | 2016-08-12
Gorkha | Khoplang | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-25 | 2016-08-13
Gorkha | Khoplang | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-07-30 | 2016-08-05
Gorkha | Khoplang | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 122 | 122 | 2016-06-25 | 2016-08-08
Gorkha | Khoplang | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 66 | 66 | 2016-06-25 | 2016-08-13
Gorkha | Khoplang | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Khoplang | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 84 | 84 | 2016-07-29 | 2016-07-29
Gorkha | Khoplang | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Khoplang | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 109 | 109 | 2016-07-28 | 2016-08-11
Gorkha | Khoplang | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-18 | 2016-06-24
Gorkha | Khoplang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 100
Gorkha | Khoplang |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Laprak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 64 | 64 | 2016-07-08 | 2016-07-10
Gorkha | Laprak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 103 | 103 | 2016-07-09 | 2016-07-10
Gorkha | Laprak | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-07-10 | 2016-07-10
Gorkha | Laprak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 66 | 66 | 2016-07-10 | 2016-07-12
Gorkha | Laprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 56 | 56 | 2016-07-10 | 2016-07-13
Gorkha | Laprak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 73 | 73 | 2016-07-10 | 2016-07-14
Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Laprak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 51 | 51 | 2016-07-10 | 2016-07-20
Gorkha | Laprak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 65 | 65 | 2016-07-10 | 2016-07-17
Gorkha | Laprak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 68 | 68 | 2016-07-10 | 2016-07-18
Gorkha | Laprak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-10 | 2016-06-16
Gorkha | Laprak | All | PIN | UNIFICATION-N | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 640 | 627 | 2016-10-25 | 2016-10-28
Gorkha | Laprak | All | PIN | UNIFICATION-N | ECHO | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 397 | 397 | 2016-09-01 | 2016-11-01
Gorkha | Laprak | All | PAF | HADC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Laprak | ALL | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 573 | 25 | 2016-11-01
Gorkha | Laprak |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Lapu | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 113 | 0
Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 113 | 0
Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 113 | 0
Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 26 | 26 | 2017-01-04 | 2017-02-09
Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 17 | 0
Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 17 | 0
Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 17 | 0
Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2016-11-30 | 2016-12-06
Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 86 | 0
Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 86 | 0
Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 86 | 0
Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2017-01-04 | 2017-01-10
Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 50 | 0
Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 50 | 0
Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 50 | 0
Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-01-04 | 2017-01-10
Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 34 | 0
Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 34 | 0
Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 34 | 0
Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2016-11-30 | 2016-12-06
Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-02-26 | 2017-04-20
Gorkha | Lapu | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 82 | 0
Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 82 | 0
Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 82 | 0
Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2016-11-30 | 2016-12-06
Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 57 | 0
Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 57 | 0
Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 57 | 0
Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2016-11-30 | 2016-12-06
Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 58 | 0
Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 58 | 0
Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 58 | 0
Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-11-30 | 2016-12-06
Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lapu | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 25 | 0
Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 25 | 0
Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 25 | 0
Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-11-30 | 2016-12-06
Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 35 | 0
Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 35 | 0
Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 35 | 0
Gorkha | Lho | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-12-24 | 2017-01-04
Gorkha | Lho | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 50 | 0
Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 50 | 0
Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 50 | 0
Gorkha | Lho | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2016-12-24 | 2017-01-04
Gorkha | Lho | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 43 | 0
Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 43 | 0
Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 43 | 0
Gorkha | Lho | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2016-12-24 | 2017-01-04
Gorkha | Lho | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 55 | 0
Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 55 | 0
Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 55 | 0
Gorkha | Lho | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Lho | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30
Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30
Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30
Gorkha | Lho | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-12-24 | 2017-01-04
Gorkha | Lho | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 44 | 0
Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 44 | 0
Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 44 | 0
Gorkha | Lho | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 2 | 2016-12-24 | 2017-01-04
Gorkha | Lho | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 23 | 0
Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 23 | 0
Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 23 | 0
Gorkha | Lho | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Lho | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0
Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0
Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0
Gorkha | Lho | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Lho | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 36 | 0
Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 36 | 0
Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 36 | 0
Gorkha | Lho | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-12-24 | 2017-01-04
Gorkha | Lho | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Makaising | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Makaising | All | PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Makaising | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-02-15 | 2016-02-19
Gorkha | Manakamana | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manakamana | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 9 | 9 | 2016-10-10 | 2016-11-25 | Dissegrated data were not in hand
Gorkha | Manakamana | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2016-07-23 | 2016-07-29
Gorkha | Manakamana | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-24 | 2016-07-30
Gorkha | Manakamana | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-01 | 2016-08-07
Gorkha | Manakamana | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-10 | 2016-08-16
Gorkha | Manbu | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 70 | 0
Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 70 | 0
Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 70 | 0
Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2017-01-01 | 2017-01-07
Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 152 | 0
Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 152 | 0
Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 152 | 0
Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2017-01-01 | 2017-01-07
Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 264 | 0
Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 264 | 0
Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 264 | 0
Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2017-01-01 | 2017-01-07
Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 185 | 0
Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 185 | 0
Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 185 | 0
Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 5 | 2017-01-01 | 2017-01-07
Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 224 | 0
Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 224 | 0
Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 224 | 0
Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 5 | 2017-01-16 | 2017-01-22
Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 305 | 0
Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 305 | 0
Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 305 | 0
Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2017-01-16 | 2017-01-22
Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-02-27 | 2017-04-20
Gorkha | Manbu | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 228 | 0
Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 228 | 0
Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 228 | 0
Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-12-10 | 2016-12-16
Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 216 | 0
Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 216 | 0
Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 216 | 0
Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-12-10 | 2016-12-16
Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 203 | 0
Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 203 | 0
Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 203 | 0
Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-12-10 | 2016-12-16
Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Manbu | All | NDS | NDS | MEDICO-I | Training | Short training | Carpenter |  | # of trainees | Yes | Ongoing | 120 | 28 | 2016-07-01 | 2017-04-01
Gorkha | Masel | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 17 | 2016-04-06 | 2016-04-12
Gorkha | Masel | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Masel | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Ward no. 1 Purna Nirman Samudaik Samiti
Gorkha | Masel | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 13 | 2016-04-06 | 2016-04-12
Gorkha | Masel | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Masel | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Ward no. 2 Purna Nirman Samudaik Samiti
Gorkha | Masel | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 30 | 2016-04-06 | 2016-07-26
Gorkha | Masel | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Masel | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ujyalo Purna Nirman Samudaik Samiti
Gorkha | Masel | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 11 | 2016-04-06 | 2016-04-12
Gorkha | Masel | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Masel | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Ward no. 4 Purna Nirman Samudaik Samiti
Gorkha | Masel | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 11 | 2016-04-01 | 2016-04-07
Gorkha | Masel | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Shree Krishna Purna Nirman Samudaik Samiti
Gorkha | Masel | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 12 | 2016-04-01 | 2016-04-07
Gorkha | Masel | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Masel | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Khagi Thok Purna Nirman Samudaik Samiti
Gorkha | Masel | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2016-04-01 | 2016-04-07
Gorkha | Masel | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Masel | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Brindawati Purna Nirman Samudaik Samiti
Gorkha | Masel | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 11 | 2016-04-01 | 2016-04-07
Gorkha | Masel | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Masel | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Devi Sthan Purna Nirman Samudaik Samiti
Gorkha | Masel | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 14 | 2016-04-01 | 2016-04-07
Gorkha | Masel | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2016-02-29
Gorkha | Masel | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8
Gorkha | Masel | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Mandali Purna Nirman Samudaik Samiti
Gorkha | Masel | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 200 | 200 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save
Gorkha | Masel | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Ongoing | 200 | 94
Gorkha | Masel | All | SCI | SSICDC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-04 | 2017-02-12
Gorkha | Masel | All | SCI | SSICDC | SCI | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB Training( Block Making Training) | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-03-10
Gorkha | Masel | All | PAF | SDSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Masel |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 63
Gorkha | Masel |  | SCI | SSICDC |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0
Gorkha | Masel |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-02-29
Gorkha | Masel |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78
Gorkha | Muchhok | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Muchhok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Muchhok-1 CBRC
Gorkha | Muchhok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Vryangdada CBRC
Gorkha | Muchhok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Manighaun CBRC
Gorkha | Muchhok | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 189 | 189 | 2016-06-08 | 2016-09-01
Gorkha | Muchhok | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Dhiska CBRC
Gorkha | Muchhok | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 78 | 78 | 2016-08-12 | 2016-08-12
Gorkha | Muchhok | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Muchhok-3, Muchhoktar CBRC
Gorkha | Muchhok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Muchhok-3 CBRC
Gorkha | Muchhok | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 54 | 54 | 2016-08-05 | 2016-08-05
Gorkha | Muchhok | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-15 | 2016-07-21
Gorkha | Muchhok | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Muchhok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Muchhok-4 CBRC
Gorkha | Muchhok | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-08-11 | 2016-08-11
Gorkha | Muchhok | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-01 | 2016-06-07
Gorkha | Muchhok | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Muchhok | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Muchhok-5 CBRC
Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 91 | 91 | 2016-08-31 | 2016-08-31
Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Muchhok | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Muchhok | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Muchhok-6 CBRC
Gorkha | Muchhok | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 105 | 105 | 2016-09-03 | 2016-09-03
Gorkha | Muchhok | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Muchhok | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 56 | 56 | 2016-08-04 | 2016-08-04
Gorkha | Muchhok | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9
Gorkha | Muchhok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Muchhok-8 CBRC
Gorkha | Muchhok | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 47 | 47 | 2016-08-01 | 2016-08-01
Gorkha | Muchhok | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Muchhok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Agridanda CBRC
Gorkha | Muchhok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Dharapani CBRC
Gorkha | Muchhok | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 104 | 104 | 2016-07-31 | 2016-07-31
Gorkha | Muchhok | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-01 | 2016-07-21
Gorkha | Muchhok | All | PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0
Gorkha | Muchhok | ALL | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 861 | 50 | 2016-11-01
Gorkha | Muchhok |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 31
Gorkha | Muchhok |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78
Gorkha | Muchhok |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Namjung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 73 | 2016-08-27 | 2016-08-27
Gorkha | Namjung | 1 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 1 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 100 | 2016-08-23 | 2016-08-23
Gorkha | Namjung | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 2 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 65 | 2016-08-24 | 2016-08-24
Gorkha | Namjung | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 3 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 37 | 2016-08-10 | 2016-08-10
Gorkha | Namjung | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 4 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 116 | 2016-08-11 | 2016-08-13
Gorkha | Namjung | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 5 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 74 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 66 | 2016-08-14 | 2016-08-14
Gorkha | Namjung | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 6 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 48 | 2016-08-25 | 2016-08-25
Gorkha | Namjung | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 7 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 86 | 2016-08-26 | 2016-08-26
Gorkha | Namjung | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 8 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 50 | 2016-08-13 | 2016-08-13
Gorkha | Namjung | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04
Gorkha | Namjung | 9 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29
Gorkha | Namjung | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04
Gorkha | Namjung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 340
Gorkha | Namjung |  | CA | GORETO GORKHA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0
Gorkha | Palumtar N.P. | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 10 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 10 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 11 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 11 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 12 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 12 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 13 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 13 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Palumtar N.P. | 2,3 | PAF | LLCSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 50 | 0
Gorkha | Palumtar N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 552
Gorkha | Panchkhuwadeurali | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2016-04-17 | 2016-04-23
Gorkha | Panchkhuwadeurali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-04 | Simalkheti Purna Nirman Samudaik Samiti
Gorkha | Panchkhuwadeurali | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 14 | 2016-07-28 | 2016-05-02
Gorkha | Panchkhuwadeurali | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-05 | Mandali Chautara Purna Nirman Samudaik Samiti
Gorkha | Panchkhuwadeurali | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 10 | 2016-04-17 | 2016-04-23
Gorkha | Panchkhuwadeurali | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Bhawani Purna Nirman Samudaik Samiti
Gorkha | Panchkhuwadeurali | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 13 | 2016-07-28 | 2016-05-02
Gorkha | Panchkhuwadeurali | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-09 | Dharapani Purna Nirman Samudaik Samiti
Gorkha | Panchkhuwadeurali | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 15 | 2016-04-17 | 2016-04-23
Gorkha | Panchkhuwadeurali | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Lakuridhara Purna Nirman Samudaik Samiti
Gorkha | Panchkhuwadeurali | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-07-28 | 2016-05-02
Gorkha | Panchkhuwadeurali | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Aamle Purna Nirman Samudaik Samiti
Gorkha | Panchkhuwadeurali | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 14 | 2016-07-26 | 2016-05-02
Gorkha | Panchkhuwadeurali | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Panchkhuwadeurali | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Panchkhuwadeurali | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-02 | 2016-08-06
Gorkha | Panchkhuwadeurali | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 130 | 130 | 2016-06-02 | 2016-10-01
Gorkha | Panchkhuwadeurali |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0
Gorkha | Panchkhuwadeurali |  | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 60 | 0
Gorkha | Pandrung | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 11 | 2016-04-17 | 2016-04-23
Gorkha | Pandrung | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Gau Sudhar Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 4 | 2016-04-17 | 2016-04-23
Gorkha | Pandrung | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Bramha Charini Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 5 | 2016-04-17 | 2016-04-23
Gorkha | Pandrung | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Bhawani Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 13 | 2016-04-17 | 2016-04-23
Gorkha | Pandrung | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Pandrung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Thulo Pandrung Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 14 | 2016-04-17 | 2016-04-23
Gorkha | Pandrung | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9
Gorkha | Pandrung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Thali Bari Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 6 | 2016-04-26 | 2016-05-02
Gorkha | Pandrung | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Lama Gau Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 6 | 2016-04-26 | 2016-05-02
Gorkha | Pandrung | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Pandrung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Mandali Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 5 | 2016-04-26 | 2016-05-02
Gorkha | Pandrung | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Jana Jagriti Purna Nirman Samudaik Samiti
Gorkha | Pandrung | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 15 | 2016-04-26 | 2016-05-02
Gorkha | Pandrung | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Kalika Purna Nirman Samudaik Samiti
Gorkha | Pandrung | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Ongoing | 120 | 44
Gorkha | Pandrung | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 120 | 120 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save
Gorkha | Pandrung | All | SCI | SSICDC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-18 | 2017-03-29
Gorkha | Pandrung | All | SCI | SSICDC | SCI | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB Training( Block Making Training) | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-03-10
Gorkha | Pandrung | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 70 | 70 | 2016-12-01 | 2016-10-01
Gorkha | Pandrung |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-02-08 | 2016-02-22
Gorkha | Pandrung |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 43
Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 34 | 0
Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 34 | 0
Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 34 | 0
Gorkha | Prok | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Prok | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 26 | 0
Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 26 | 0
Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 26 | 0
Gorkha | Prok | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-12-25 | 2016-12-31
Gorkha | Prok | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 3 | PIN | PIN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-09-04 | 2016-01-01
Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 27 | 0
Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 27 | 0
Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 27 | 0
Gorkha | Prok | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Prok | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 23 | 0
Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 23 | 0
Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 23 | 0
Gorkha | Prok | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-25 | 2016-12-31
Gorkha | Prok | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 28 | 0
Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 28 | 0
Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 28 | 0
Gorkha | Prok | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Prok | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 40 | 0
Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 40 | 0
Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 40 | 0
Gorkha | Prok | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-25 | 2016-12-31
Gorkha | Prok | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 25 | 0
Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 25 | 0
Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 25 | 0
Gorkha | Prok | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Prok | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 19 | 0
Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 19 | 0
Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 19 | 0
Gorkha | Prok | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Prok | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0
Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0
Gorkha | Prok | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Prok | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 28 | 0
Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 28 | 0
Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 28 | 0
Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0
Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0
Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0
Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 5 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 36 | 0
Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 36 | 0
Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 36 | 0
Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 2 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0
Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0
Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0
Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 3 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 26 | 0
Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 26 | 0
Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 26 | 0
Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 40 | 0
Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 40 | 0
Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 40 | 0
Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 12 | 0
Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 12 | 0
Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 12 | 0
Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 17 | 0
Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 17 | 0
Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 17 | 0
Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2016-12-21 | 2016-12-28
Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 11 | 0
Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 11 | 0
Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 11 | 0
Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Samagaun |  | CA | CA | IOM | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 220 | 220 | 2015-12-24 | 2015-12-28
Gorkha | Saurpani | 1 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 112
Gorkha | Saurpani | 1 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Saurpani | 1 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Saurpani | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Saurpani | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Bhuwanighunchok CBRC
Gorkha | Saurpani | 1 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Saurpani | 2 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 81
Gorkha | Saurpani | 2 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8
Gorkha | Saurpani | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Saurpani | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Manakamana CBRC
Gorkha | Saurpani | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Thani CBRC
Gorkha | Saurpani | 3 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 172
Gorkha | Saurpani | 3 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8
Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Devithan CBRC
Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Devithan CBRC
Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Bhagbhairab CBRC
Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Gyaji CBRC
Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Pokhari CBRC
Gorkha | Saurpani | 4 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 40
Gorkha | Saurpani | 4 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Saurpani | 4 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Saurpani | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Saurpani | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Thanthani CBRC
Gorkha | Saurpani | 4 | HELVETAS | Janahit | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees |  | Planned | 10 | 0
Gorkha | Saurpani | 4 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2015-12-01 | 2016-01-30
Gorkha | Saurpani | 5 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 80
Gorkha | Saurpani | 5 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Saurpani | 5 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Saurpani | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Saurpani | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Chunedada CBRC
Gorkha | Saurpani | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Srijana CBRC
Gorkha | Saurpani | 6 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 101
Gorkha | Saurpani | 6 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Saurpani | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7
Gorkha | Saurpani | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Rakshakdevi CBRC
Gorkha | Saurpani | 7 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 247 | 247
Gorkha | Saurpani | 7 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Saurpani | 7 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3
Gorkha | Saurpani | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Saurpani | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Tukrang CBRC
Gorkha | Saurpani | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Kewara CBRC
Gorkha | Saurpani | 8 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 200 | 114
Gorkha | Saurpani | 8 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Saurpani | 8 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 9
Gorkha | Saurpani | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9
Gorkha | Saurpani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Bhukampa Pratirodhi CBRC
Gorkha | Saurpani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Nawa Jagrit CBRC
Gorkha | Saurpani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Gurung Samaj CBRC
Gorkha | Saurpani | 9 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 353 | 353
Gorkha | Saurpani | 9 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8
Gorkha | Saurpani | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Tamu Samaj CBRC
Gorkha | Saurpani | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Simbu Samaj CBRC
Gorkha | Saurpani | All | PAF | UNIFICATION-N | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Saurpani | All | OXFAM-GB | GORETO GORKHA |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Ongoing | 500 | 234 |  |  | CGI 2B
Gorkha | Saurpani | All | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1535 | 0
Gorkha | Saurpani | All | OXFAM-GB | GORETO GORKHA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 59
Gorkha | Saurpani | All | HELVETAS | Janahit | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-12 | 2016-08-17
Gorkha | Saurpani | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-12-01 | 2016-10-01
Gorkha | Saurpani | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 80 | 80 | 2016-06-12 | 2016-08-17
Gorkha | Saurpani |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 65
Gorkha | Shreenathkot | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Shreenathkot | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Sankamai CBRC
Gorkha | Shreenathkot | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Shreenathkot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Srijanshil CBRC
Gorkha | Shreenathkot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Laganshil CBRC
Gorkha | Shreenathkot | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7
Gorkha | Shreenathkot | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Ghatmai CBRC
Gorkha | Shreenathkot | 3 | ACN | ACN | INFUK-GZB-Others | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-08-15 | 2016-08-22 | We are planning to give this training for skill manpower
Gorkha | Shreenathkot | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Shreenathkot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Gurung Samaj CBRC
Gorkha | Shreenathkot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Dhakalsamaj CBRC
Gorkha | Shreenathkot | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6
Gorkha | Shreenathkot | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Pipal Chautara CBRC
Gorkha | Shreenathkot | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Shreenathkot | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Shreenath Mandali CBRC
Gorkha | Shreenathkot | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Shreenathkot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Banmala CBRC
Gorkha | Shreenathkot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Laliguras CBRC
Gorkha | Shreenathkot | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Shreenathkot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Birele jhayl CBRC
Gorkha | Shreenathkot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Siamley Devisthan CBRC
Gorkha | Shreenathkot | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Shreenathkot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Thanimandali CBRC
Gorkha | Shreenathkot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Janagaran CBRC
Gorkha | Shreenathkot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Dharmawati CBRC
Gorkha | Shreenathkot | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-01-25 | 2016-03-31
Gorkha | Shreenathkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-13 | 2016-05-19
Gorkha | Shreenathkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-30 | 2016-06-05
Gorkha | Shreenathkot | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-06 | 2016-06-12
Gorkha | Shreenathkot |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 67
Gorkha | Simjung | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 117
Gorkha | simjung | 1 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6
Gorkha | Simjung | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Simjung | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Tamuthum CBRC
Gorkha | Simjung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 120
Gorkha | simjung | 2 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5
Gorkha | Simjung | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Kalika CBRC
Gorkha | Simjung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 78
Gorkha | simjung | 3 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3
Gorkha | Simjung | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Simjung | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Annapurna CBRC
Gorkha | Simjung | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Devithan CBRC
Gorkha | Simjung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 218 | 218
Gorkha | simjung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Simjung | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Simjung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Inarpani CBRC
Gorkha | Simjung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Sivalaya CBRC
Gorkha | Simjung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 77
Gorkha | Simjung | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11
Gorkha | Simjung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Dadagaun CBRC
Gorkha | Simjung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Newar tole CBRC
Gorkha | Simjung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 69
Gorkha | Simjung | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Bharke CBRC
Gorkha | Simjung | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Taguse CBRC
Gorkha | Simjung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 73
Gorkha | simjung | 7 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 1
Gorkha | Simjung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Goganpani CBRC
Gorkha | Simjung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Taple CBRC
Gorkha | Simjung | 8 | ROTARY | CDRA | ROTARY | Reconstruction through contractors | Construction | Private house |  | # of constructions |  | Planned | 50 | 0
Gorkha | Simjung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 137
Gorkha | simjung | 8 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13
Gorkha | Simjung | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Simjung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Dhodeni CBRC
Gorkha | Simjung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Pokhardada CBRC
Gorkha | Simjung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Pokharatar CBRC
Gorkha | Simjung | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 174
Gorkha | simjung | 9 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 1
Gorkha | Simjung | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Simjung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Baluwa CBRC
Gorkha | Simjung | All | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 915 | 0 |  |  | Information Center
Gorkha | Simjung | All | OXFAM-GB | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 60 | 29
Gorkha | Simjung |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 68
Gorkha | Sirdibas | 1 | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 25 | 2016-09-18 | 2016-09-24
Gorkha | Sirdibas | 8 | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 23 | 2016-08-29 | 2016-09-04
Gorkha | Sirdibas | ALL | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Completed | 40 | 38 | 2017-01-15 | 2017-01-22
Gorkha | Sirdibas |  | SP | UVN |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households |  | Planned | 33 | 0
Gorkha | Sirdibas |  | SP | UVN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0
Gorkha | Swara | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2016-05-12 | 2016-05-18
Gorkha | Swara | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Swara | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Rupa kot Swara Purna Nirman Samudaik Samiti
Gorkha | Swara | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0
Gorkha | Swara | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Swara | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Sita Gufa Bagdul Purna Nirman Samudaik Samiti
Gorkha | Swara | 2 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Swara | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 4 | 2016-05-19 | 2016-05-25
Gorkha | Swara | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Swara | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Sulikot Rato Matey Purna Nirman Samudaik Samiti
Gorkha | Swara | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 10 | 2016-05-12 | 2016-05-18
Gorkha | Swara | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Swara | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Bageshwori Purna Nirman Samudaik Samiti
Gorkha | Swara | 4 | HELVETAS | Janahit | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Swara | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2016-05-19 | 2016-05-25
Gorkha | Swara | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Swara | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Shimvu Purna Nirman Samudaik Samiti
Gorkha | Swara | 5 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Swara | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 14 | 2016-05-19 | 2016-05-25
Gorkha | Swara | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6
Gorkha | Swara | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Majh Gau Chitrey Purna Nirman Samudaik Samiti
Gorkha | Swara | 6 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Swara | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 3 | 2016-05-12 | 2016-05-18
Gorkha | Swara | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Swara | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Himali Samajh Purna Nirman Samudaik Samiti
Gorkha | Swara | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2016-05-12 | 2016-05-18
Gorkha | Swara | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Swara | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Manakamana Purna Nirman Samudaik Samiti
Gorkha | Swara | 8 | HELVETAS | Janahit | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Swara | 8 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 40 | 40 | 2016-12-01 | 2016-10-01
Gorkha | Swara | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 5 | 2016-05-12 | 2016-05-18
Gorkha | Swara | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Saat Kanya Devi Purna Nirman Samudaik Samiti
Gorkha | Swara | All | PAF | UNIFICATION-N | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Swara | All | HELVETAS | Janahit | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-06 | 2016-08-04
Gorkha | Swara | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 10 | 2016-06-06 | 2016-08-04
Gorkha | Swara |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 80
Gorkha | Taklung | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 59
Gorkha | Taklung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 90 | 2016-08-17 | 2016-08-18
Gorkha | Taklung | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 88
Gorkha | Taklung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Taklung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 63 | 2016-08-04 | 2016-08-05
Gorkha | Taklung | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 205 | 205
Gorkha | Taklung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Taklung | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 300 | 293 | 2016-08-17 | 2016-08-23
Gorkha | Taklung | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 184
Gorkha | Taklung | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 67 | 2016-08-10 | 2016-08-10
Gorkha | Taklung | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 245 | 245
Gorkha | Taklung | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 122 | 2016-08-11 | 2016-08-12
Gorkha | Taklung | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 165
Gorkha | Taklung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 115 | 2016-08-16 | 2016-08-17
Gorkha | Taklung | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 125
Gorkha | Taklung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Taklung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 61 | 2016-08-26 | 2016-08-26
Gorkha | Taklung | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 188
Gorkha | Taklung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Taklung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 77 | 2016-08-25 | 2016-08-25
Gorkha | Taklung | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 235 | 235
Gorkha | Taklung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 150 | 2016-08-31 | 2016-09-01
Gorkha | Taklung | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Taklung | All | PAF | LLCSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Taklung | All | OXFAM-GB | TMUC |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1241 | 0
Gorkha | Taklung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 171
Gorkha | Takukot | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 19 | 2016-04-28 | 2016-06-21
Gorkha | Takukot | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Takukot | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Ward no. 1 Purna Nirman Samudaik Samiti
Gorkha | Takukot | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 10 | 2016-04-28 | 2016-05-04
Gorkha | Takukot | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Takukot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Bhale Dhunga Purna Nirman Samudaik Samiti
Gorkha | Takukot | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 12 | 2016-04-28 | 2016-05-04
Gorkha | Takukot | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Takukot | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Ward no. 3 Purna Nirman Samudaik Samiti
Gorkha | Takukot | 3 | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees |  | Planned | 10 | 0
Gorkha | Takukot | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 4 | 2016-04-28 | 2016-05-04
Gorkha | Takukot | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Takukot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ward no. 4 Purna Nirman Samudaik Samiti
Gorkha | Takukot | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 14 | 2016-04-28 | 2016-05-04
Gorkha | Takukot | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Takukot | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Ward no. 5 Purna Nirman Samudaik Samiti
Gorkha | Takukot | 5 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Takukot | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 8 | 2016-04-28 | 2016-05-04
Gorkha | Takukot | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Takukot | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-29 | Bahakot Purna Nirman Samudaik Samiti
Gorkha | Takukot | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 10 | 2016-05-03 | 2016-06-21
Gorkha | Takukot | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Takukot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Bhohoriya Purna Nirman Samudaik Samiti
Gorkha | Takukot | 7 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Takukot | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 44 | 44 | 2016-05-03 | 2016-06-21
Gorkha | Takukot | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Takukot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Ward no. 8 Purna Nirman Samudaik Samiti
Gorkha | Takukot | 8 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Takukot | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2016-05-03 | 2016-06-21
Gorkha | Takukot | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4
Gorkha | Takukot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Ward no. 9 Purna Nirman Samudaik Samiti
Gorkha | Takukot | 9 | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-10-01
Gorkha | Takukot | 9 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 40 | 10 | 2016-12-01 | 2016-10-01
Gorkha | Takukot |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 80
Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 76
Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3
Gorkha | Takumajhalakuribot | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Takumajhalakuribot | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Ward no. 1 Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 1 | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-10-01
Gorkha | Takumajhalakuribot | 1 | HELVETAS | Sathi | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees |  | Planned | 10 | 0
Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Gorkha | Takumajhalakuribot | 2 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 76
Gorkha | Takumajhalakuribot | 2 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 2
Gorkha | Takumajhalakuribot | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Takumajhalakuribot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Ward no. 2 Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 3 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 57
Gorkha | Takumajhalakuribot | 3 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 2
Gorkha | Takumajhalakuribot | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Takumajhalakuribot | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Siran Lakuribot Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 4 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 60
Gorkha | Takumajhalakuribot | 4 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3
Gorkha | Takumajhalakuribot | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Takumajhalakuribot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-14 | Ward no. 4 Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 5 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 92
Gorkha | Takumajhalakuribot | 5 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3
Gorkha | Takumajhalakuribot | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Takumajhalakuribot | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Thale Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 6 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 81
Gorkha | Takumajhalakuribot | 6 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3
Gorkha | Takumajhalakuribot | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Takumajhalakuribot | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jal Kanya Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 6 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Takumajhalakuribot | 7 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 80
Gorkha | Takumajhalakuribot | 7 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 4
Gorkha | Takumajhalakuribot | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5
Gorkha | Takumajhalakuribot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Ward no. 7 Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 7 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Takumajhalakuribot | 8 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 72
Gorkha | Takumajhalakuribot | 8 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 4
Gorkha | Takumajhalakuribot | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Takumajhalakuribot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Ward no. 8 Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 9 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 89
Gorkha | Takumajhalakuribot | 9 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5
Gorkha | Takumajhalakuribot | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10
Gorkha | Takumajhalakuribot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Ward no. 9 Purna Nirman Samudaik Samiti
Gorkha | Takumajhalakuribot | 9 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 10 | 2015-12-01 | 2016-01-01
Gorkha | Takumajhalakuribot | All | OXFAM-GB | TMUC |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 638 | 0 |  |  | Info Center
Gorkha | Takumajhalakuribot | All | OXFAM-GB | TMUC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 60 | 30
Gorkha | Takumajhalakuribot | All | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-01-01
Gorkha | Takumajhalakuribot | All | HELVETAS | Sathi | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-01-01
Gorkha | Takumajhalakuribot |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78
Gorkha | Tandrang | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 2 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 173 | 0
Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 173 | 0
Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 173 | 0
Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-11-29 | 2017-02-07
Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 2 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 174 | 0
Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 174 | 0
Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 174 | 0
Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-12-31 | 2017-01-06
Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 2 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 51 | 0
Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 51 | 0
Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 51 | 0
Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-31 | 2017-01-06
Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 2 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 74 | 0
Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 74 | 0
Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 74 | 0
Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-31 | 2017-01-06
Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 58 | 0
Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 58 | 0
Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 58 | 0
Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-11-29 | 2016-12-05
Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 4 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 102 | 0
Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 102 | 0
Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 102 | 0
Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2016-11-29 | 2016-12-05
Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 136 | 0
Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 136 | 0
Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 136 | 0
Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-11-29 | 2016-12-05
Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 91 | 0
Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 91 | 0
Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 91 | 0
Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-11-29 | 2016-12-05
Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-08 | 2016-03-19
Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 134 | 0
Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 134 | 0
Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 134 | 0
Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31
Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Tandrang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 364
Gorkha | Tandrang |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-08 | 2016-03-19
Gorkha | Tanglichok | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Tanglichok | All | PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Tanglichok | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 62 | 62 | 2016-02-20 | 2016-02-24
Gorkha | Taple | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Bagh Bhairav Purna Nirman Samudaik Samiti
Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 165 | 0
Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 165 | 0
Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 165 | 0
Gorkha | Taple | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-28 | 2016-04-01
Gorkha | Taple | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-02-08 | 2016-03-14 | 30 days vocational training
Gorkha | Taple | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Shree Krishna Purna Nirman Samudaik Samiti
Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-06 | 2017-05-01
Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 121 | 0
Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 121 | 0
Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 121 | 0
Gorkha | Taple | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-03-28 | 2016-04-01
Gorkha | Taple | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 5 | 2016-02-08 | 2016-03-14 | 30 days vocational training
Gorkha | Taple | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 1 |  |  | Organized in Pandrung; People from Taple participated
Gorkha | Taple | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Gauir Shankar Purna Nirman Samudaik Samiti
Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 169 | 0
Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 169 | 0
Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 169 | 0
Gorkha | Taple | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-04-25 | 2016-04-29
Gorkha | Taple | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-02-08 | 2016-03-14 | 30 days vocational training
Gorkha | Taple | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  | Organized in Pandrung; People from Taple participated
Gorkha | Taple | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-09 | Aahaley Bhanjyan Purna Nirman Samudaik Samiti
Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 145 | 0
Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 145 | 0
Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 145 | 0
Gorkha | Taple | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-04-25 | 2016-04-29
Gorkha | Taple | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 9 | 2015-07-10 | 2015-08-08 | 30 days vocational training
Gorkha | Taple | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Manaslu Gau Purna Nirman Samiti
Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 174 | 0
Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 174 | 0
Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 174 | 0
Gorkha | Taple | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-02-29 | 2016-03-04
Gorkha | Taple | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-03-28 | 2016-05-01 | 30 days vocational training
Gorkha | Taple | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Mahadev Basti Gau Purna Nirman Samiti
Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 225 | 0
Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 225 | 0
Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 225 | 0
Gorkha | Taple | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-02-29 | 2016-03-04
Gorkha | Taple | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-03-28 | 2016-05-01 | 30 days vocational training
Gorkha | Taple | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-04 | Shiva Aakala Purna Nirman Samudaik Samiti
Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 135 | 0
Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 135 | 0
Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 135 | 0
Gorkha | Taple | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2016-02-29 | 2016-03-04
Gorkha | Taple | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-03-28 | 2016-05-01 | 30 days vocational training
Gorkha | Taple | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-05 | Taplekot Purna Nirman Samudaik Samiti
Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-01-12 | 2017-03-12
Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 138 | 0
Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 138 | 0
Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 138 | 36 | 2016-02-19 | 2016-02-19
Gorkha | Taple | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-01-25 | 2016-01-29
Gorkha | Taple | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-03-28 | 2016-03-03 | 30 days vocational training
Gorkha | Taple | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-03 | Shiva Parbati Purna Nirman Samudaik Samiti
Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Taple | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0
Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 151 | 0
Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 151 | 0
Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 151 | 98 | 2016-02-19 | 2016-02-21
Gorkha | Taple | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-01-25 | 2016-01-29
Gorkha | Taple | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-03-28 | 2016-03-03 | 30 days vocational training
Gorkha | Taple | 4,8,9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Sirdibas Gau Purna Nirman Samiti
Gorkha | Taple |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 85
Gorkha | Taple |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0
Gorkha | Thalajung | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Thalajung | All | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-01-18 | 2016-03-31
Gorkha | Thalajung | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-13 | 2016-05-19
Gorkha | Thalajung | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-30 | 2016-06-05
Gorkha | Thalajung | All | NRCS | NRCS | B-GRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-07 | 2016-06-13
Gorkha | Thalajung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 51
Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 83 | 0
Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 83 | 0
Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 83 | 0
Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2016-12-11 | 2016-12-17
Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 59 | 59 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save
Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Planned | 59 | 0
Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-25 | mason training done with partner with CARE-N dhadhing.
Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 94 | 0
Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 94 | 0
Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 94 | 0
Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-12-11 | 2016-12-17
Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 131 | 0
Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 131 | 0
Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 131 | 0
Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-12-11 | 2016-12-17
Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 95 | 0
Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 95 | 0
Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 95 | 0
Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-01 | 2017-02-07
Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 241 | 0
Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 241 | 0
Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 241 | 0
Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-12-27 | 2017-01-02
Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-01-11 | 2017-03-11
Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 206 | 0
Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 206 | 0
Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 206 | 0
Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-12-27 | 2017-01-02
Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 115 | 0
Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 115 | 0
Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 115 | 0
Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-12-27 | 2017-01-02
Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 112 | 0
Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 112 | 0
Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 112 | 0
Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 4 | 2017-02-01 | 2017-02-07
Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 118 | 0
Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 118 | 0
Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 118 | 0
Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 5 | 2017-02-01 | 2017-02-07
Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Gorkha | Thumi |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 91
Gorkha | Uhya | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 69 | 69 | 2016-06-15 | 2016-09-14
Gorkha | Uhya | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-08 | 2016-06-14
Gorkha | Uhya | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 91 | 91 | 2016-06-15 | 2016-07-31
Gorkha | Uhya | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 95 | 95 | 2016-06-15 | 2016-07-31
Gorkha | Uhya | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-08 | 2016-06-14
Gorkha | Uhya | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 20 | 20 | 2016-06-15 | 2016-09-06
Gorkha | Uhya | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Ongoing | 1 | 0
Gorkha | Uhya | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-06-15 | 2016-09-07
Gorkha | Uhya | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-08 | 2016-06-14
Gorkha | Uhya | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 18 | 18 | 2016-09-09 | 2016-09-09
Gorkha | Uhya | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-08 | 2016-06-14
Gorkha | Uhya | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-09-09 | 2016-09-09
Gorkha | Uhya | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 28 | 28 | 2016-09-11 | 2016-09-11
Gorkha | Uhya | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-08 | 2016-06-14
Gorkha | Uhya | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-09-13 | 2016-09-13
Gorkha | Uhya | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-06-08 | 2016-06-14
Gorkha | Uhya | All | PAF | HADC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0
Gorkha | Uhya | ALL | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 330 | 11 | 2016-11-01
Gorkha | Uhya |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 1 | 0 |  |  | Flagged as 1 to show the area has plans
Gorkha | Warpak | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6
Gorkha | Warpak | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Barpak-1, Pokhare CBRC
Gorkha | Warpak | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 70 | 70 | 2016-06-25 | 2016-07-21
Gorkha | Warpak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Warpak | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Barpak-2, Rangrung CBRC
Gorkha | Warpak | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Barpak-2, Mandrey CBRC
Gorkha | Warpak | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 117 | 117 | 2016-07-22 | 2016-07-27
Gorkha | Warpak | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1
Gorkha | Warpak | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Barpak-3, Allghau CBRC
Gorkha | Warpak | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Barpak-3, Thamsuk CBRC
Gorkha | Warpak | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 51 | 51 | 2016-07-23 | 2016-07-23
Gorkha | Warpak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9
Gorkha | Warpak | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Barpak-4 Sorda CBRC
Gorkha | Warpak | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Barpak-4 CBRC
Gorkha | Warpak | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 85 | 85 | 2016-06-25 | 2016-07-28
Gorkha | Warpak | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Warpak | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Barpak 5 CBRC
Gorkha | Warpak | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 14 | 14 | 2016-06-25 | 2016-07-24
Gorkha | Warpak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Barpak 6 CBRC
Gorkha | Warpak | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 44 | 2016-06-25 | 2016-07-24
Gorkha | Warpak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7
Gorkha | Warpak | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 101 | 101 | 2016-06-25 | 2016-07-26
Gorkha | Warpak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Gorkha | Warpak | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Barpak 8 CBRC
Gorkha | Warpak | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-06-25 | 2016-06-25
Gorkha | Warpak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3
Gorkha | Warpak | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Barpak 9 CBRC
Gorkha | Warpak | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Gorkha | Warpak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 52 | 52 | 2016-06-25 | 2016-07-25
Gorkha | Warpak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24
Gorkha | Warpak | 1,2,3 | NRCS | NRCS | B-GRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 3 | 3 | 2016-10-01 | 2016-11-25
Gorkha | Warpak | All | PIN | UNIFICATION-N | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-10-25 | 2016-10-26
Gorkha | Warpak | All | PIN | UNIFICATION-N | ECHO | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 407 | 407 | 2016-09-01 | 2016-11-01
Gorkha | Warpak | ALL | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1248 | 72 | 2016-11-01
Gorkha | Warpak |  | JICA | TPIS-ERP |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1380 | 0
Gorkha | Warpak |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160
Kathmandu | Chandragiri N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 1 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 4 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 2 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 4 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 43 | 2016-08-15 | 2016-08-15
Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 3 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 4 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 4 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 4 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 8 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08
Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Chandragiri N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 5 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 4 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 2 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 6 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 2 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 7 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 31 | 2016-12-15 | 2016-12-15
Kathmandu | Chandragiri N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 39 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 8 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 17 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 9 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 36 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 10 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 11 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 12 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | Support - Integrated reclustering of urban settlements |  | Yes | Planned | 38 | 0 | 2016-03-01 | 2016-11-01 | Land Consolidation and Readjustment Planning in Taukhel where 38 households will be benefited
Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | 7 houses under construction | # of households | Yes | Ongoing | 69 | 0
Kathmandu | Chandragiri N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31
Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 7 houses under construction | # of households | Yes | Ongoing | 69 | 0 | 2016-07-01
Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | 2 houses under construction | # of households | Yes | Ongoing | 46 | 0
Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 2 houses under construction | # of households | Yes | Ongoing | 46 | 0 | 2016-07-01
Kathmandu | Chandragiri N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 61 | 2016-10-20 | 2016-10-20
Kathmandu | Chandragiri N.P. | 15 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Chandragiri N.P. | 16 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 16 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Chandragiri N.P. | 17 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 18 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information center at municipality office | # of households supported | Yes | Ongoing | 200 | 0 | 2016-12-25 | 2017-03-31
Kathmandu | Chandragiri N.P. | 18 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 25 | 2016-11-24 | 2016-11-24
Kathmandu | Chandragiri N.P. | 19 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08
Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Chandragiri N.P. | 20 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 20 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 21 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 21 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Chandragiri N.P. | 22 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 22 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-25 | 2016-12-31
Kathmandu | Chandragiri N.P. | 23 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 24 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Chandragiri N.P. | 25 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 2 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Kathmandu | Daxinkali N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Daxinkali N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Daxinkali N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Daxinkali N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Daxinkali N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Daxinkali N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Kageshwori Manahara N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 3200 | 49 | 2015-10-01 | 2020-09-30
Kathmandu | Kageshwori Manahara N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 3200 | 63 | 2015-10-01 | 2020-09-30
Kathmandu | Kageshwori Manahara N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 30 | 2015-10-01 | 2020-09-30
Kathmandu | Kageshwori Manahara N.P. | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 30 | 2015-10-01 | 2020-09-30
Kathmandu | Kageshwori Manahara N.P. | 14 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 3200 | 52 | 2015-10-01 | 2020-09-30
Kathmandu | Kathmandu M.N.P. | 11 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 204 | 210 | 2015-10-01 | 2020-09-30
Kathmandu | Kathmandu M.N.P. | 17 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Kathmandu M.N.P. | 17 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-11-28 | 2016-12-07
Kathmandu | Kathmandu M.N.P. | 17 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 26 | 2016-08-07 | 2016-08-13
Kathmandu | Kathmandu M.N.P. | 17 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-28 | 2016-08-03
Kathmandu | Kathmandu M.N.P. | 35 | NSET | NSET | USAID | Training | Other trainings | Local Authority Training |  | # of trainees | Yes | Completed | 2563 | 2563 | 2015-10-01 | 2020-09-30
Kathmandu | Kirtipur N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Kirtipur N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Kirtipur N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Kirtipur N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Kirtipur N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Kirtipur N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04
Kathmandu | Kirtipur N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Nagarjun N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 7 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 19 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 31 | 2016-10-15 | 2016-10-15
Kathmandu | Nagarjun N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 56 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 22 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Nagarjun N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 44 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 69 | 2016-08-25 | 2016-09-25
Kathmandu | Nagarjun N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Kathmandu | Nagarjun N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Kathmandu | Nagarjun N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 26 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2016-02-28 | 2016-03-04
Kathmandu | Nagarjun N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 27 | 2016-12-20 | 2017-03-31
Kathmandu | Nagarjun N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2016-02-28 | 2016-03-04
Kathmandu | Nagarjun N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 29 | 2016-09-15 | 2016-09-15
Kathmandu | Nagarjun N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-05-25 | 2016-05-31
Kathmandu | Nagarjun N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04
Kathmandu | Shankarapur N.P. | 8 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Shankarapur N.P. | 8 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-10 | 2016-12-17
Kathmandu | Shankarapur N.P. | 8 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-06 | 2016-11-09 | it is about repair and rehab of water supply system
Kathmandu | Shankarapur N.P. | 9 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Shankarapur N.P. | 9 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-20 | 2016-12-28
Kathmandu | Shankarapur N.P. | 10 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Shankarapur N.P. | 10 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-20 | 2016-12-28
Kathmandu | Shankarapur N.P. | 10 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-06 | 2016-11-09 | it is about repair and rehab of water supply system
Kathmandu | Shankarapur N.P. | 11 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Shankarapur N.P. | 11 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-10 | 2016-12-17
Kathmandu | Shankarapur N.P. | 8, 9, 10 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 18 | 2016-08-26 | 2016-09-01 | In Sankharapur, two training was planned. One of the training shifted to tarkeshwor municipality
Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-10 | 2016-12-27
Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-06 | 2016-11-08 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Planned | 164 | 0 | 2016-11-11 | 2016-11-30
Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-10 | 2016-12-27
Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about debris clearance work |  | Yes | Planned | 164 | 0 | 2016-11-11 | 2016-11-30
Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-09 | 2016-11-12 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 3 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 3 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-10 | 2016-12-27
Kathmandu | Tarakeshwor N.P. | 7 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 7 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-11-30 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 7 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-12 | 2016-11-15 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 8 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 8 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-11-30 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 8 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-08 | 2016-11-09 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 12 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 12 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-12-28 | 2017-01-05
Kathmandu | Tarakeshwor N.P. | 12 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-26 | 2016-11-28 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 13 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 13 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | it is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-01-06 | 2016-01-10
Kathmandu | Tarakeshwor N.P. | 13 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-15 | 2016-11-18 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 14 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 14 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Planned | 164 | 0 | 2016-01-06 | 2016-01-10
Kathmandu | Tarakeshwor N.P. | 14 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-19 | 2016-11-21 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 15 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | First Aid training |  | Yes | Planned | 1 | 0 | 2016-11-27 | 2016-12-07
Kathmandu | Tarakeshwor N.P. | 15 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | It is about conditional cash grant (livelihood programme) |  | Yes | Ongoing | 164 | 104 | 2016-11-25 | 2016-12-05
Kathmandu | Tarakeshwor N.P. | 15 | NRCS | NRCS | BRC | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 1 | 0 | 2016-11-22 | 2016-11-25 | it is about repair and rehab of water supply system
Kathmandu | Tarakeshwor N.P. | 1,2,3 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-08-11 | 2016-08-17
Kathmandu | Tarakeshwor N.P. | 13, 14 15 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-29 | 2016-08-04
Kathmandu | Tarakeshwor N.P. | 13, 14, 15 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-19 | 2016-07-25
Kathmandu | Tarakeshwor N.P. | 7, 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-08-07 | 2016-08-13
Kathmandu | Tarakeshwor N.P. |  | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 10 | 10 | 2016-07-15 | 2016-07-19
Kathmandu | Tarakeshwor N.P. |  | NRCS | NRCS | BRC | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-15 | 2016-07-19
Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 55 | 55 | 2016-12-05
Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 55 | 3 | 2016-10-01
Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 61 | 0
Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 2 | 2016-09-08 | 2016-09-08 | Tole level re construction group formation
Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 55 | 55 | 2016-09-20 | 2016-09-20 | In NRA list there are 61 HH, 55 HH made agreement with NRA
Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 18 | 30 | 2016-11-15
Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 18 | 6 | 2016-10-01
Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 19 | 26 | 2016-12-17
Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 2 | 2016-09-08 | 2016-09-08
Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 18 | 18 | 2016-09-20 | 2016-09-20 | In NRA list there are 19 HH, 18 HH made agreement with NRA
Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 34 | 21 | 2016-12-08
Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 34 | 2 | 2016-10-01
Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 34 | 5
Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 2 | 2016-09-09 | 2016-09-09
Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 34 | 34 | 2016-09-20 | 2016-09-29 | In NRA list there are 34 HH
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 53 | 43 | 2016-12-07
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 53 | 5 | 2016-10-01
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-08-23 | Handover complete formally
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 53 | 0
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-09 | 2016-09-09
Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 53 | 52 | 2016-09-20 | 2016-09-29 | In NRA list there are 53 HH, One Demo house has been supported.
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 155 | 116 | 2016-12-18
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Nepane Water system repair and maintenance, ward no 5 | # of households | Yes | Ongoing | 157 | 157 | 2016-11-09
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 155 | 23 | 2016-10-01
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 169 | 0
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 6 | 2016-09-15 | 2016-09-15
Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 155 | 155 | 2016-09-20 | 2016-09-29 | In NRA list there are 169 HH, 155 HH made agreement with NRA
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) |  | Yes | Ongoing | 2 | 2 | 2016-12-07
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 61 | 45 | 2016-12-06
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Dada gaun Water system repair and maintenance, ward no 6 | # of households | Yes | Ongoing | 70 | 70 | 2016-12-21
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 61 | 11 | 2016-10-01
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 67 | 25 | 2016-12-17
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-07 | 2016-09-07
Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 62 | 62 | 2016-09-20 | 2017-02-23 | In NRA list there are 67 HH, 61 HH made agreement with NRA
Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 29 | 17 | 2016-12-13
Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 29 | 2 | 2016-10-01
Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 29 | 0
Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 2 | 2016-09-13 | 2016-09-13
Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 29 | 29 | 2016-09-20 | 2016-09-29 | In NRA list there are 29 HH
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) |  | Yes | Ongoing | 2 | 2 | 2016-12-07
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 17 | 17 | 2016-11-14
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 17 | 3 | 2016-10-01
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 1 | 2016-07-08
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 17 | 0
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 2 | 2016-09-13 | 2016-09-13
Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 17 | 16 | 2016-09-20 | 2016-09-29 | In NRA list there are 17 HH, One Demo house has been supported.
Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 54 | 57 | 2016-12-01
Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 54 | 10 | 2016-10-01
Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 58 | 0
Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-11 | 2016-07-12
Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-14
Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 54 | 54 | 2016-09-20 | 2016-09-29 | In NRA list there are 58 HH, 54 HH made agreement with NRA
Kavrepalanchok | Baldthali |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) |  | Yes | Ongoing | 507 | 473 | 2016-06-29 | 2016-09-25 | Ward wise support is not tracked
Kavrepalanchok | Baldthali |  | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | One unit plan | # of households | Yes | Planned | 50 | 0
Kavrepalanchok | Baldthali |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One VDC Level Committee | # of committees | Yes | Completed | 1 | 1 | 2016-12-14 | 2016-12-14
Kavrepalanchok | Balting | 1 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 1 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 2 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 2 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Balting | 3 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 3 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Balting | 4 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 | In a combine training 11 mason from Balting
Kavrepalanchok | Balting | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-03 | 2016-06-09 | In two group at same venue, same date 17 mason from Balting
Kavrepalanchok | Balting | 4 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 5 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Balting | 5 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 6 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Balting | 6 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 7 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Balting | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Balting | 7 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 8 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 8 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Balting | 9 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Balting | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Balting | 9 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 23 | 16 | 2016-11-10 | 2017-03-15 | 6 lintel band, 2 sill band, 8 plinth level completed
Kavrepalanchok | BaluwapatiDeupur | 1 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-04-18 | 2016-04-24
Kavrepalanchok | BaluwapatiDeupur | 1 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 2 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 20 | 0 | 2017-01-10 | 2017-03-15 | 2 lintel, 6 sill band completed
Kavrepalanchok | BaluwapatiDeupur | 2 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-18 | 2016-04-24
Kavrepalanchok | BaluwapatiDeupur | 2 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 14 | 0 | 2017-03-10 | 2017-05-15
Kavrepalanchok | BaluwapatiDeupur | 3 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 3 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-17 | 2016-08-21
Kavrepalanchok | BaluwapatiDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 7 | 3 | 2017-03-10 | 2017-05-15 | 3 foundation started
Kavrepalanchok | BaluwapatiDeupur | 4 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-04-18 | 2016-04-24
Kavrepalanchok | BaluwapatiDeupur | 4 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 5 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 5 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-18 | 2016-04-24
Kavrepalanchok | BaluwapatiDeupur | 5 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 14 | 8 | 2017-05-10 | 2017-07-15
Kavrepalanchok | BaluwapatiDeupur | 6 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-18 | 2016-04-24
Kavrepalanchok | BaluwapatiDeupur | 6 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 7 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 7 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 8 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-04-24
Kavrepalanchok | BaluwapatiDeupur | 8 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BaluwapatiDeupur | 9 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BaluwapatiDeupur | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18 | Total 36 masons were trained in this (13-18 Feb 2016) training, in which 11 masons from other district
Kavrepalanchok | BaluwapatiDeupur | 9 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 1 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 1 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 2 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 2 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 3 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 3 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-06 | 2016-08-12
Kavrepalanchok | BanakhuChor | 4 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 4 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-06 | 2016-08-12
Kavrepalanchok | BanakhuChor | 5 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 5 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12
Kavrepalanchok | BanakhuChor | 6 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 6 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-06 | 2016-08-12
Kavrepalanchok | BanakhuChor | 7 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 7 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12
Kavrepalanchok | BanakhuChor | 8 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 8 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12
Kavrepalanchok | BanakhuChor | 9 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BanakhuChor | 9 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BanakhuChor | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 8 | 8 | 2016-07-06 | 2016-08-12
Kavrepalanchok | Banepa N.P. | 3 | CL | CL | VG | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT Short training | # of trainees | Yes | Completed | 18 | 18 | 2016-08-15 | 2016-10-12 | Was funded as part of Corporate CSR activity - Centum didn't report to any local authorities
Kavrepalanchok | Banepa N.P. | 6 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Banepa N.P. | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Banepa N.P. | 10 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Banepa N.P. | All | NRCS | NRCS | DRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 30 | 30 | 2016-08-10 | 2016-08-13
kavrepalanchok | Banepa N.P. | All | NRCS | NRCS | DRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 30 | 30 | 2016-09-08 | 2016-09-11
Kavrepalanchok | Banepa N.P. |  | NRCS | NRCS | DRC | Training | Short training | Social mobilizer | DUDBC | # of trainees | Yes | Completed | 30 | 30 | 2016-08-10 | 2016-08-13
Kavrepalanchok | BekhsimleDhartigaun | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | BekhsimleDhartigaun | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | BekhsimleDhartigaun | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 1 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 | In a combine training 17 mason from Bhimkhori
Kavrepalanchok | Bhimkhori | 1 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 2 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-20 | 2016-05-26 | In a combine training on this date 30 mason from Bhimkhori
Kavrepalanchok | Bhimkhori | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Bhimkhori | 2 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 3 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 | In two group at same venue, same date 31 mason from Bhimkhori
Kavrepalanchok | Bhimkhori | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-20 | 2016-05-26
Kavrepalanchok | Bhimkhori | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Bhimkhori | 3 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 4 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Bhimkhori | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Bhimkhori | 4 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 5 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 5 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 6 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-20 | 2016-05-26
Kavrepalanchok | Bhimkhori | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Bhimkhori | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Bhimkhori | 6 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 7 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-20 | 2016-05-26
Kavrepalanchok | Bhimkhori | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Bhimkhori | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Bhimkhori | 7 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 8 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Bhimkhori | 8 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhimkhori | 9 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhimkhori | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-27 | 2016-06-02
Kavrepalanchok | Bhimkhori | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Bhimkhori | 9 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 1 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-11-02 | 2015-11-06 | MToT training, Implementing Partner:- Nangshal Association
Kavrepalanchok | Bhumlutar | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 2 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 2 | 2 | 2015-11-02 | 2015-11-06
Kavrepalanchok | Bhumlutar | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 3 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2015-11-02 | 2015-11-06
Kavrepalanchok | Bhumlutar | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 4 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | Bhumlutar | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 5 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 11 | 11 | 2015-11-02 | 2015-11-06
Kavrepalanchok | Bhumlutar | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 7 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | Bhumlutar | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 8 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2015-11-02 | 2015-11-06
Kavrepalanchok | Bhumlutar | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Bhumlutar | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Bhumlutar | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Birtadeurali | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-06 | 2016-08-13
kavrepalanchok | Birtadeurali | 7 | NYF | NYF | NYF-US | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 25 | 20 | 2016-04-14 | 2016-04-20 | The tools distributed in the community for common use to Social leader and Chairperson of Bachheshwor Primary School in Birta Deurali VDC.
Kavrepalanchok | Birtadeurali | 7 | NYF | NYF | NYF-US | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-04-15 | 2016-05-15 | Lead Engineer
Kavrepalanchok | Birtadeurali | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 26 | 20 | 2016-04-14 | 2016-04-20 | Reconstruction Manager
Kavrepalanchok | BoldeFediche | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-28 | 2016-04-03
Kavrepalanchok | BoldeFediche | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03
Kavrepalanchok | BoldeFediche | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-28 | 2016-04-03
Kavrepalanchok | BoldeFediche | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-28 | 2016-04-03
Kavrepalanchok | BoldeFediche | 9 | NYF | NYF | NYF-US | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 25 | 24 | 2016-05-20 | 2016-05-20 | The tools distributed in the community for common use to Bolde Vikash Samaj in Bolde Fediche VDC kavre
Kavrepalanchok | BoldeFediche | 9 | NYF | NYF | NYF-US | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-05-05
Kavrepalanchok | BoldeFediche | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Budhakhani | 1 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 1 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 2 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 2 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 3 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 3 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Budhakhani | 4 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 4 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 5 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 5 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 6 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 6 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 7 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Budhakhani | 7 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 8 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 8 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Budhakhani | 9 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Budhakhani | 9 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | ChalalGaneshsthan | 1 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 1 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-07 | 2016-05-13
Kavrepalanchok | ChalalGaneshsthan | 2 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 3 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 4 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 5 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 6 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 7 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 8 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChalalGaneshsthan | 9 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-12 | 2016-09-18
Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 166 | 131 | 2016-10-19
Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 166 | 24 | 2016-10-01
Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 168 | 20 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 6 | 2016-09-24 | 2016-09-24 | Tole level re construction group formation
Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 166 | 166 | 2016-09-20 | 2016-09-20 | In NRA list there are 168 HH, 166 HH made agreement with NRA
Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 77 | 77 | 2016-11-13
Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 77 | 6 | 2016-10-01
Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 81 | 31 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 4 | 4 | 2016-09-21 | 2016-09-21
Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 79 | 79 | 2016-09-20 | 2017-02-23 | In NRA list there are 81 HH, 77 HH made agreement with NRA
Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 59 | 50 | 2016-11-17
Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 59 | 1
Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 62 | 21 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-24 | 2016-09-24
Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 62 | 62 | 2016-09-20 | 2017-02-23 | In NRA list there are 62 HH, 59 HH made agreement with NRA
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 117 | 96 | 2016-11-17
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Himjyoti water system repair and maintenance, ward no 4 | # of households | Yes | Ongoing | 40 | 40
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 117 | 12 | 2016-10-01
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 126 | 28 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 5 | 5 | 2016-09-28 | 2016-09-28
Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 121 | 121 | 2016-09-20 | 2017-02-23 | In NRA list there are 126 HH, 117 HH made agreement with NRA
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) |  | Yes | Ongoing | 15 | 15 | 2016-11-19
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 149 | 36 | 2016-11-13
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Jogitar waster system repair and maintenance, ward no 5 | # of households | Yes | Completed | 115 | 115 | 2016-09-15 | 2016-10-15
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Planned | 45 | 0
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 149 | 47 | 2016-10-01
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-25
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 157 | 11 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 6 | 2016-11-08 | 2016-11-08
Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 149 | 148 | 2016-09-20 | 2016-09-20 | In NRA list there are 157 HH, 149 HH made agreement with NRA, One Demo house has been supported.
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 136 | 69 | 2016-11-14
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Planned | 49 | 0
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 136 | 11 | 2016-10-01
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 142 | 32 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 6 | 2016-11-07 | 2016-11-07
Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 136 | 136 | 2016-09-20 | 2016-09-20 | In NRA list there are 142 HH, 136 HH made agreement with NRA
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 54 | 55 | 2016-11-23
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Planned | 54 | 0
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Planned | 54 | 0
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 61 | 31 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-27 | 2016-09-27
Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 54 | 54 | 2016-09-20 | 2016-10-25 | In NRA list there are 61 HH, 54 HH made agreement with NRA
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 102 | 93 | 2016-11-18
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Planned | 200 | 0 |  |  | 200 HH of ward no 8,6,7,5, 9 and 1,4,5 Upper part
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 102 | 1
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2016-09-23
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 107 | 32 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 5 | 5 | 2016-11-07 | 2016-11-07
Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 102 | 102 | 2016-09-20 | 2017-02-23 | In NRA list there are 107 HH, 101 HH made agreement with NRA, One Demo house has been supported
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) |  | Yes | Ongoing | 9 | 9 | 2016-11-19
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 80 | 80 | 2016-11-14
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 80 | 24 | 2016-10-01
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 80 | 32 | 2016-09-22
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-19 | 2016-08-27
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-08
Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 80 | 80 | 2016-09-20 | 2016-10-25 | In NRA list there are 80 HH,
Kavrepalanchok | ChandeniMandan |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) |  | Yes | Ongoing | 984 | 935 | 2016-06-21 | 2016-10-10 | Ward wise support is not tracked
Kavrepalanchok | ChandeniMandan |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One VDC Level Committee | # of committees | Yes | Completed | 1 | 1 | 2016-11-15 | 2016-11-15
Kavrepalanchok | Choubas | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Choubas | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Choubas | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 1 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 1 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 1 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 2 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 2 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 2 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 3 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 3 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 3 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 4 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 4 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 4 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 5 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 5 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 5 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 6 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 6 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 6 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 7 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 7 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 7 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 8 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 8 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 8 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Chyamrangbesi | 9 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Chyamrangbesi | 9 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Chyamrangbesi | 9 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | ChyasingKharka | 1 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-14 | 2016-09-20
Kavrepalanchok | ChyasingKharka | 2 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-14 | 2016-09-20
Kavrepalanchok | ChyasingKharka | 3 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-14 | 2016-09-20
Kavrepalanchok | ChyasingKharka | 4 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Kavrepalanchok | ChyasingKharka | 5 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Kavrepalanchok | ChyasingKharka | 6 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Kavrepalanchok | ChyasingKharka | 7 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Kavrepalanchok | Dandagaun | 1 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 1 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 2 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 2 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 3 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 3 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 4 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 4 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 5 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 5 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-06 | 2016-08-07
Kavrepalanchok | Dandagaun | 6 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 6 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 7 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 7 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 8 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 8 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dandagaun | 9 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Dandagaun | 9 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 25 | 25 | 2016-09-07 | 2016-09-13 | Previous Methinkot vdc - Our plan is to conduct 8 mason training and 25 mason in each training
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-08-17 | 2016-12-31 | Previous Methinkot vdc - 1 model houses per 3 mason training
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2016-09-07 | 2016-09-13 | Previous Methinkot vdc - Our plan is to conduct 8 mason training and 25 mason in each training
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-26 | 2016-07-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 53 | 12 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Completed | 1 | 1 | 2016-10-20 | 2016-12-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 31 | 31 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 33 | 33 | 2016-09-21 | 2016-09-27
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-07-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 30 | 2 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 4 | 0 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-14 | 2017-02-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 42 | 42 | 2016-11-02
Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 25 | 0 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 13 | 13 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 29 | 0 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-08-17 | 2016-12-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 17 | 10 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 16 | 16 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 10 | 0 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Completed | 1 | 1 | 2016-10-20 | 2016-12-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2016-08-17 | 2016-12-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-10-19 | 2016-10-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 53 | 23 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 57 | 57 | 2016-11-15 | 2016-11-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 69 | 69 | 2016-11-15 | 2016-11-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-26 | 2016-07-25
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 42 | 42 | 2016-12-07
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 35 | 0 | 2016-06-05
Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Planned | 1 | 1 | 2016-02-07
Kavrepalanchok | Dapcha Kashikhand N.P. | 10 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 10 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 10 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Dapcha Kashikhand N.P. | 11 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 12 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 12 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-13
Kavrepalanchok | Dapcha Kashikhand N.P. | 13 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 13 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 14 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 14 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21
Kavrepalanchok | Dapcha Kashikhand N.P. | 14 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Dapcha Kashikhand N.P. | 15 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok
Kavrepalanchok | Dapcha Kashikhand N.P. | 1,2 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 36 | 36 | 2016-07-13 |  | Ward wise data is not received
Kavrepalanchok | Dapcha Kashikhand N.P. | 5,6 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 47 | 47 | 2016-08-17 |  | Ward wise data is not received
Kavrepalanchok | Dapcha Kashikhand N.P. | 7,6 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-09-14 |  | Ward wise data is not received
Kavrepalanchok | Dapcha Kashikhand N.P. | 8,3 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-08-10 |  | Ward wise data is not received
Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Others | Others | (Please specify in Activity Detail) | Previous Methainkot vdc - 1 training for water user committie |  | Yes | Planned | 1 | 0 | 2016-05-01 | 2016-12-31
Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Others | Others | (Please specify in Activity Detail) | Prrvious Methainkot vdc- 1 sign bord with Built Back Safer ( 10 Key Messaged) in each 9 wards |  | Yes | Planned | 8 | 0 | 2016-05-01 | 2016-12-31
Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Planned | 1 | 0 | 2016-05-01 | 2016-12-31 | Detail data yet to come (Previous Methinkot vdc - Rehabilitation of community water supply system - 1 community water supply system in Methinkot VDC)
Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 51 | 0 | 2016-11-15 | 2016-11-21
Kavrepalanchok | Devitar | 1 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 1 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 15 | 15 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 2 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 2 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 3 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 3 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 4 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 4 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 5 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 5 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 6 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 6 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 7 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 7 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 8 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 8 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Devitar | 9 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Devitar | 9 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Devitar | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-14 | 2016-08-14
Kavrepalanchok | Dhulikhel N.P. | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | ToT | Engineers, sub engineers (7 days DUDBC) | Two Event, total 45 Engineer ( 40 Engineer from DUDBC and 5 from Caritas(2 ChandeniMandan+3Baldthali)) | # of trainees | Yes | Completed | 45 | 45 | 2016-10-15 | 2016-11-14 | Venue is Dhulikhel
Kavrepalanchok | Dhunkharka | 1 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 129 | 129 | 2016-03-24 | 2016-03-24
Kavrepalanchok | Dhunkharka | 1 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Dhunkharka | 2 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 341 | 341 | 2016-03-23 | 2016-03-24
Kavrepalanchok | Dhunkharka | 4 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 204 | 204 | 2016-03-26 | 2016-03-26
Kavrepalanchok | Dhunkharka | 4 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Dhunkharka | 6 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 142 | 142 | 2016-03-25 | 2016-03-25
Kavrepalanchok | Dhunkharka | 6 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Dhunkharka | 7 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 111 | 111 | 2016-03-24 | 2016-03-24
Kavrepalanchok | Dhunkharka | 7 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW | BC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 |  |  | 3 Technical resource center
Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW | BC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-05-24 | 2016-08-12 | Community building
Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 326 | 326 | 2016-03-25 | 2016-03-25
Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Dhunkharka | 9 | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 180 | 180 | 2016-03-26 | 2016-03-26
Kavrepalanchok | Dhunkharka | 9 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Dhunkharka |  | BC | ARSOW | BC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2017-03-01 |  | Ward not fixed yet (planned for March 2017)
Kavrepalanchok | Dolalghat | All | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-29 | 2016-07-04
Kavrepalanchok | Falatebhumlu | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falatebhumlu | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falatebhumlu | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 1 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 1 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 2 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 2 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 3 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 3 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 4 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 4 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 5 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 5 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 6 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 6 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 7 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 7 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 8 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 8 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Falemetar | 9 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Falemetar | 9 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 1 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 1 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 2 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 2 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 3 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 3 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-06 | 2016-08-07
Kavrepalanchok | Foksingtar | 4 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 4 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-06 | 2016-08-13
Kavrepalanchok | Foksingtar | 5 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 5 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-06 | 2016-08-13
Kavrepalanchok | Foksingtar | 6 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 6 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 7 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 7 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 8 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 8 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Foksingtar | 9 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Foksingtar | 9 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 1 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-17 | 2016-03-23
Kavrepalanchok | GairiBisounaDeupur | 1 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-17 | 2016-08-21
Kavrepalanchok | GairiBisounaDeupur | 2 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-17 | 2016-03-23
Kavrepalanchok | GairiBisounaDeupur | 2 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 68 | 45 | 2016-08-20 | 2017-04-15 | 8 completed, 26 roof, 4 lintel,7 plinth level completed
Kavrepalanchok | GairiBisounaDeupur | 3 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 3 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-03-17 | 2016-03-23
Kavrepalanchok | GairiBisounaDeupur | 3 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-17 | 2016-08-21
Kavrepalanchok | GairiBisounaDeupur | 4 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-17 | 2016-03-23
Kavrepalanchok | GairiBisounaDeupur | 4 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-17 | 2016-08-21
Kavrepalanchok | GairiBisounaDeupur | 5 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 5 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 29 | 29 | 2015-10-03 | 2015-10-07 | MToT training, Implementing Partner:- Nangshal Association
Kavrepalanchok | GairiBisounaDeupur | 5 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 6 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-17 | 2016-03-23
Kavrepalanchok | GairiBisounaDeupur | 6 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 4 | 0 | 2017-04-15 | 2017-06-15
Kavrepalanchok | GairiBisounaDeupur | 7 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-17 | 2016-03-23
Kavrepalanchok | GairiBisounaDeupur | 7 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-17 | 2016-08-21
Kavrepalanchok | GairiBisounaDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 9 | 0 | 2017-04-15 | 2017-06-15
Kavrepalanchok | GairiBisounaDeupur | 8 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 8 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | GairiBisounaDeupur | 9 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 1 | 0 | 2017-04-15 | 2017-06-15
Kavrepalanchok | GairiBisounaDeupur | 9 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | GairiBisounaDeupur | 9 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 1 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 1 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 8 | 8 | 2016-06-26 | 2016-08-07
Kavrepalanchok | Ghartichhap | 2 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 2 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-26 | 2016-08-07
Kavrepalanchok | Ghartichhap | 3 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 3 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-07-25
Kavrepalanchok | Ghartichhap | 4 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 4 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 5 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 5 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-16 | 2016-08-07
Kavrepalanchok | Ghartichhap | 6 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 6 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-16 | 2016-08-07
Kavrepalanchok | Ghartichhap | 7 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 7 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-16 | 2016-08-07
Kavrepalanchok | Ghartichhap | 8 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 8 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 9 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Ghartichhap | 9 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Ghartichhap | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-07-25
Kavrepalanchok | Gokule | 1 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 1 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-16 | 2016-08-07
Kavrepalanchok | Gokule | 2 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 2 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 3 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 3 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12
Kavrepalanchok | Gokule | 4 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Gokule | 4 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-06 | 2016-08-13
Kavrepalanchok | Gokule | 5 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 5 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-06-26 | 2016-08-12
Kavrepalanchok | Gokule | 6 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 6 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-06-26 | 2016-08-13
Kavrepalanchok | Gokule | 7 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 7 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-06 | 2016-08-13
Kavrepalanchok | Gokule | 8 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 8 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-06 | 2016-08-12
Kavrepalanchok | Gokule | 9 | HELVETAS | Alliance-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Gokule | 9 | HELVETAS | Alliance-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Gokule | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-06 | 2016-08-12
Kavrepalanchok | JaisithokMandan | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 3 | 0 | 2016-10-15 | 2017-07-15
Kavrepalanchok | JaisithokMandan | 3 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 4 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 5 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 6 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 11 | 7 | 2016-11-15 | 2017-02-28 | 2 lintel,2 sill, 1 plinth, 2 foundation work completed
Kavrepalanchok | JaisithokMandan | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 7 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 26 | 15 | 2016-11-15 | 2017-04-15 | 4 roof completed, 1 lintel, 1 sill, 1 plinth,8 foundation work completed
Kavrepalanchok | JaisithokMandan | 7 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 8 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 12 | 1 | 2017-04-15 | 2017-06-30 | 1 roof completed
Kavrepalanchok | JaisithokMandan | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JaisithokMandan | 9 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 5 | 0 | 2017-04-15 | 2017-06-30
Kavrepalanchok | JaisithokMandan | 9 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-05 | 2016-04-11
Kavrepalanchok | JyamdiMandan | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22 | Our capacity to train in one group Is 30, so planned 30 but reached may vary depending on situation
Kavrepalanchok | JyamdiMandan | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-05-22
Kavrepalanchok | JyamdiMandan | All | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-15 | 2016-06-21
Kavrepalanchok | KatunjeBesi | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16
Kavrepalanchok | Kharelthok | All | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-22 | 2016-06-28
Kavrepalanchok | Kharpachok | 1 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 1 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 2 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 2 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 3 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 3 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 4 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 4 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 5 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 5 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 6 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 6 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 7 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 7 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 8 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 8 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kharpachok | 9 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kharpachok | 9 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | KolatiBhumlu | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-24 | 2016-05-30 | Two group of 30/30 at same venue and date, planned 30 but reached may vary depending on situation
Kavrepalanchok | KolatiBhumlu | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-31 | 2016-06-06 | Two group of 30/30 at same venue and date, planned 30 but reached may vary depending on situation
Kavrepalanchok | KolatiBhumlu | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-31 | 2016-06-06
Kavrepalanchok | KolatiBhumlu | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-31 | 2016-06-06
Kavrepalanchok | KolatiBhumlu | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-31 | 2016-06-06
Kavrepalanchok | KolatiBhumlu | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-24 | 2016-05-30
Kavrepalanchok | KolatiBhumlu | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-31 | 2016-06-06
Kavrepalanchok | Koshidekha | 1 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 7 | 7 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 2 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 20 | 20 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 3 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 8 | 8 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 4 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 15 | 15 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 5 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 7 | 7 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 6 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 46 | 46 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 6 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Material support on household WASH | HH Rain Water Harvesting | Tank and Hygiene Kits | # of households | Yes | Completed | 41 | 41 | 2016-08-01 | 2018-07-30
Kavrepalanchok | Koshidekha | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 7 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 9 | 9 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 8 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 35 | 35 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha | 9 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 23 | 23 | 2015-05-01 | 2016-07-30
Kavrepalanchok | Koshidekha | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Koshidekha | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | 2 Plastic ponds, water source protection and supply system construction | # of constructions | Yes | Planned | 4 | 0 | 2016-08-01 | 2018-07-30 | Ward not fixed yet
Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA-MISSO-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Planned | 200 | 0 | 2016-08-01 | 2017-07-30 | Ward will be fixed after beneficiary selection
Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Material support on household WASH | HH Rain Water Harvesting | Tank and Hygiene Kits | # of households | Yes | Planned | 55 | 0 | 2016-08-01 | 2018-07-30 | Ward will be fixed after beneficiary selection
Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Material support on household WASH | Household toilet construction | 35 Eco Toilet Construction | # of households | Yes | Planned | 35 | 0 | 2016-08-01 | 2018-07-30 | Ward will be fixed after beneficiary selection
Kavrepalanchok | Kushadevi | 1 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 1 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 2 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 2 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 3 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 3 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 4 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 4 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 5 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 5 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 6 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 6 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 7 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 7 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 8 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 8 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Kushadevi | 9 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Kushadevi | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Kushadevi | 9 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Machchhegaun | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-05-20 | 2016-05-26 | In a combine training 11 mason from Mechhegaaun
Kavrepalanchok | Machchhegaun | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 | In two group at same venue, same date 3 mason from Mechhegaun
Kavrepalanchok | MahadevsthanMandan | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-24 | 2016-03-30
Kavrepalanchok | MahadevsthanMandan | 1 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 | MToT training, Implementing Partner:- Nangshal Association
Kavrepalanchok | MahadevsthanMandan | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-27 | 2016-08-01
Kavrepalanchok | MahadevsthanMandan | 2 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 6 | 6 | 2016-06-01 | 2016-09-15 | beneficiaries are living in the completed houses
Kavrepalanchok | MahadevsthanMandan | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-24 | 2016-03-30
Kavrepalanchok | MahadevsthanMandan | 2 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-27 | 2016-08-01
Kavrepalanchok | MahadevsthanMandan | 3 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18 | Total 25 carpenter were trained in this (13-18 Feb 2016) training, in which 15 from other districts
Kavrepalanchok | MahadevsthanMandan | 3 | ROTARY | CC | ROTARY-BHU | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Planned | 28 | 0 | 2017-01-01 |  | Creative Cooperative in local implementing partner
Kavrepalanchok | MahadevsthanMandan | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 64 | 56 | 2016-08-25 | 2017-04-15 | 9 completed, 39 roof, 8 lintel band reached
Kavrepalanchok | MahadevsthanMandan | 3 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-13 | 2016-02-18
Kavrepalanchok | MahadevsthanMandan | 3 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-24 | 2016-03-30
Kavrepalanchok | MahadevsthanMandan | 3 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-27 | 2016-08-01
Kavrepalanchok | MahadevsthanMandan | 3 | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 69 | 69 | 2015-12-27 | 2018-12-30
Kavrepalanchok | MahadevsthanMandan | 4 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-27 | 2016-08-01
Kavrepalanchok | MahadevsthanMandan | 5 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 22 | 0 | 2017-04-20 | 2017-06-25
Kavrepalanchok | MahadevsthanMandan | 5 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-27 | 2016-08-01
Kavrepalanchok | MahadevsthanMandan | 6 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18
Kavrepalanchok | MahadevsthanMandan | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-03-30
Kavrepalanchok | MahadevsthanMandan | 6 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 7 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | MahadevsthanMandan | 7 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-24 | 2016-03-30
Kavrepalanchok | MahadevsthanMandan | 8 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 9 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-24 | 2016-03-30
Kavrepalanchok | MahadevsthanMandan | 9 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06
Kavrepalanchok | MahadevsthanMandan | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-06-27 | 2016-08-01
Kavrepalanchok | Mahadevtar | 2 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-11-29 | 2015-12-03
Kavrepalanchok | Mahadevtar | 3 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-11-29 | 2015-12-03
Kavrepalanchok | Mahadevtar | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-11-29 | 2015-12-03
Kavrepalanchok | Mahadevtar | 6 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-29 | 2015-12-03
Kavrepalanchok | Mahadevtar | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-29 | 2015-12-03
Kavrepalanchok | Mahadevtar | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-29 | 2015-12-03
Kavrepalanchok | Mahadevtar | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-29 | 2015-12-03
Kavrepalanchok | MahankalChaur | 1 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 2 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 3 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 4 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 5 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 6 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 7 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 8 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-22 | 2016-09-28
Kavrepalanchok | MahankalChaur | 9 | ARSOW | ARSOW | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-22 | 2016-09-28
Kavrepalanchok | Mangaltar | 1 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 1 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 2 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 2 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Mangaltar | 3 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 3 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Mangaltar | 4 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 4 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 5 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | Mangaltar | 5 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 6 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-20 | 2016-05-26 | In a combine training 2 mason from mangaltar
Kavrepalanchok | Mangaltar | 6 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Mangaltar | 7 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 7 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 8 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-03 | 2016-06-09 | In two group at same venue, same date 7 mason from Mangaltar
Kavrepalanchok | Mangaltar | 8 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Mangaltar | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-19 | 2016-07-20
Kavrepalanchok | Mangaltar | 9 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Mangaltar | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Kavrepalanchok | Mangaltar | 9 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 1 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 1 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 2 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 2 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 3 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 3 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 4 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 4 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 5 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 5 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 6 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 6 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Milche | 6 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 7 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 7 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-13
Kavrepalanchok | Milche | 7 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 8 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 8 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Milche | 9 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Milche | 9 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Nala(Ugrachandi) | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18
Kavrepalanchok | NayagaunDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-30 | 2016-04-05
Kavrepalanchok | NayagaunDeupur | 5 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Planned | 6 | 0 | 2017-08-22 | 2017-07-15
Kavrepalanchok | NayagaunDeupur | 5 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-30 | 2016-04-05
Kavrepalanchok | NayagaunDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 34 | 31 | 2016-08-15 | 2017-02-28 | 9 completed, 2 roof, 7 lintel, 10 sill,1 plinth, 2 foundation work completed
Kavrepalanchok | NayagaunDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-30 | 2016-04-05
Kavrepalanchok | NayagaunDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 30 | 17 | 2016-11-15 | 2017-04-15 | 7 roof, 1 lintel, 8 sill, 1 plinth level completed
Kavrepalanchok | NayagaunDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-30 | 2016-04-05
Kavrepalanchok | NayagaunDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 8 | 6 | 2017-05-15 | 2017-07-15 | 6 foundation work completed
Kavrepalanchok | NayagaunDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-30 | 2016-04-05
Kavrepalanchok | NayagaunDeupur | 9 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-30 | 2016-04-05
Kavrepalanchok | Panauti N.P. | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Panauti N.P. | 11 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations |  | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-09-01 | 2016-09-15
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 49 | 49 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 14 | 14 | 2016-07-07 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 16 | 16 | 2016-09-05 | 2016-09-23 | 60 masons from 5 ward are trained and so was planned
Kavrepalanchok | Panchkhal N.P. | 1 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-25 | 2016-02-29 | Location Detail: Tamaghat
Kavrepalanchok | Panchkhal N.P. | 1 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-28 | 2016-04-03 | Location Detail: Tinpiple
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 49 | 49 | 2016-08-01 | 2016-11-18 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Planned | 50 | 0 | 2016-12-14
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations |  | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-08-05 | 2016-09-11 | As community mobilizers were supporting enrolment, this session was postponded.
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 99 | 99 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 26 | 26 | 2016-07-07 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2016-09-01 |  | Through Housing support service Center (HSSC)
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 9 | 9 | 2016-09-05 | 2016-09-23
Kavrepalanchok | Panchkhal N.P. | 2 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 30 | 0 | 2016-09-01 |  | Venue is at ward 2, and mason were from ward 1 to 5
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 99 | 99 | 2016-08-01 | 2016-11-18 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Planned | 50 | 0 | 2016-12-14
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations |  | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 28 | 2016-08-03 | 2016-08-10
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 27 | 27 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 24 | 24 | 2016-07-07 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 3 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | Brick masonry with cement mortar technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-10 | 2016-12-31
Kavrepalanchok | Panchkhal N.P. | 3 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Ongoing | 1 | 0 | 2016-11-20 | 2017-01-31
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 12 | 12 | 2016-09-05 | 2016-09-23
Kavrepalanchok | Panchkhal N.P. | 3 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 3 | CL | CL | VG | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT Short training | # of trainees | Yes | Completed | 20 | 20 | 2016-08-15 | 2016-10-12 | Was funded as part of Corporate CSR activity - Centum didn't report to any local authorities
Kavrepalanchok | Panchkhal N.P. | 3 | CL | VG | VG | Training | Short training | Plumber | CTEVT Short training | # of trainees | Yes | Completed | 20 | 20 | 2016-08-18 | 2016-10-12 | Was funded as part of Corporate CSR activity - Centum didn't report to any local authorities
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 27 | 27 | 2016-08-01 | 2016-11-18 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Planned | 50 | 0 | 2016-12-14
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations |  | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-07-31 | 2016-08-03
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 15 | 15 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 28 | 28 | 2016-07-07 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 12 | 12 | 2016-09-05 | 2016-09-23
Kavrepalanchok | Panchkhal N.P. | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 15 | 15 | 2016-08-01 | 2016-11-18 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Planned | 50 | 0 | 2016-12-14
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations |  | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-09-05 | 2016-09-09
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 9 | 9 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 30 | 30 | 2016-07-07 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 11 | 11 | 2016-09-05 | 2016-09-23
Kavrepalanchok | Panchkhal N.P. | 5 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25 | Location Detail: Anaikot
Kavrepalanchok | Panchkhal N.P. | 5 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 9 | 9 | 2016-08-01 | 2016-11-18 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive
Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Planned | 50 | 0 | 2016-12-14
Kavrepalanchok | Panchkhal N.P. | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 8 | PIPALTAR | PSD-N | HFH | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 86 | 44 | 2016-04-01 | 2017-03-01 | This project is in planning stage. It will be finalized at the end of March
Kavrepalanchok | Panchkhal N.P. | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 10 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 10 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 11 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 11 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 13 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2015-12-25
Kavrepalanchok | Panchkhal N.P. | 14 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2015-12-21 | 2015-12-25
Kavrepalanchok | Panchkhal N.P. | 15 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2015-12-21 | 2015-12-25
Kavrepalanchok | Panchkhal N.P. | 15 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 15 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-28 | 2016-04-03
Kavrepalanchok | Panchkhal N.P. | 16 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2016-01-12 | 2016-01-16 | Location Detail: Anaikot
Kavrepalanchok | Panchkhal N.P. | 16 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-25 | 2016-02-29
Kavrepalanchok | Panchkhal N.P. | 17 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2015-12-25
Kavrepalanchok | Panchkhal N.P. |  | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance | # of constructions | Yes | Planned | 120 | 0 | 2016-09-01 |  | Ward will be identified after beneficiaries selected
Kavrepalanchok | Panchkhal N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 2 | # of trainees | Yes | Completed | 30 | 30 | 2016-11-14 | 2016-09-18
Kavrepalanchok | Panchkhal N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 1 | # of trainees | Yes | Completed | 30 | 30 | 2016-09-25 | 2016-09-29
Kavrepalanchok | Panchkhal N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 3 | # of trainees | Yes | Completed | 30 | 30 | 2016-11-21 | 2016-11-25
Kavrepalanchok | RaviOpi | 1 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 1 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 1 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 2 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 2 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 2 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 3 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 3 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 3 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 4 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 4 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 4 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 5 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 5 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 5 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 6 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 6 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 7 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 7 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 7 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 8 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 8 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 8 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi | 9 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RaviOpi | 9 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-14 | 2016-05-20
Kavrepalanchok | RaviOpi | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | RaviOpi | 9 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RaviOpi |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot- 8 ) and other logistic support |  | Yes | Completed | 970 | 921 | 2016-04-10
Kavrepalanchok | RyaleBhir | 1 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 1 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 1 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-08-29
Kavrepalanchok | RyaleBhir | 1 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 5 | 5 | 2016-06-05
Kavrepalanchok | RyaleBhir | 2 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 2 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2016-08-17 | 2016-12-31
Kavrepalanchok | RyaleBhir | 2 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 2 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 8 | 8 | 2016-06-05
Kavrepalanchok | RyaleBhir | 2 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Planned | 1 | 1 | 2016-02-07
Kavrepalanchok | RyaleBhir | 3 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 17 | 17 | 2016-12-06 | 2016-12-12 | Ryale vdc - Our plan is to conduct 8 mason training and 25 mason in each training
Kavrepalanchok | RyaleBhir | 3 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 3 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-12-06 | 2016-12-12 | Ryale vdc - Our plan is to conduct 8 mason training and 25 mason in each training
Kavrepalanchok | RyaleBhir | 3 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 3 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 16 | 16 | 2016-06-05
Kavrepalanchok | RyaleBhir | 4 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 63 | 63 | 2016-11-08 | 2016-11-14
Kavrepalanchok | RyaleBhir | 4 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 4 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 63 | 63 | 2016-11-08 | 2016-11-14
Kavrepalanchok | RyaleBhir | 4 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 4 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 38 | 38 | 2016-10-19
Kavrepalanchok | RyaleBhir | 4 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 12 | 0 | 2016-06-05
Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 31 | 31 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 5 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-08-17 | 2016-12-31 | Ryale vdc - 1 model houses per 3 mason training
Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 5 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 41 | 41 | 2016-11-16
Kavrepalanchok | RyaleBhir | 5 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 29 | 0 | 2016-06-05
Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Completed | 1 | 1 | 2016-10-20 | 2016-12-31
Kavrepalanchok | RyaleBhir | 6 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 13 | 13 | 2016-10-22 | 2016-12-12
Kavrepalanchok | RyaleBhir | 6 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 6 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-10-22 | 2016-12-12
Kavrepalanchok | RyaleBhir | 6 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 6 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 52 | 52 | 2016-06-05
Kavrepalanchok | RyaleBhir | 7 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 7 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 7 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 7 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 7 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 10 | 9 | 2016-06-05
Kavrepalanchok | RyaleBhir | 8 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 8 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 8 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 8 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 8 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 4 | 2 | 2016-06-05
Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 9 | HELVETAS | PTI |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2016-08-17 | 2016-12-31
Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28
Kavrepalanchok | RyaleBhir | 9 | HELVETAS | PTI |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | RyaleBhir | 9 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 13 | 0 | 2016-06-05
Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Planned | 1 | 1 | 2016-02-07
Kavrepalanchok | RyaleBhir | 2,7,8 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 30 | 30 | 2016-09-27 |  | Ward wise data is not received
Kavrepalanchok | RyaleBhir | 6,3 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-09-06 |  | Ward wise data is not received
Kavrepalanchok | RyaleBhir |  | NCRS | NCRS | SP | Others | Others | (Please specify in Activity Detail) | Prrvious Methainkot vdc- 1 sign bord with Built Back Safer ( 10 Key Messaged) in each 9 wards |  | Yes | Planned | 8 | 0 | 2016-05-01 | 2016-12-31
Kavrepalanchok | RyaleBhir |  | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 67 | 0 | 2016-10-22 | 2016-10-28
Kavrepalanchok | Saldhara | 1 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 1 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 2 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 2 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 3 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 3 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 4 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 4 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 5 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 5 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 6 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 6 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 7 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 7 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 8 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 8 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saldhara | 9 | HELVETAS | ANS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saldhara | 9 | HELVETAS | ANS |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SalleBhumlu | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SalleBhumlu | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 1 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 1 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 2 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 2 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 3 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 3 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 4 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 4 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 5 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 5 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 6 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 6 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 7 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 7 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 8 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 8 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 9 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Salmechakala(Taldhu) | 9 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sanowangthali | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 35 | 0 | 2016-05-14 | 2016-05-20
Kavrepalanchok | Saping | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saping | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Saping | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Saramthali | 1 | NYF | NYF | NYF-US | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-05-20 | 2016-05-20 | The tools distributed in the community for common use to Social leader and Chairperson of Bhume Secondary School in Shramthali VDC.
Kavrepalanchok | Saramthali | 1 | NYF | NYF | NYF-US | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-04-10 | 2016-05-15
Kavrepalanchok | Saramthali | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-07 | 2016-04-13
Kavrepalanchok | Saramthali | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-07 | 2016-04-13
Kavrepalanchok | Saramthali | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-07 | 2016-04-13
Kavrepalanchok | Saramthali | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-07 | 2016-04-13
Kavrepalanchok | Saramthali | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-07 | 2016-04-13
Kavrepalanchok | SikharAmbote | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Kavrepalanchok | SimalchourSyampati | 1 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18
Kavrepalanchok | Simthali | 1 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 1 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 1 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 2 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 2 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 2 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 3 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 3 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 3 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 4 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 4 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 5 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 5 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 5 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 6 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 6 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 6 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 7 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 7 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 8 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-27 | 2016-01-31
Kavrepalanchok | Simthali | 8 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Simthali | 9 | HELVETAS | JAYAN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Simthali | 9 | HELVETAS | JAYAN |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 1 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 1 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 2 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 2 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 3 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 3 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 4 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 4 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 5 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 5 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 6 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 6 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 7 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 7 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 8 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 8 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | SipaliChilaune | 9 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | SipaliChilaune | 9 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 1 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 1 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 2 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 2 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 3 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 3 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 4 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 4 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 5 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 5 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 6 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 6 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 7 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 7 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 8 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 8 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Kavrepalanchok | Sisakhani | 9 | HELVETAS | NETSA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Kavrepalanchok | Sisakhani | 9 | HELVETAS | NETSA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Lalitpur | Bajrabarahi N.P. | 1 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 4 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 14 | 2016-05-01 | 2016-11-01 | Agreement done with NRA
Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | MSEREOR |  | Technical Assistance | Door-to-door technical assistance | Continuous | 7 houses under construction | # of households | Yes | Ongoing | 58 | 0
Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 12 | 2016-05-01 | 2016-11-01 | Agreement done with NRA
Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | MSEREOR | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 7 houses under construction | # of households | Yes | Ongoing | 58 | 0 |  |  | 58 houses including 1 model house will be constructed
Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | MSEREOR |  | Technical Assistance | Door-to-door technical assistance | Continuous | 2 houses under construction | # of households | Yes | Ongoing | 57 | 0
Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 12 | 2016-05-01 | 2016-11-01 | Agreement done with NRA
Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | MSEREOR | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 2 houses under construction | # of households | Yes | Ongoing | 57 | 0 |  |  | 57 houses including 1 model house will be constructed
Lalitpur | Bajrabarahi N.P. | 7 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 12 | 2016-05-01 | 2016-11-01 | Agreement done with NRA
Lalitpur | Bajrabarahi N.P. | 9 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 3 | 3 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 11 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 12 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 8 | 8 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 13 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 44 | 44 | 2016-01-01 | 2016-03-04 | Funding organisation name- GDAA(Govinda Development Aid Association )
Lalitpur | Bajrabarahi N.P. | 13 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 20 | 20 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 14 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 9 | 9 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 15 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 4 | 4 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 16 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 2 | 2 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 17 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2015-09-01 | 2016-07-01
Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 250 | 0 | 2016-10-15 | 2017-11-30
Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 80 | 20 | 2016-09-15 | 2016-10-30
Lalitpur | Bajrabarahi N.P. | 2,3 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Planned | 4 | 0 | 2016-11-01 | 2016-12-31
Lalitpur | Bajrabarahi N.P. | 2,3 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Planned | 2 | 0 | 2016-11-01 | 2016-12-31
Lalitpur | Choughare | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 6 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-22 | 2016-12-28
Lalitpur | Choughare | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 6 | 2016-12-22 | 2016-12-28
Lalitpur | Dalchoki | 1 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 34 | 27
Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-11-01 | Agreement done with NRA
Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 34 | 27 |  |  | The grant support in Dalchoki VDC is given on the basis of NRS 200,000 per beneficiries to 250 Households
Lalitpur | Dalchoki | 2 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 15 | 1
Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 15 | 1
Lalitpur | Dalchoki | 3 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 23 | 1
Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 5 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 23 | 1
Lalitpur | Dalchoki | 4 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 23 | 2
Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 5 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 23 | 2
Lalitpur | Dalchoki | 5 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 21 | 11
Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 21 | 11
Lalitpur | Dalchoki | 6 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 19 | 2
Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 19 | 2
Lalitpur | Dalchoki | 7 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 47 | 23
Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 5 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 47 | 23
Lalitpur | Dalchoki | 8 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 34 | 11
Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 5 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 34 | 11
Lalitpur | Dalchoki | 9 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 34 | 17
Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 2016-01-01
Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRS 50,000 per beneficiries | # of households | Yes | Ongoing | 34 | 17
Lalitpur | Godawari N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Godawari N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Godawari N.P. | 9 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-05 | 2016-03-09
Lalitpur | Godawari N.P. | 1 & 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-06-21 | 2016-06-27
Lalitpur | Godawari N.P. | 1,2,3,4 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Ongoing | 76 | 54 | 2016-07-01
Lalitpur | Godawari N.P. | 1,2,3,4 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program | # of participants | Yes | Completed | 5 | 4 | 2016-08-23 | 2016-08-27 | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program
Lalitpur | Godawari N.P. | 1,2,3,4 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 4 | 0 |  |  | Date TBP
Lalitpur | Godawari N.P. | 3 & 4 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 32 | 2016-07-07 | 2016-07-13
Lalitpur | Karyabinayak N.P. | 2 | NSET | NSET | USAID | Training | Other trainings | Basic engineers training |  | # of trainees | Yes | Completed | 32 | 32 | 2015-10-01 | 2020-09-30
Lalitpur | Karyabinayak N.P. | 14 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-01-01 | 2016-03-04 | Funding organisation name- GDAA(Govinda Development Aid Association )
Lalitpur | Karyabinayak N.P. | 14 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 5 | 5 | 2016-03-05 |  | Funding organisation name- GDAA(Govinda Development Aid Association )
Lalitpur | Karyabinayak N.P. | 15 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-01-01 | 2016-03-04 | Funding organisation name- GDAA(Govinda Development Aid Association )
Lalitpur | Karyabinayak N.P. | 15 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 2 | 2 | 2016-03-05 |  | Funding organisation name- GDAA(Govinda Development Aid Association )
Lalitpur | Karyabinayak N.P. | 10,11,12,13 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Ongoing | 143 | 4 | 2016-07-01
Lalitpur | Karyabinayak N.P. | 10,11,12,13 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program | # of participants | Yes | Completed | 5 | 4 | 2016-08-23 | 2016-08-27 | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program
Lalitpur | Karyabinayak N.P. | 10,11,12,13 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 4 | 0 |  |  | Date TBP
Lalitpur | Karyabinayak N.P. | 10,11,12,13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 25 | 2016-07-24 | 2016-07-30 | Event venue is Chunni devi Temple, Karyabinayak 13
Lalitpur | Karyabinayak N.P. | 10,11,12,13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0
Lalitpur | Lalitpur U.M.N.P. | 28 & 29 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 28 | 2016-07-19 | 2016-07-25
Lalitpur | Lalitpur U.M.N.P. | 9 & 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-15 | 2016-07-21
Lalitpur | Lalitpur U.M.N.P. | 9,11,28,29 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program | # of participants | Yes | Completed | 5 | 7 | 2016-08-23 | 2016-08-27 | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program
Lalitpur | Lalitpur U.M.N.P. | 9,11,28,29 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 4 | 0
Lalitpur | Lalitpur U.M.N.P. |  | UNDP | UNDP | UNDP | Others | Others | (Please specify in Activity Detail) | To develop and test a concrete building blocks out of the debris materials that could be used as major construction materials to make reconstruction affordable and faster. |  | Yes | Planned | 0 | 0
Lalitpur | Lalitpur U.M.N.P. |  | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program | # of participants | Yes | Completed | 7 | 7 | 2016-07-15 | 2016-07-19
Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 50 | 98 | 2016-06-15 | 2016-06-15
Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 29 | 2016-12-08 | 2016-12-08
Lalitpur | Mahalaxmi N.P. | 1 | DCA | FSCN | DCA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Community orientation program on safe and resilient shelter construction | # of participants | Yes | Completed | 150 | 180 | 2016-07-16 | 2016-07-17
Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 1 | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Planned | 20 | 0 | 2016-12-30 | 2017-01-05
Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 1 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 20 | 2016-12-12 | 2016-12-12
Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 7 | 2016-09-16 | 2016-09-22
Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 2 | 2016-09-16 | 2016-09-22
Lalitpur | Mahalaxmi N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 4 | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Completed | 20 | 23 | 2016-03-16 | 2016-03-20 | At that time the DUDBC curriculum was of 5 days
Lalitpur | Mahalaxmi N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 1 | 2016-09-16 | 2016-09-22
Lalitpur | Mahalaxmi N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 4 | DCA | FSCN | DCA | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT based 390 hours Mason Training | # of trainees | Yes | Completed | 18 | 18 | 2016-02-01 | 2016-04-02
Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 23 | 2016-08-12 | 2016-08-12
Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 1 | 2016-09-16 | 2016-09-22
Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 20 | 2016-08-12 | 2016-08-12
Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 7 | 2016-09-16 | 2016-09-22
Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 20 | 2016-08-12 | 2016-08-12
Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 2 | 2016-09-16 | 2016-09-22
Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 10 | 2016-08-12 | 2016-08-12
Lalitpur | Mahalaxmi N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02
Lalitpur | Mahalaxmi N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training
Lalitpur | Mahalaxmi N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 15 | 18 | 2016-08-25 | 2016-08-25
Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRs. 50,000 per beneficiary as first installment | # of households | Yes | Ongoing | 33 | 0
Lalitpur | Mahalaxmi N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 27 | 8 | 2016-03-01 | 2018-05-01
Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRs. 50,000 per beneficiary as first installment | # of households | Yes | Ongoing | 33 | 0 | 2016-07-01
Lalitpur | Mahalaxmi N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 15 | 6 | 2016-08-25 | 2016-08-25
Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRs. 50,000 per beneficiary as first installment | # of households | Yes | Ongoing | 41 | 0
Lalitpur | Mahalaxmi N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 27 | 8 | 2016-03-01 | 2018-05-01
Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRs. 50,000 per beneficiary as first installment | # of households | Yes | Ongoing | 41 | 0 | 2016-07-01
Lalitpur | Mahalaxmi N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 15 | 6 | 2016-08-25 | 2016-08-25
Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti |  | Technical Assistance | Door-to-door technical assistance | Continuous | NRs. 50,000 per beneficiary as first installment | # of households | Yes | Ongoing | 41 | 0
Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 27 | 8 | 2016-03-01 | 2018-05-01
Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NRs. 50,000 per beneficiary as first installment | # of households | Yes | Ongoing | 41 | 0 | 2016-07-01
Lalitpur | Mahalaxmi N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information center at municipality office | # of households supported | Yes | Ongoing | 200 | 0 | 2016-11-25 | 2017-03-31
Lalitpur | Mahalaxmi N.P. | 19 | DCA | FSCN | DCA | Technical Assistance | Community reconstruction orientation | 1 session | Orientation on safe and resilient shelter construction | # of participants | Yes | Completed | 30 | 35 | 2016-07-13 | 2016-07-13 | Orientation by NRA Engineer
Lalitpur | Mahalaxmi N.P. | 1 & 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-28 | 2016-08-03
Lalitpur | Mahalaxmi N.P. | 1,2,6,7 | NRCS | NRCS | BRC | Others | Others | (Please specify in Activity Detail) | Debris Clearance by CFW |  | Yes | Ongoing | 69 | 61 | 2016-07-01
Lalitpur | Mahalaxmi N.P. | 1,2,6,7 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program | # of participants | Yes | Completed | 5 | 4 | 2016-08-23 | 2016-08-27 | District level TOT on PASSA was conducted where 19 volunteers from each working ward participated the program
Lalitpur | Mahalaxmi N.P. | 1,2,6,7 | NRCS | NRCS | BRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 4 | 0 |  |  | Date TBP
Lalitpur | Mahalaxmi N.P. | 6 & 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 23 | 2016-06-30 | 2016-07-06
Lalitpur | Mahalaxmi N.P. | 6 & 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-08-04 | 2016-08-04
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 33 | 0 | 2016-07-15
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-16 | 2016-02-20
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 33 | 32 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 33 | 20 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 33 | 9 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-05-27 | 2016-05-27
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 36 | 0 | 2016-07-15
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2015-09-14 | 2015-09-18 | During 5 days mason training as per DUDBC
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-22 | 2016-02-26
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 36 | 36 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 36 | 12 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 36 | 2 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-08-06
Makwanpur | Agara | 3 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 49 | 0 | 2016-07-15
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 | 2015-12-20 | 2016-01-24
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 15 | 2016-02-22 | 2016-02-26
Makwanpur | Agara | 3 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 49 | 48 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 49 | 15 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 49 | 3 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-07-11 | 2016-07-11
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 21 | 0 | 2016-07-15
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 15 | 2016-02-16 | 2016-02-20
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 21 | 21 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 21 | 4 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 21 | 3 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 2200986 cash support for 207 household | # of households | Yes | Completed | 207 | 207 | 2016-03-13 | 2016-06-30 | Rehabilitation of 3 GFS WASH Scheme
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-05-17 | 2016-05-17
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 22 | 0 | 2016-07-15
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2015-09-20 | 2015-09-24 | During 5 days mason training as per DUDBC
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-22 | 2016-02-26
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 22 | 22 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 22 | 11 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 22 | 4 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-18
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 21 | 0 | 2016-07-15
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-16 | 2016-02-20
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 21 | 21 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 21 | 17 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 21 | 10 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-10
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 43 | 0 | 2016-07-15
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-16 | 2016-02-20
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 43 | 43 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 43 | 26 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 43 | 5 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-08-03 | 2016-08-03
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 50 | 0 | 2016-07-15
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-22 | 2016-02-26
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 50 | 50 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 50 | 34 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 50 | 3 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-07-14 | 2016-07-14 | 1 session was conducted in each ward
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 25 | 0 | 2016-07-15
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-02-22 | 2016-02-26
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 25 | 25 | 2016-08-04 | 2016-10-04
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 25 | 16 | 2016-09-27 | 2017-01-30
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 25 | 0 | 2016-10-17 | 2017-07-17
Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 556498 cash support for 89 households | # of households | Yes | Completed | 89 | 89 | 2016-03-13 | 2016-06-30 | Rehabilitation of 1 GFS WASH Scheme
Makwanpur | Ambhanjyang | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 1 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 1 | 2016-04-18 | 2016-04-24
Makwanpur | Ambhanjyang | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Ambhanjyang | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 3 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-04-18 | 2016-04-24 | 7 days mason training
Makwanpur | Ambhanjyang | 3 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 1 | 2016-04-18 | 2016-04-24
Makwanpur | Ambhanjyang | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 5 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-04-24
Makwanpur | Ambhanjyang | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 7 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Ambhanjyang | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 7 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 3 | 2016-04-18 | 2016-04-24
Makwanpur | Ambhanjyang | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 8 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Ambhanjyang | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 9 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-01-22
Makwanpur | Ambhanjyang | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 4 | 4 | 2016-03-11 | 2016-04-14
Makwanpur | Ambhanjyang | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Ambhanjyang | 9 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Betini | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-10 | 2016-12-10
Makwanpur | Betini | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 33 | 33 | 2016-05-16 | 2016-05-16
Makwanpur | Betini | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 1 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-08-16 | 2016-08-22
Makwanpur | Betini | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-11 | 2016-12-11
Makwanpur | Betini | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 15 | 15 | 2016-05-17 | 2016-05-17
Makwanpur | Betini | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 2 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 7 | 2016-08-16 | 2016-08-22
Makwanpur | Betini | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 | 2016-03-11 | 2016-04-14
Makwanpur | Betini | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-11 | 2016-12-11
Makwanpur | Betini | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 63 | 63 | 2016-05-18 | 2016-05-18
Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27
Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 8 | 8 | 2016-08-16 | 2016-08-22
Makwanpur | Betini | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-12 | 2016-12-12
Makwanpur | Betini | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 19 | 19 | 2016-05-19 | 2016-05-19
Makwanpur | Betini | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 4 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 8 | 7 | 2016-08-16 | 2016-08-22
Makwanpur | Betini | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-12 | 2016-12-12
Makwanpur | Betini | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 28 | 28 | 2016-05-20 | 2016-05-20
Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-08 | 2016-08-14
Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 8 | 2016-08-08 | 2016-08-14
Makwanpur | Betini | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Betini | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 5 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Betini | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-13 | 2016-12-13
Makwanpur | Betini | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 15 | 15 | 2016-05-21 | 2016-05-21
Makwanpur | Betini | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 6 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-08-08 | 2016-08-14
Makwanpur | Betini | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-13 | 2016-12-13
Makwanpur | Betini | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 30 | 30 | 2016-05-22 | 2016-05-22
Makwanpur | Betini | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 7 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 6 | 2016-08-08 | 2016-08-14
Makwanpur | Betini | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-13 | 2016-12-13
Makwanpur | Betini | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Betini | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 54 | 54 | 2016-05-23 | 2016-05-23
Makwanpur | Betini | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 8 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 7 | 2016-08-08 | 2016-08-14
Makwanpur | Betini | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-13 | 2016-12-13
Makwanpur | Betini | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | Betini | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 33 | 33 | 2016-05-24 | 2016-05-24
Makwanpur | Betini | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Betini | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Betini | 9 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 6 | 2016-08-08 | 2016-08-14
Makwanpur | Betini | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 1 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Bhaise | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 1 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Bhaise | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 1 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 2 | 2 | 2015-12-20 | 2016-01-24
Makwanpur | Bhaise | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 2 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Bhaise | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 | 2016-03-11 | 2016-04-14
Makwanpur | Bhaise | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 9 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Bhaise | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Bhaise |  | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | BhartaPundyadevi | 1 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 2 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | BhartaPundyadevi | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 3 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 4 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | BhartaPundyadevi | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 5 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 6 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 7 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 8 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | BhartaPundyadevi | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 9 | HELVETAS | TCN | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | BhartaPundyadevi | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | BhartaPundyadevi | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 | 2016-03-11 | 2016-04-14
Makwanpur | Bhimfedi | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Bhimfedi | 8 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | Bhimfedi | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Bhimfedi | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Bhimfedi | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04
Makwanpur | Budhichaur | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 15 | 15 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-03
Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-07-20 | 2016-07-26
Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 12 | 2016-07-20 | 2016-07-26
Makwanpur | Budhichaur | 1 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 4 | 4 | 2016-03-11 | 2016-04-14
Makwanpur | Budhichaur | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-05 | 2016-12-05
Makwanpur | Budhichaur | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 11 | 11 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 2 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-07-20 | 2016-07-26
Makwanpur | Budhichaur | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-05 | 2016-12-05
Makwanpur | Budhichaur | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 9 | 9 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 | 2015-12-20 | 2016-01-24
Makwanpur | Budhichaur | 3 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-07-20 | 2016-07-26
Makwanpur | Budhichaur | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-05 | 2016-12-05
Makwanpur | Budhichaur | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 7 | 7 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 4 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-07-20 | 2016-07-26
Makwanpur | Budhichaur | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04
Makwanpur | Budhichaur | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 21 | 21 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-03
Makwanpur | Budhichaur | 5 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-07-20 | 2016-07-26
Makwanpur | Budhichaur | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04
Makwanpur | Budhichaur | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 6 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-08-21 | 2016-08-27
Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-08 | 2016-12-08
Makwanpur | Budhichaur | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 23 | 23 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27
Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27
Makwanpur | Budhichaur | 7 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Budhichaur | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04
Makwanpur | Budhichaur | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 14 | 14 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 8 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-08-21 | 2016-08-27
Makwanpur | Budhichaur | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-08 | 2016-12-08
Makwanpur | Budhichaur | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 14 | 14 | 2016-02-05 | 2016-02-07
Makwanpur | Budhichaur | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Budhichaur | 9 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-08-21 | 2016-08-27
Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 65 | 2016-12-24 | 2016-11-30
Makwanpur | Chitlang | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 8 | 8 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 8 | 8 | 2015-12-23 | 2015-12-23
Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 21 | 21 | 2016-11-24 | 2017-01-04
Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 | 2016-01-20 | 2016-01-24 | At that time the training period was 5 days and the training was conducted at ward no. 8, Markhu, where the participation form Markhu and Chitlang were merged.
Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 61 | 2016-12-15 | 2016-12-15
Makwanpur | Chitlang | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 14 | 14 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 | 2015-12-23 | 2015-12-23
Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 13 | 9 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 56 | 2016-12-16 | 2016-12-16
Makwanpur | Chitlang | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 7 | 7 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 7 | 7 | 2015-12-23 | 2015-12-23
Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 20 | 0 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 49 | 2016-11-30 | 2016-11-30
Makwanpur | Chitlang | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 | 2015-12-23 | 2015-12-23
Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 14 | 1 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1.5 hours each session | # of participants | Yes | Ongoing | 600 | 195 | 2016-07-22 | 2016-12-23
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information Center for reconstruction process in Chitlang | # of households supported | Yes | Ongoing | 150 | 34 | 2016-01-09 | 2017-02-16
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and 1-2 project staffs | # of households | Yes | Ongoing | 90 | 24 | 2017-02-28 | 2018-02-28 | 2 Constructions were completed before Lumanti's intervention
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 per household | # of households | Yes | Ongoing | 90 | 53 | 2016-11-01 | 2018-02-28
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Planned | 10 | 0 | 2017-02-25
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Retrofitting | 80000 per household | # of households | Yes | Planned | 25 | 0 | 2017-03-01
Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Soap, Water, Posters, Flipchart, orientation | # of households | Yes | Planned | 90 | 0 | 2017-03-01
Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Planned | 45 | 0 | 2017-11-10
Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 13 | 13 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 13 | 13 | 2015-12-23 | 2015-12-23
Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 10 | 0 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Completed | 25 | 24 | 2016-01-24 | 2016-01-24 | This is local disaster management Committee ( it helped in beneficiary selection process and CGI sheet distribution)
Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 78 | 2016-12-08 | 2016-12-08
Makwanpur | Chitlang | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 6 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 5 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 6 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 10 | 3 | 2016-09-01 | 2016-11-30 | Joint training Mason and carpenter
Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 6 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-02 | 2016-12-01 | 7 days basic plumbing training
Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 73 | 2016-12-23 | 2016-12-23
Makwanpur | Chitlang | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 | 2015-12-23 | 2015-12-23
Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 16 | 15 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1.5 hours each session | # of participants | Yes | Ongoing | 300 | 113 | 2016-07-22 | 2016-12-26
Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and 1-2 project staffs | # of households | Yes | Ongoing | 36 | 4 | 2017-02-28 | 2018-02-28
Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 per household | # of households | Yes | Ongoing | 36 | 22 | 2016-11-01 | 2018-02-28
Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Planned | 5 | 0 | 2017-02-25
Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Retrofitting | 80000 per household | # of households | Yes | Planned | 25 | 0 | 2017-03-01
Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Soap, Water, Posters, Flipchart, orientation | # of households | Yes | Planned | 36 | 0 | 2017-03-01
Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 80 | 2016-12-18 | 2016-12-18
Makwanpur | Chitlang | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 14 | 14 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 8 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 5 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Chitlang | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 | 2015-12-23 | 2015-12-23 | There were no distribution in ward no. 6 and 9.
Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 21 | 0 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 8 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 10 | 5 | 2016-09-01 | 2016-11-30 | Joint training Mason and carpenter
Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 8 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-02 | 2016-12-01 | 7 days basic plumbing training
Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 90 | 2016-12-14 | 2016-12-14
Makwanpur | Chitlang | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 29 | 29 | 2016-01-22 | 2016-01-24
Makwanpur | Chitlang | 9 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 5 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 23 | 0 | 2016-11-24 | 2017-02-28
Makwanpur | Chitlang | 9 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 10 | 12 | 2016-09-01 | 2016-11-30 | Joint training Mason and carpenter
Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22
Makwanpur | Chitlang | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24
Makwanpur | Chitlang | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-05 | 2016-10-05
Makwanpur | Chitlang | 9 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 4 | 2016-09-02 | 2016-12-01 | 7 days basic plumbing training
Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1.5 hours each session | # of participants | Yes | Ongoing | 200 | 135 | 2016-07-22 | 2016-12-23
Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and 1-2 project staffs | # of households | Yes | Ongoing | 24 | 16 | 2017-02-28 | 2018-02-28
Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 per household | # of households | Yes | Ongoing | 24 | 23 | 2016-11-01 | 2018-02-28
Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Planned | 5 | 0 | 2017-02-25
Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Retrofitting | 80000 per household | # of households | Yes | Planned | 25 | 0 | 2017-03-01
Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Soap, Water, Posters, Flipchart, orientation | # of households | Yes | Planned | 24 | 0 | 2017-03-01
Makwanpur | Dandakharka | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 3 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 7 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 9 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | Dandakharka | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Dandakharka | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-29 | 2016-06-04
Makwanpur | Dandakharka | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Dandakharka | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Dhimal | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Dhimal |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01
Makwanpur | Dhimal |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Planned | 9 | 1 | 2017-01-01 | 2017-05-01
Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 | 2016-11-26 | 2016-11-26
Makwanpur | Fakhel | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 31 | 31 | 2016-08-01 | 2016-12-31
Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | At that time the training period was 5 days and the training was conducted at ward no. 2, Kulekhani, where the participation form Fakhel and Kulekhani were merged.
Makwanpur | Fakhel | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 51 | 2016-11-25 | 2016-11-25
Makwanpur | Fakhel | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 28 | 28 | 2016-11-24 | 2017-01-04
Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 | 2016-11-22 | 2016-11-22
Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 29 | 29 | 2016-11-24 | 2017-01-04
Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Completed | 25 | 27 | 2016-01-21 | 2016-01-21
Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 55 | 2016-11-23 | 2016-11-23
Makwanpur | Fakhel | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 20 | 20 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 20 | 20 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 23 | 23 | 2016-11-24 | 2017-01-04
Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 4 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 62 | 2016-11-19 | 2016-11-19
Makwanpur | Fakhel | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 13 | 13 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 13 | 13 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 22 | 20 | 2016-11-24 | 2017-02-28
Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 | 2016-11-18 | 2016-11-18
Makwanpur | Fakhel | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 5 | 5 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 5 | 5 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 | 2016-11-24 | 2017-01-04
Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 53 | 2016-11-24 | 2016-11-24
Makwanpur | Fakhel | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 22 | 15 | 2016-11-24 | 2017-02-28
Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 | 2016-11-27 | 2016-11-27
Makwanpur | Fakhel | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Fakhel | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 20 | 20 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 20 | 20 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 | 2016-11-24 | 2017-01-04
Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 41 | 2016-11-29 | 2016-11-29
Makwanpur | Fakhel | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | Fakhel | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 | 2016-01-23 | 2016-01-24
Makwanpur | Fakhel | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 | 2016-02-06 | 2016-02-08
Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 17 | 17 | 2016-11-24 | 2017-01-04
Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14
Makwanpur | Fakhel | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23
Makwanpur | Fakhel | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-03 | 2016-10-03
Makwanpur | Fakhel |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01
Makwanpur | Fakhel |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Planned | 9 | 1 | 2017-01-01 | 2017-05-01 | Community participation and donor support continious
Makwanpur | Faparbari | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 2 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Faparbari | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Faparbari | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Faparbari | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 9 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Faparbari | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | Faparbari | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Faparbari | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Gogane | 1 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 80 | 22 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 1 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 47 | 1 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 2 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 40 | 0 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 2 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 39 | 2 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 2 | BC | CARD | ARC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | 1 Architect, Engineer | # of households supported | Yes | Ongoing | 637 | 67 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-11-17 | 2016-11-23 | Second time Mason training at Gogane
Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2016-11-24 |  | Will conduct Mason training at Gogane from 24th Nov 2016
Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-04 | 2016-06-10
Makwanpur | Gogane | 3 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 30 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 3 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 46 | 2 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 4 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 32 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 4 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 46 | 10 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 5 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 27 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 5 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 64 | 2 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 6 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 20 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 6 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 92 | 0 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 7 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 80 | 0 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 7 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 145 | 6 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 8 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 30 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 8 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 93 | 4 | 2016-12-01 | 2018-06-20
Makwanpur | Gogane | 9 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 20 | 2016-12-21 | 2017-12-20
Makwanpur | Gogane | 9 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 65 | 6 | 2016-12-01 | 2018-06-20
Makwanpur | Handikhola |  | BLF | BNMT Nepal | BLF | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01
Makwanpur | Handikhola |  | BLF | BNMT Nepal | BLF | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 1 | 1 | 2016-12-16 | 2016-12-17
Makwanpur | Hetauda U.M.N.P. | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Hetauda U.M.N.P. |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01
Makwanpur | Hetauda U.M.N.P. |  | BLF | BNMT Nepal | BLF | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01
Makwanpur | Hetauda U.M.N.P. |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Planned | 9 | 3 | 2017-01-01 | 2017-05-01
Makwanpur | Hetauda U.M.N.P. |  | BLF | BNMT Nepal | BLF | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 1 | 1 | 2016-12-14 | 2016-12-15
Makwanpur | IpaPanchakanya | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-07 | 2016-12-07 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 39 | 39 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-07 | 2016-12-07 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 45 | 45 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | IpaPanchakanya | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-06 | 2016-12-06 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 84 | 84 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-02 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-05 | 2016-12-05 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 44 | 44 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-02 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-05 | 2016-12-05 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 50 | 50 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-02 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | IpaPanchakanya | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-09 | 2016-12-09 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 34 | 34 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-09 | 2016-12-09 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 25 | 25 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-09 | 2016-12-09 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 8 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | IpaPanchakanya | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 75 | 75 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 8 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | IpaPanchakanya | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-08 | 2016-12-08 | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 57 | 57 | 2016-02-04 | 2016-02-06
Makwanpur | IpaPanchakanya | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | IpaPanchakanya | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 1 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 1 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 3 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 5 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 7 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 8 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 8 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 9 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kalikatar | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kankada | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-12 | 2016-06-18 | Demo house was constructed during mason training.
Makwanpur | Khairang | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 3 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 5 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 7 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 8 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Khairang |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01 | Demo house was constructed during mason training.
Makwanpur | Khairang |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 1 | 1 | 2016-12-07 | 2016-12-09 | Demo house was constructed during mason training.
Makwanpur | Kogate | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-02 | 2016-12-02 | Demo house was constructed during mason training.
Makwanpur | Kogate | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Kogate | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kogate | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-02 | 2016-12-02 | Demo house was constructed during mason training.
Makwanpur | Kogate | 2 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 | 2015-12-17 | 2016-01-22 | Demo house was constructed during mason training.
Makwanpur | Kogate | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 14 | 14 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kogate | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kogate | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-02 | 2016-12-02 | Demo house was constructed during mason training.
Makwanpur | Kogate | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 6 | 6 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-20 | Demo house was constructed during mason training.
Makwanpur | Kogate | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kogate | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Kogate | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kogate | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 5 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22 | Demo house was constructed during mason training.
Makwanpur | Kogate | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Kogate | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-03 | 2016-12-03 | Demo house was constructed during mason training.
Makwanpur | Kogate | 6 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22 | Demo house was constructed during mason training.
Makwanpur | Kogate | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 8 | 8 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Kogate | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Kogate | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-03 | 2016-12-03 | Demo house was constructed during mason training.
Makwanpur | Kogate | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-20 | Demo house was constructed during mason training.
Makwanpur | Kogate | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-03 | 2016-12-03 | Demo house was constructed during mason training.
Makwanpur | Kogate | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 4 | 4 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-20 | Demo house was constructed during mason training.
Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Kogate | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-04 | 2016-12-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 17 | 17 | 2016-02-03 | 2016-02-04 | Demo house was constructed during mason training.
Makwanpur | Kogate | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Kogate | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Kogate | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 49 | 2016-12-15 | 2016-12-15 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 14 | 14 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 27 | 15 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Planned | 45 | 0 | 2017-01-10 |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 16 | 16 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-29 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 27 | 28 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 3 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed in the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School qnd Political parties. | # of committees | Yes | Completed | 25 | 27 | 2016-01-21 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 51 | 2016-12-16 | 2016-12-16 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 23 | 23 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 23 | 23 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 34 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Planned | 45 | 0 | 2017-01-11 |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 7 | 7 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 7 | 7 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 10 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Planned | 45 | 0 | 2017-01-12 |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 21 | 21 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 21 | 21 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 50 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 45 | 2016-12-18 | 2016-12-18 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 15 | 15 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 23 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 48 | 2016-12-22 | 2016-12-22 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 9 | 9 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 9 | 9 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 14 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 52 | 2016-12-24 | 2016-12-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 28 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 | 2016-12-29 | 2016-12-29 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 | 2016-01-22 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 15 | 0 | 2016-11-24 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-02-19 | 2016-02-23 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 42 | 42 | 2016-04-16 | 2016-04-17 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-25 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 34 | 34 | 2016-04-16 | 2016-04-17 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 101 | 101 | 2016-04-16 | 2016-04-17 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 66 | 66 | 2016-04-16 | 2016-04-17 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 58 | 58 | 2016-04-17 | 2016-04-18 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 32 | 32 | 2016-04-17 | 2016-04-18 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 43 | 43 | 2016-04-17 | 2016-04-18 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 10 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 47 | 47 | 2016-04-17 | 2016-04-18 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 77 | 77 | 2016-04-17 | 2016-04-18 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18 |  | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-08 | 2016-08-14 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01 | Demo house was constructed during mason training.
Makwanpur | Makwanpurgadhi |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Planned | 9 | 0 | 2017-01-01 | 2017-05-01 | Demo house was constructed during mason training.
Makwanpur | Manahari | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 3 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 5 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 7 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 8 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 9 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manahari |  | BLF | BNMT Nepal | BLF | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01 | Demo house was constructed during mason training.
Makwanpur | Manahari |  | BLF | BNMT Nepal | BLF | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 1 | 1 | 2016-12-18 | 2016-12-19 | Demo house was constructed during mason training.
Makwanpur | Manahari |  | CS | Sabal | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Planned | 20 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 41 | 41 | 2016-05-12 | 2016-05-13 | Demo house was constructed during mason training.
Makwanpur | Manthali | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 53 | 53 | 2016-05-12 | 2016-05-13 | Demo house was constructed during mason training.
Makwanpur | Manthali | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 44 | 44 | 2016-05-12 | 2016-05-13 | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 3 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Manthali | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 42 | 42 | 2016-05-12 | 2016-05-13 | Demo house was constructed during mason training.
Makwanpur | Manthali | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 37 | 37 | 2016-05-11 | 2016-05-12 | Demo house was constructed during mason training.
Makwanpur | Manthali | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 50 | 50 | 2016-05-11 | 2016-05-12 | Demo house was constructed during mason training.
Makwanpur | Manthali | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 61 | 61 | 2016-05-11 | 2016-05-12 | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-10-01 |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 33 | 33 | 2016-05-11 | 2016-05-12 | Demo house was constructed during mason training.
Makwanpur | Manthali | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-10-01 | 2016-12-18 | Demo house was constructed during mason training.
Makwanpur | Manthali | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 24 | 24 | 2016-05-11 | 2016-05-12 | Demo house was constructed during mason training.
Makwanpur | Manthali | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-10-01 | 2016-12-18 | Demo house was constructed during mason training.
Makwanpur | Manthali | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Manthali | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-09-08 | 2016-09-14 | Demo house was constructed during mason training.
Makwanpur | Manthali | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 90 | 2016-11-18 | 2016-11-18 | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 16 | 16 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 26 | 26 | 2016-11-25 | 2017-01-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 80 | 2016-11-19 | 2016-11-19 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 19 | 8 | 2016-11-25 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 51 | 2016-11-26 | 2016-11-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 16 | 0 | 2016-11-25 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 48 | 2016-11-25 | 2016-11-25 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 19 | 19 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 19 | 19 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 18 | 0 | 2016-11-25 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 49 | 2016-11-19 | 2016-11-19 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 15 | 15 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 24 | 24 | 2016-11-25 | 2017-01-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 63 | 2016-11-23 | 2016-11-23 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 12 | 12 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 12 | 12 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 15 | 0 | 2016-11-25 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 33 | 2016-11-28 | 2016-11-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 17 | 17 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 17 | 17 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 10 | 0 | 2016-11-25 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 47 | 2016-11-27 | 2016-11-27 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 | 2015-02-26 | 2016-03-01 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 | 2016-11-25 | 2017-01-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed in the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School qnd Political parties. | # of committees | Yes | Completed | 25 | 17 | 2016-01-20 | 2016-01-20 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 53 | 2016-11-24 | 2016-11-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 7 | 7 | 2016-01-20 | 2016-01-21 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 7 | 7 | 2015-12-25 | 2015-12-26 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 11 | 0 | 2016-11-25 | 2017-02-28 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-11-22 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 5 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-04 | 2016-10-04 | Demo house was constructed during mason training.
Makwanpur | Namtar | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 28 | 2016-02-29 | 2016-03-04 | Demo house was constructed during mason training.
Makwanpur | Namtar | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 32 | 2016-06-02 | 2016-06-08 | Demo house was constructed during mason training.
Makwanpur | Namtar | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 3 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | Namtar | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 5 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 7 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 8 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 9 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Namtar | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 2 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Nibuwatar |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01 | Demo house was constructed during mason training.
Makwanpur | Nibuwatar |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 1 | 1 | 2016-12-11 | 2016-12-13 | Demo house was constructed during mason training.
Makwanpur | Raigaun | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 2 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-01-22 | Demo house was constructed during mason training.
Makwanpur | Raigaun | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Raigaun | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 2 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Raigaun | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 5 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-01-22 | Demo house was constructed during mason training.
Makwanpur | Raigaun | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 8 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raigaun | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Raksirang | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 3 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 5 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 7 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 8 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 9 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SarikhetPalase | ALL | CS | Sabal | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Planned | 20 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 1 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 4 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 6 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 6 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 7 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 8 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 9 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Shikharpur | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 5 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 3 | 3 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 6 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 7 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 8 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 8 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 3 | 3 | 2016-03-11 | 2016-04-14 | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | ShreepurChhatiwan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-06 | 2016-12-06
Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 13 | 13 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 1 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27
Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-09 | 2016-12-09
Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 35 | 35 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 2 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27
Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 22 | 22 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-15
Makwanpur | SisneriMahadevsthan | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-07-20 | 2016-07-26 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-07-20 | 2016-07-26
Makwanpur | SisneriMahadevsthan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-07 | 2016-12-07
Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 25 | 25 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 4 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-07-20 | 2016-07-26
Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-07 | 2016-12-07
Makwanpur | SisneriMahadevsthan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 17 | 17 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | SisneriMahadevsthan | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 5 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-07-20 | 2016-07-26
Makwanpur | SisneriMahadevsthan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 82 | 82 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | SisneriMahadevsthan | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 6 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27
Makwanpur | SisneriMahadevsthan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-12-09 | 2016-12-09
Makwanpur | SisneriMahadevsthan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 19 | 19 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-15
Makwanpur | SisneriMahadevsthan | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 7 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-08-21 | 2016-08-27
Makwanpur | SisneriMahadevsthan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 2 | 2 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | SisneriMahadevsthan | 8 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 8 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-07-20 | 2016-07-26
Makwanpur | SisneriMahadevsthan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 2 | 2 | 2016-02-17 | 2016-02-18 | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-15
Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | SisneriMahadevsthan | 9 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-07-20 | 2016-07-26
Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Demo house was constructed during mason training.
Makwanpur | Sukaura | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 27 | 27 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-06
Makwanpur | Sukaura | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 | 2016-07-20 | 2016-07-26
Makwanpur | Sukaura | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 33 | 33 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Sukaura | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Sukaura | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-07-20 | 2016-07-26
Makwanpur | Sukaura | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 | 2016-07-20 | 2016-07-26
Makwanpur | Sukaura | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 1 | 1 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Sukaura | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 2 | 2016-07-20 | 2016-07-26
Makwanpur | Sukaura | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 30 | 30 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Sukaura | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-07-20 | 2016-07-26
Makwanpur | Sukaura | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 18 | 18 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-06
Makwanpur | Sukaura | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27
Makwanpur | Sukaura | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 9 | 9 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 | 2016-08-21 | 2016-08-27
Makwanpur | Sukaura | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 26 | 26 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 0 | 2016-09-18
Makwanpur | Sukaura | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2016-08-21 | 2016-08-27
Makwanpur | Sukaura | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-08-21 | 2016-08-27
Makwanpur | Sukaura | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 20 | 20 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-06
Makwanpur | Sukaura | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-08-21 | 2016-08-27
Makwanpur | Sukaura | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 63 | 63 | 2016-02-09 | 2016-02-10
Makwanpur | Sukaura | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 | 2016-09-18 | 2016-12-06
Makwanpur | Sukaura | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 | 2016-07-20 | 2016-07-26
Makwanpur | Sukaura | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Thaha N.P. | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-05 | 2016-07-11 | At Thaha Municipality,Palung
Makwanpur | Thaha N.P. | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | Thaha N.P. | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-12 | 2016-07-18 | At Thaha Municipality,Daman
Makwanpur | Thaha N.P. | 9 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 30 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Thaha N.P. | 9 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 12 | 2016-09-03 | 2016-12-02 | Joint training Mason and carpenter
Makwanpur | Thaha N.P. | 9 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-04 | 2016-02-29 | 7 days basic plumbing training
Makwanpur | Thaha N.P. | 10 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 30 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Thaha N.P. | 10 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 11 | 2016-09-03 | 2016-12-02 | Joint training Mason and carpenter
Makwanpur | Thaha N.P. | 10 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-04 | 2016-02-29 | 7 days basic plumbing training
Makwanpur | Thaha N.P. | 12 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 30 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Thaha N.P. | 12 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 13 | 2016-09-03 | 2016-12-02 | Joint training Mason and carpenter
Makwanpur | Thaha N.P. | 12 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-04 | 2016-02-29 | 7 days basic plumbing training
Makwanpur | Thaha N.P. | 14 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Planned | 30 | 0 | 2017-01-01 | 2017-05-30
Makwanpur | Thaha N.P. | 14 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 19 | 2016-09-03 | 2016-12-02 | Joint training Mason and carpenter
Makwanpur | Thaha N.P. | 14 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-28 | 2016-07-04 | At Thaha Municipality,Bajrabarahi
Makwanpur | Thaha N.P. | 14 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-04 | 2016-02-29 | 7 days basic plumbing training
Makwanpur | Thingan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 8 | 8 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 31 | 31 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 30 | 30 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Thingan | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 4 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Thingan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 34 | 34 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 5 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-01-22
Makwanpur | Thingan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 55 | 55 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 5 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | Thingan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 29 | 29 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 7 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 17 | 17 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 1 | 0
Makwanpur | Thingan | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 15 | 15 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 8 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 2 | 0
Makwanpur | Thingan | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 30 | 30 | 2016-04-14 | 2016-04-15
Makwanpur | Thingan | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Makwanpur | Thingan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-22 | 1 session was conducted in each ward
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 15 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2015-02-16 | 2015-02-20 | During 5 days mason training as per DUDBC
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 17 | 2016-09-20 | 2016-09-24
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 15 | 13 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 15 | 7 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 15 | 7 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-05-20 | 2016-05-20
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 36 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 14 | 2016-09-20 | 2016-09-24
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 36 | 36 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 36 | 10 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 36 | 2 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 253829 cash support for 44 households | # of households | Yes | Completed | 44 | 44 | 2016-03-13 | 2016-06-30 | Rehabilitation of 1 GFS WASH Scheme
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-05-26 | 2016-05-26
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 33 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 | 2015-09-26 | 2015-09-30 | During 5 days mason training as per DUDBC
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 18 | 2016-09-20 | 2016-09-24
Makwanpur | TistungDeurali | 3 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-01-24
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 33 | 32 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 33 | 10 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 33 | 5 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-18
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 28 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-09-20 | 2016-09-24
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 28 | 28 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 28 | 18 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 28 | 14 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 1300602 cash support for 104 households | # of households | Yes | Completed | 104 | 104 | 2016-03-13 | 2016-06-30 | Rehabilitation of 1 GFS WASH Scheme
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-22
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 46 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 15 | 2016-09-26 | 2016-09-30
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 46 | 44 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 46 | 15 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 46 | 7 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-18
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 33 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 3 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 13 | 2016-09-26 | 2016-09-30
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 33 | 32 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 33 | 12 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 33 | 5 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-07
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 22 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 14 | 2016-09-26 | 2016-09-30
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 22 | 21 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 22 | 8 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 22 | 3 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-08-30
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 25 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-09-26 | 2016-09-30
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 25 | 24 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 25 | 6 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 25 | 1 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 | 2016-08-16 | 2016-08-16
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 62 | 0 | 2016-07-15
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-09-15 | Technical assistance was done during Model house construction
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-09-20 | 2016-09-24
Makwanpur | TistungDeurali | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 | 2016-03-11 | 2016-04-14
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 62 | 60 | 2016-08-04 | 2016-10-04
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 62 | 24 | 2016-09-27 | 2017-01-30
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 62 | 5 | 2016-10-17 | 2017-07-17
Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 811682 cash support for 35 households | # of households | Yes | Completed | 35 | 35 | 2016-03-13 | 2016-06-30 | Rehabilitation of 1 GFS WASH Scheme
Makwanpur | TistungDeurali |  | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2017-05-01 | This activity is not mentioned in drop down menu.
Makwanpur | TistungDeurali |  | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Planned | 9 | 1 | 2017-01-01 | 2017-05-01 | Community participation and donor support continious
Nuwakot | BagesworiChokade | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | BagesworiChokade | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Balkumari | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Barsunchet | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Belkot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Belkot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Belkot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Belkot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Belkot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Belkot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Belkot | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Belkot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Betini |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 60 | 2016-12-21
Nuwakot | Betini |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Betini |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 60 | 2016-12-21
Nuwakot | Bhadratar | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Bhadratar | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Bhalche | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bhalche | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-20 | 2016-05-26
Nuwakot | Bhalche | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-08 | 2016-08-14
Nuwakot | Bhalche | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-31 | 2016-09-06
Nuwakot | Bhalche | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-09-24 | 2016-09-30
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 272 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 280 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 280 | 68 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 6 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 6 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 146 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 318 | 318 | 2016-02-10 | 2016-07-01
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 312 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 312 | 66 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 91 | 91 | 2016-04-01 | 2016-09-30
Nuwakot | Bidur N.P. | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 30 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 30 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 249 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 369 | 369 | 2016-02-10 | 2016-07-01
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 442 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 442 | 199 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 191 | 191 | 2016-04-01 | 2016-09-30
Nuwakot | Bidur N.P. | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 21 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 21 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 399 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 347 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 384 | 298 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Retrofitting training | Engineers, sub-engineers |  | # of trainees | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 347 | 108 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 25 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Short training | Social mobilizer |  | # of trainees | Yes | Ongoing | 256 | 73 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Ongoing | 96 | 66 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 25 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 414 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 503 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 503 | 125 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | ACF | EA | ECHO | Technical Assistance | Demonstration Construction | House | Stone machinary, iron pillars, use of hood and plywod 2 storeys house | # of constructions | Yes | Completed | 1 | 1 | 2016-04-01 | 2016-06-07 | Implementating Local partner is ITDSN, 30 mason also tranied from various VDCs,NRA provided 7 days training
Nuwakot | Bidur N.P. | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 39 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 39 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 312 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 326 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 326 | 78 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 355 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 395 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 395 | 89 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 28 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 28 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 462 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 660 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 660 | 98 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 385 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 806 | 806 | 2016-02-10 | 2016-07-01
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 725 | 31 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 725 | 58 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 149 | 149 | 2016-04-01 | 2016-09-30
Nuwakot | Bidur N.P. | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 43 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 43 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 44 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 131 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 131 | 44 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 59 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 59 | 69 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 64 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Bidur N.P. |  | SCI | CDC | SCI | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | Broadcasting through 3 FM twice a day | # of episodes | Yes | Ongoing | 6 | 6 | 2016-09-01 | 2017-03-31 | Reconstruction related Radio program
Nuwakot | Budhasing | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 48 | 2016-10-03
Nuwakot | Budhasing | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Budhasing |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 66 | 2016-12-16
Nuwakot | Budhasing |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Budhasing |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 66 | 2016-12-16
Nuwakot | Bungtang | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Bungtang | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Charghare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Charghare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Charghare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Charghare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Charghare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Charghare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Charghare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Charghare | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 48 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 105 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 105 | 20 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 118 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 88 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 136 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 47 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 45 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 45 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 70 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 92 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 92 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 20 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 20 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 57 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 121 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 121 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 75 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 95 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 95 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 80 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 67 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 67 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chaturale | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0
Nuwakot | Chaughada | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 2 | Islamic Relief | BATAS | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 210 | 210 | 2016-03-01 | 2017-02-28 | Rehabilitation/Construction of 6 community learning centre
Nuwakot | Chaughada | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 3 | Islamic Relief | BATAS | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0 |  |  | Rehabilitation/Construction of 6 community learning centre
Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Team Leader, Social Mobilizer | # of households | Yes | Planned | 255 | 0
Nuwakot | Chaughada | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 4 | Islamic Relief | BATAS | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0 |  |  | Rehabilitation/Construction of 6 community learning centre
Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days Masons training | # of trainees | Yes | Planned | 40 | 0
Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Construction of 255 household | # of households | Yes | Planned | 255 | 0
Nuwakot | Chaughada | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 6 | Islamic Relief | BATAS | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0 |  |  | Rehabilitation/Construction of 6 community learning centre
Nuwakot | Chaughada | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chaughada | 8 | Islamic Relief | BATAS | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0 |  |  | Rehabilitation/Construction of 6 community learning centre
Nuwakot | Chaughada | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chauthe | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 7 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07
Nuwakot | Chauthe | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 58 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 58 | 48 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 64 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 54 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 54 | 42 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 47 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 52 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 52 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 31 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 64 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 35 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 77 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 30 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 46 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 46 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 31 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 31 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 42 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 102 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 102 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Chhap | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 7 | 0 | 2017-01-05
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 94 | 0 | 2016-10-06
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 94 | 0 | 2016-10-06
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 6 | 6 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 19 | 19 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 94 | 0 | 2016-10-06 |  | ON going under shelter program
Nuwakot | Dangsing | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Composite structure, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 19 | 19 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 2 | 0 | 2017-01-05
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 94 members in 3 committee | # of committees | Yes | Completed | 94 | 94 | 2016-10-06 | 2016-10-06
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 94 | 94 | 2016-10-06 | 2016-10-06 | ON going under shelter program
Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 28 | 28 | 2016-01-26 | 2016-01-26
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 16 | 0 | 2016-10-06
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 16 | 0 | 2016-10-06
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 16 | 0 | 2016-10-06 |  | ON going under shelter program
Nuwakot | Dangsing | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 16 members in 1 committee | # of committees | Yes | Completed | 16 | 16 | 2016-10-06 | 2016-10-06
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 16 | 16 | 2016-10-06 | 2016-10-06 | ON going under shelter program
Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 8 | 8 | 2016-01-26 | 2016-01-26
Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 13 | 13 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 13 | 13 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Stone masonry in mud mortar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06
Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-09-27 | 2016-10-03
Nuwakot | Dangsing | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 1 | 0 | 2017-01-05
Nuwakot | Dangsing | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Dangsing | 9 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 2 | 0 | 2017-01-05
Nuwakot | Deurali | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Deurali | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Duipipal | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Duipipal | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Fikuri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ganeshthan | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 38 | 2016-09-14 | 2016-09-14
Nuwakot | Gaunkharka | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 72 | 2016-09-15
Nuwakot | Gaunkharka | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 60 | 2016-09-16
Nuwakot | Gaunkharka | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 78 | 2016-09-17
Nuwakot | Gaunkharka | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 50 | 2016-09-18
Nuwakot | Gaunkharka | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 54 | 2016-11-11
Nuwakot | Gaunkharka | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 67 | 2016-11-12
Nuwakot | Gaunkharka | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 54 | 2016-11-13
Nuwakot | Gaunkharka | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 82 | 2016-11-14
Nuwakot | Gaunkharka | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gaunkharka |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 62 | 2016-11-22
Nuwakot | Gaunkharka |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Gaunkharka |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 62 | 2016-11-22
Nuwakot | Gerkhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Gerkhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Gerkhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Gerkhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gerkhu | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ghyangphedi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ghyangphedi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Gorsyang | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 1 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 3 | 0 | 2017-01-05
Nuwakot | Gorsyang | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 3 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 4 | 0 | 2017-01-05
Nuwakot | Gorsyang | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Gorsyang | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 4 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Ongoing | 1 | 0 | 2017-01-05
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 22 | 0 | 2016-08-24
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 22 | 0 | 2016-08-24
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 22 | 22 | 2016-08-24 |  | ON going under shelter program
Nuwakot | Gorsyang | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 22 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 22 | 22 | 2016-08-24 | 2016-08-24 | ON going under shelter program
Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 1 | 1 | 2016-01-30 | 2016-01-30
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 20 | 0 | 2016-08-24
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 20 | 0 | 2016-08-24
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 20 | 20 | 2016-08-24 |  | ON going under shelter program
Nuwakot | Gorsyang | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 20 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 20 | 20 | 2016-08-24 | 2016-08-24 | ON going under shelter program
Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 9 | 9 | 2016-01-30 | 2016-01-30
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 56 | 0 | 2016-08-24
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 56 | 0 | 2016-08-24
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 56 | 56 | 2016-08-24 |  | ON going under shelter program
Nuwakot | Gorsyang | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Brick masonry in cement motar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Training | Other trainings | Other trainings (specify in Activity Detail) | Compressed Stabilized Earthen Block (CSEB) Production | # of trainees | Yes | Completed | 18 | 18 | 2016-12-19 | 2016-12-25
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 56 members in 3 committee | # of committees | Yes | Completed | 3 | 3 | 2016-08-24 | 2016-08-24
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 56 | 56 | 2016-08-24 | 2016-08-24 | ON going under shelter program
Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 22 | 22 | 2016-01-30 | 2016-01-30
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 32 | 0 | 2016-08-24
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 32 | 0 | 2016-08-24
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 9 | 9 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 32 | 32 | 2016-08-24 |  | ON going under shelter program
Nuwakot | Gorsyang | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Composite structure, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 9 | 9 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 32 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 32 | 32 | 2016-08-24 | 2016-08-24 | ON going under shelter program
Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 11 | 11 | 2016-01-30 | 2016-01-30
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 10 | 0 | 2016-08-24
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 10 | 0 | 2016-08-24
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 10 | 10 | 2016-08-24 |  | ON going under shelter program
Nuwakot | Gorsyang | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05
Nuwakot | Gorsyang | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 10 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 10 | 10 | 2016-08-24 | 2016-08-24 | ON going under shelter program
Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 6 | 6 | 2016-01-30 | 2016-01-30
Nuwakot | Jiling | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Jiling | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Jiling | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kabilas | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kabilas | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kakani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 1 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 106 | 106 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 1 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 52 | 52 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 118 | 118 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 2 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 80 | 80 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 124 | 124 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 3 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 85 | 85 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 4 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 112 | 112 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 4 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 62 | 62 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 5 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 95 | 95 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 5 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 72 | 72 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 6 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 69 | 69 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 6 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 53 | 53 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 7 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 74 | 74 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 7 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 73 | 73 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 8 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 215 | 215 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 8 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 154 | 154 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 119 | 119 | 2016-02-10 | 2016-07-01
Nuwakot | Kalikahalde | 9 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 85 | 85 | 2016-04-01 | 2016-09-30
Nuwakot | Kalikahalde | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalikahalde | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-02 | 2016-07-08
Nuwakot | Kalyanpur | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-06-23 | 2016-06-30 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Kalyanpur | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-23 | 2016-06-30 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Kalyanpur | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-23 | 2016-06-30 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Kalyanpur | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kalyanpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kalyanpur | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kaule | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2016-01-25 | 2016-01-29
Nuwakot | Kaule | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2016-05-20 | 2016-05-26
Nuwakot | Kaule |  | BC | NRCS | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-25 | 2016-01-29
Nuwakot | KhadagBhanjyang | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 40 | 2016-11-23
Nuwakot | KhadagBhanjyang | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 61 | 2016-11-24
Nuwakot | KhadagBhanjyang | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 72 | 2016-11-25
Nuwakot | KhadagBhanjyang | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Completed | 120 | 178 | 2016-08-24 | 2016-09-01
Nuwakot | KhadagBhanjyang | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 80 | 2016-09-29
Nuwakot | KhadagBhanjyang | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 16 | 0
Nuwakot | KhadagBhanjyang | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Community house construction in on the job training- Stone Mortar with Cement | # of constructions | Yes | Ongoing | 1 | 0
Nuwakot | KhadagBhanjyang | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KhadagBhanjyang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 63 | 2016-11-15
Nuwakot | KhadagBhanjyang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | KhadagBhanjyang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 63 | 2016-11-15
Nuwakot | Kharanitar | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kharanitar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kharanitar | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | KholegaunKhanigau | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | KholegaunKhanigau | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | KholegaunKhanigau | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | KholegaunKhanigau | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | KholegaunKhanigau | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | KholegaunKhanigau | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Kintang | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Kumari | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Kumari | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Lachyang | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-28 | 2016-06-03
Nuwakot | Lachyang | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2016-06-04 | 2016-06-09
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 88 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 131 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 131 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 149 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 143 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 117 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 123 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 113 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 94 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 94 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 88 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 147 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 134 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 191 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 191 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 170 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 117 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 103 | 25 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 103 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Likhu | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Madanpur | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 2 | 0
Nuwakot | Madanpur | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 56 | 2016-10-26
Nuwakot | Madanpur | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 3 | 0
Nuwakot | Madanpur | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 1 | 0
Nuwakot | Madanpur | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 53 | 2016-09-29
Nuwakot | Madanpur | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 1 | 0
Nuwakot | Madanpur | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 2 | 0
Nuwakot | Madanpur | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 2 | 0
Nuwakot | Madanpur | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 84 | 2016-08-17
Nuwakot | Madanpur | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Community house construction in on the job training- Stone Mortar with Cement | # of constructions | Yes | Ongoing | 1 | 0
Nuwakot | Madanpur | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Madanpur | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Madanpur | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 5 | 0
Nuwakot | Madanpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 86 | 2016-06-24 | 2016-10-26
Nuwakot | Madanpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Madanpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 62 | 2016-06-24 | 2016-10-26
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 24 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 236 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 236 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 43 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 239 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 239 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 62 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 176 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 176 | 20 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 257 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 257 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 171 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 162 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 162 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 108 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 108 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 87 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 180 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 180 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 80 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 384 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 384 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 29 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 400 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 400 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Manakamana | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 1 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 5 | 5 | 2016-04-17 | 2016-04-23
Nuwakot | Manakamana | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 3 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23
Nuwakot | Manakamana | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 129 | 129 | 2016-09-01 | 2017-01-10
Nuwakot | Manakamana | 4 | WR | NJS | WR | Training | Short training | Carpenter | CTEVT for Carpenter (12person trained) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-23 | 2016-10-29
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Providing transport support for construction of houses,house are under constructionn | # of households | Yes | Ongoing | 129 | 53 | 2016-05-01
Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Door-to-door technical assistance | Continuous | Inspection, monitoring, supervisio and facialition | # of households | Yes | Ongoing | 129 | 50 | 2016-05-01 |  | Construction ongoing
Nuwakot | Manakamana | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Demonstration Construction | House | Model Panel Construction (no. of constructions) model house | # of constructions | Yes | Ongoing | 24 | 1 | 2016-05-01 | 2016-11-21
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | tools | # of households | Yes | Ongoing | 129 | 127 | 2016-05-01
Nuwakot | Manakamana | 4 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 24 | 24 | 2016-04-17 | 2016-04-23
Nuwakot | Manakamana | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 4 | WR | NJS | WR | Training | Vocational training | New masons (50 days OJT CTEVT) | DUDBC/CTEVT/NRA | # of trainees | Yes | Ongoing | 10 | 20 | 2017-02-09 |  | Planning to give in actaul construction site of beneficiaries
Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One Reconstruction Coordintion Committee is formed in each ward | # of committees | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-15
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs. 50,000/- per household | # of households | Yes | Ongoing | 129 | 127 | 2016-08-17
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs. Rs. 150,000/- as per the govenrment grant distribution guidelines | # of households | Yes | Planned | 129 | 0
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs. 100,000/- As per the Government grants distribuiton guidelines | # of households | Yes | Planned | 129 | 0
Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Rs. 50,000/- per household | # of households | Yes | Planned | 129 | 0
Nuwakot | Manakamana | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 5 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 5 | 1 | 2016-04-17 | 2016-04-23
Nuwakot | Manakamana | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 85 | 85 | 2016-08-01 | 2017-01-10
Nuwakot | Manakamana | 6 | WR | NJS | WR | Training | Short training | Carpenter | CTEVT for Carpenter (8 person trained ) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-23 | 2016-10-29
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Providing transport support for construction of houses, house are under construction | # of households | Yes | Ongoing | 85 | 30 | 2016-05-01
Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Door-to-door technical assistance | Continuous | Inspection, monitoring, supervisio and facialition | # of households | Yes | Ongoing | 85 | 28 | 2016-05-01 |  | Construction ongoing
Nuwakot | Manakamana | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Demonstration Construction | House | Model Panel Construction (no. of constructions) model house | # of constructions | Yes | Ongoing | 13 | 3 | 2016-05-01 | 2016-11-21
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | tools | # of households | Yes | Ongoing | 85 | 73 | 2016-05-01
Nuwakot | Manakamana | 6 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 20 | 19 | 2016-04-05 | 2016-04-11
Nuwakot | Manakamana | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 6 | WR | NJS | WR | Training | Vocational training | New masons (50 days OJT CTEVT) | DUDBC/CTEVT/NRA | # of trainees | Yes | Ongoing | 10 | 11 | 2017-02-10 |  | Planning to give in actaul construction site of beneficiaries
Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One Reconstruction Coordintion Committee is formed in each ward | # of committees | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-15
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs. 50,000/- per household | # of households | Yes | Ongoing | 85 | 78 | 2016-08-17
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs. Rs. 150,000/- as per the govenrment grant distribution guidelines | # of households | Yes | Planned | 85 | 0
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs. 100,000/- As per the Government grants distribuiton guidelines | # of households | Yes | Planned | 85 | 0
Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Rs. 50,000/- per household | # of households | Yes | Planned | 85 | 0
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 71 | 71 | 2016-08-01 | 2017-01-10
Nuwakot | Manakamana | 7 | WR | NJS | WR | Training | Short training | Carpenter | CTEVT for Carpenter (12 person trained ) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-23 | 2016-10-29
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Providin transport support for construction of houses,house are under construction | # of households | Yes | Ongoing | 71 | 33 | 2016-05-01
Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Door-to-door technical assistance | Continuous | Inspection, monitoring, supervisio and facialition | # of households | Yes | Ongoing | 71 | 34 | 2016-05-01 |  | Construction ongoing
Nuwakot | Manakamana | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Demonstration Construction | House | Model Panel Construction (no. of constructions) model house | # of constructions | Yes | Ongoing | 15 | 2 | 2016-05-01 | 2016-11-21
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | tools | # of households | Yes | Ongoing | 71 | 69 | 2016-05-01
Nuwakot | Manakamana | 7 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 21 | 21 | 2016-03-22 | 2016-03-30
Nuwakot | Manakamana | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 7 | WR | NJS | WR | Training | Vocational training | New masons (50 days OJT CTEVT) | DUDBC/CTEVT/NRA | # of trainees | Yes | Ongoing | 10 | 9 | 2017-02-11 |  | Planning to give in actaul construction site of beneficiaries
Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One Reconstruction Coordintion Committee is formed in each ward | # of committees | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-16
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs. 50,000/- per household | # of households | Yes | Ongoing | 71 | 68 | 2016-08-17
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs. Rs. 150,000/- as per the govenrment grant distribution guidelines | # of households | Yes | Planned | 71 | 0
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs. 100,000/- As per the Government grants distribuiton guidelines | # of households | Yes | Planned | 71 | 0
Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Rs. 50,000/- per household | # of households | Yes | Planned | 71 | 0
Nuwakot | Manakamana | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 8 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 10 | 8 | 2016-04-05 | 2016-04-11
Nuwakot | Manakamana | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | 9 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 10 | 13 | 2016-04-05 | 2016-04-11
Nuwakot | Manakamana | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Manakamana | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2016-07-28 | 2016-08-03
Nuwakot | Manakamana |  | BC | WR | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 99 | 99 | 2016-03-28 | 2016-04-23
Nuwakot | Narjamandap | 1 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 91 | 91 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 1 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 45 | 45 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 245 | 245 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 2 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 155 | 155 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 195 | 195 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 3 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 131 | 131 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 4 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 195 | 195 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 4 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 78 | 78 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 5 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 112 | 112 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 5 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 89 | 89 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 6 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 149 | 149 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 6 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 126 | 126 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 7 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 106 | 106 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 7 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 59 | 59 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 8 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 94 | 94 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 8 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 82 | 82 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 166 | 166 | 2016-02-10 | 2016-07-01
Nuwakot | Narjamandap | 9 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 139 | 139 | 2016-04-01 | 2016-09-30
Nuwakot | Narjamandap | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Narjamandap | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Okharpauwa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Panchkanya | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ralukadevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ratmate | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 7 | 7 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ratmate | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ratmate | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ratmate | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ratmate | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Ratmate | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Ratmate | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Rautbesi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Rautbesi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 59 | 2016-06-10 | 2016-06-26
Nuwakot | Rautbesi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Rautbesi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 59 | 2016-06-10 | 2016-06-26
Nuwakot | Salme | 1 | HFH | ASF | HFH | Technical Assistance | Household reconstruction orientation | 1 session | Orientation given in Skilled Mason Training, Community and PASSA meeting. | # of households | Yes | Completed | 560 | 560 | 2016-07-09 | 2016-10-02
Nuwakot | Salme | 1 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Ongoing | 539 | 539 | 2016-11-20
Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Completed | 30 | 30 | 2016-08-17 | 2016-08-23
Nuwakot | Salme | 1 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House | One Demo house construction for all 9 wards. | # of constructions | Yes | Completed | 1 | 1 | 2017-01-02 | 2017-02-03
Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | Two groups mason were given skilled mason training | # of trainees | Yes | Completed | 60 | 60 | 2016-09-17 | 2016-10-02
Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-02 | 2017-02-02
Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | Short training | Social mobilizer | Participatory Approach For Safe Shelter (PASSA) training given to Social Mobilizers | # of trainees | Yes | Completed | 1 | 1 | 2016-07-12 | 2016-07-16
Nuwakot | Salme | 2 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 2 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site supervisors are visiting the sites for technical assistance | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site supervisors are visiting the sites for technical assistance | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site supervisors are visiting the sites for technical assistance | # of households |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Samari | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 9 | 9 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Samari | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 2 | 2 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 4 | 4 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samari | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04
Nuwakot | Samari | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 73 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 80 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 80 | 28 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 76 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 96 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 96 | 30 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 131 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 139 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 139 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 127 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 114 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 114 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 129 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 45 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 65 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 65 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 35 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 60 | 27 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 97 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 102 | 23 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 95 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 34 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 1 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 1 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 56 | 56 | 2016-04-02 | 2016-04-02
Nuwakot | Samundratar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 52 | 52 | 2016-04-03 | 2016-04-03
Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 39 | 39 | 2016-04-04 | 2016-04-04
Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 55 | 55 | 2016-04-05 | 2016-04-05
Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 63 | 63 | 2016-04-06 | 2016-04-06
Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 1 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 68 | 68 | 2016-04-07 | 2016-04-07
Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 12 | 12 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 97 | 97 | 2016-04-08 | 2016-04-08
Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 10 | 10 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 8 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 8 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 80 | 80 | 2016-04-09 | 2016-04-09
Nuwakot | Samundratar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-04-11 | 2016-05-31
Nuwakot | Samundratar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 35 | 35 | 2016-04-10 | 2016-04-10
Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2015-11-27 | 2015-12-07
Nuwakot | Samundratar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Shikharbesi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 44 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 8 | 8 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 62 | 62 | 2016-04-11 | 2016-04-11
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 47 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 47 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 62 | 62 | 2016-04-12 | 2016-04-12
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-10-26 | 2016-12-22 | most of women belong from tamang community
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 45 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 59 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 59 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 56 | 56 | 2016-04-13 | 2016-04-13
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 120 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 59 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 59 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 64 | 64 | 2016-04-14 | 2016-04-14
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 8 | 8 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 7 | 7 | 2016-10-26 | 2016-12-22 | most of women belong from tamang community
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 58 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 54 | 54 | 2016-04-15 | 2016-04-15
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-10-26 | 2016-12-22 | most of women belong from tamang community
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 53 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 36 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 36 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 46 | 46 | 2016-04-16 | 2016-04-16
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 26 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 61 | 27 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 60 | 60 | 2016-04-17 | 2016-04-17
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-10-26 | 2016-12-22 | most of women belong from tamang community
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 42 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 23 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 64 | 64 | 2016-04-18 | 2016-04-18
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2015-11-25 | 2015-12-05
Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-10-26 | 2016-12-22 | most of women belong from tamang community
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 38 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 30 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 30 | 34 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 28 | 28 | 2016-04-19 | 2016-04-19
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sikre | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 1 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 84 | 84 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 104 | 104 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 38 | 38 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 4 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 72 | 72 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 5 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 53 | 53 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 6 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 58 | 58 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 7 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 51 | 51 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 8 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 66 | 66 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 49 | 49 | 2016-02-10 | 2016-07-01
Nuwakot | Sundaradevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sundaradevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Sunkhani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Suryamati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Suryamati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Suryamati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Suryamati | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-20 | 2016-07-26
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 77 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 64 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 101 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 139 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 97 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 97 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 45 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 56 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 56 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 71 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 3 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 39 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 89 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 89 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 24 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 37 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 76 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 3 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 5 | 14 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 9 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 68 | 0 | 2016-10-06
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 68 | 0 | 2016-10-06
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 20 | 2 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 68 | 68 | 2016-10-06 |  | ON going under shelter program
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Stone masonry in mud mortar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Brick masonry in cement motar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Composite structure, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-09-20 | 2016-09-26
Nuwakot | Taruka | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 20 | 20 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26
Nuwakot | Taruka | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 68 members in 4 committee | # of committees | Yes | Completed | 4 | 4 | 2016-10-06 | 2016-10-06
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 68 | 68 | 2016-10-06 | 2016-10-06 | ON going under shelter program
Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 20 | 20 | 2016-01-30 | 2016-01-30
Nuwakot | Taruka | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 11 | 11 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 11 | 11 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Ongoing | 32 | 0 | 2016-10-06
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Ongoing | 32 | 0 | 2016-10-06
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 16 | 16 | 2016-09-20 | 2016-09-26
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Ongoing | 32 | 32 | 2016-10-06 |  | ON going under shelter program
Nuwakot | Taruka | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-24
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-09-20 | 2016-09-26
Nuwakot | Taruka | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 32 members in 3 committee | # of committees | Yes | Completed | 3 | 3 | 2016-10-06 | 2016-10-06
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 32 | 32 | 2016-10-06 | 2016-10-06 | ON going under shelter program
Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 16 | 16 | 2016-01-30 | 2016-01-30
Nuwakot | Taruka |  | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Planned | 20 | 0
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 110 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 28 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 28 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 142 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 109 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 109 | 28 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 93 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 52 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 52 | 25 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 23 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 23 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 41 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 32 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 46 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 38 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 38 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 117 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 75 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 89 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 57 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 11 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 57 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 18 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 80 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 129 | 5 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 129 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 1 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 129 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 210 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 210 | 27 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 1 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 6 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 81 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 142 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 142 | 19 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 2 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 135 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 2 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 17 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 3 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 12 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 126 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 103 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 103 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 4 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 236 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 179 | 7 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 179 | 18 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 5 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 16 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 195 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 190 | 22 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 190 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 6 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 8 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 69 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 62 | 4 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 62 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 7 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 10 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 672 | 373 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 360 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 360 | 13 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 24 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 8 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 24 | 15 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 704 | 193 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 203 | 9 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 203 | 14 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | EoI |  | EoI | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 32 | 57 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | EoI |  | EoI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thansing | 9 | NSET | NSET | USAID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 32 | 57 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-06-01 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Thaprek | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 1 | 0
Nuwakot | Thaprek | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 1 | 0
Nuwakot | Thaprek | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 67 | 2016-09-15
Nuwakot | Thaprek | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 2 | 0
Nuwakot | Thaprek | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 69 | 2016-11-28
Nuwakot | Thaprek | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Community house construction in on the job training- Stone Mortar with Cement | # of constructions | Yes | Ongoing | 1 | 0
Nuwakot | Thaprek | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 4 | 0
Nuwakot | Thaprek | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 40 | 2016-11-29
Nuwakot | Thaprek | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 3 | 0
Nuwakot | Thaprek | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 60 | 67 | 2016-12-01
Nuwakot | Thaprek | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Ongoing | 5 | 0
Nuwakot | Thaprek | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Thaprek |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 60 | 2016-11-17 | 2016-12-31
Nuwakot | Thaprek |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0
Nuwakot | Thaprek |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 60 | 2016-11-17 | 2016-12-31
Nuwakot | Tupche | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Tupche | 1 | HFH |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 60 | 60 | 2016-06-01
Nuwakot | Tupche | 2 | HFH |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees |  | Planned | 0 | 0
Nuwakot | Tupche | 3 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23
Nuwakot | Tupche | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants |  | Planned | 0 | 0
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 143 | 143 | 2016-11-01
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | 1 technical site supervisor, 2 social mobilizers | # of households | Yes | Ongoing | 143 | 143 | 2016-11-01
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1 | 1 | 2016-11-01 |  | established one Housing Support Service Center to provide support to both wards 6 and 8
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-01
Nuwakot | Tupche | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-10 | 2016-11-16 | 7 days rural Mason training conducted combining ward 6 and 8
Nuwakot | Tupche | 6 | HFH | ASF | HFH | Training | Short training | Social mobilizer | Conducted PASSA training | # of trainees | Yes | Completed | 1 | 1 | 2016-10-01 | 2016-10-31 | total 35 community people were given PASSA training
Nuwakot | Tupche | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants |  | Planned | 0 | 0
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 77 | 77 | 2016-11-01
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | 1 technical site supervisor, 2 social mobilizers | # of households | Yes | Ongoing | 77 | 77 | 2016-11-01
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1 | 1 | 2016-11-01 |  | established one Housing Support Service Center to provide support to both wards 6 and 8
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-01
Nuwakot | Tupche | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-10 | 2016-11-16 | 7 days rural Mason training conducted combining ward 6 and 8
Nuwakot | Tupche | 8 | HFH | ASF | HFH | Training | Short training | Social mobilizer | Conducted PASSA training | # of trainees | Yes | Completed | 1 | 1 | 2016-10-01 | 2016-10-31 | total 35 community people were given PASSA training
Nuwakot | Tupche | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-17 | 2016-06-23 | Start date of 7 days mason training is 22nd may 2016, Local partner is ITDSN to the raatmate, jiling, belkot beneficiaries
Nuwakot | Urleni | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30
Nuwakot | Urleni | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-12 | 2016-06-18
Nuwakot | Urleni | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-19 | 2016-06-25
Okhaldhunga | Baruneshwor | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-02 | 2017-03-24 | Planning data - National Level
Okhaldhunga | Baruneshwor | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-02 |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-03 | 2017-03-25 | Planning data - National Level
Okhaldhunga | Baruneshwor | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-02 |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-02 | 2017-03-24 | Planning data - National Level
Okhaldhunga | Baruneshwor | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-02 |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 5 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 5 | 5 | 2016-03-02 | 2016-04-30
Okhaldhunga | Baruneshwor | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-02 |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-03 | 2017-03-25 | Planning data - National Level
Okhaldhunga | Baruneshwor | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-02 |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-02 | 2017-03-24 | Planning data - National Level
Okhaldhunga | Baruneshwor | 7 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30
Okhaldhunga | Baruneshwor | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Baruneshwor | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-03 | 2017-03-25 | Planning data - National Level
Okhaldhunga | Baruneshwor | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-02 |  | Planning data - National Level
Okhaldhunga | Betini | 3 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30
Okhaldhunga | Betini | 4 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-04-30
Okhaldhunga | Bhussinga | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Bhussinga | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Bhussinga | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Bhussinga | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Bhussinga | 4 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 6 | 6 |  |  | Full construction of house
Okhaldhunga | Bhussinga | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Bhussinga | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Bhussinga | 7 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-23 | 2016-02-26
Okhaldhunga | Bhussinga | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Bhussinga | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19
Okhaldhunga | Bhussinga | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bhussinga | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Bhussinga | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Bigutar | 2 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-02 | 2016-04-30
Okhaldhunga | Chyanam | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Chyanam | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 1 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 1 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 2 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 2 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 3 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 3 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 4 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 4 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 5 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 5 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 6 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 6 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 7 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 7 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 8 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 8 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Fediguth | 9 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fediguth | 9 | HELVETAS |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Fulbari | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 | Event Id-Efsr-2JTI-01-0008/2015
Okhaldhunga | Fulbari | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-19 | Event Id-Efsr-2JTI-01-0002/2015
Okhaldhunga | Fulbari | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-21 | 2016-02-20 | Event Id-Efsr-2JTI-01-0007/2015
Okhaldhunga | Fulbari | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-21 | 2016-02-19
Okhaldhunga | Fulbari | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-19
Okhaldhunga | Fulbari | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2016-03-25 | 2016-02-28
Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-19
Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-20
Okhaldhunga | Fulbari | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20
Okhaldhunga | Gamnangtar | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 5 | 5 | 2016-06-26 | 2016-08-25 | Event id-Efsr-2JTI-01-0006/2016
Okhaldhunga | Gamnangtar | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 7 | 7 | 2016-06-26 | 2016-08-25 | Event id-Efsr-2JTI-01-0003/2016
Okhaldhunga | Gamnangtar | 1 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 2 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 3 | MEDAIR | LCDF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-29
Okhaldhunga | Gamnangtar | 3 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 4 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-04-23
Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0001/2016
Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 4 | 4 | 2016-06-25 | 2016-08-25 | Event id-Efsr-2JTI-01-0002/2016
Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-08-25
Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-26 | 2016-08-25
Okhaldhunga | Gamnangtar | 4 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 5 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-04-23
Okhaldhunga | Gamnangtar | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21
Okhaldhunga | Gamnangtar | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-25 | 2016-08-25
Okhaldhunga | Gamnangtar | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-08-25
Okhaldhunga | Gamnangtar | 5 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 6 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21
Okhaldhunga | Gamnangtar | 7 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 8 | MEDAIR | LCDF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-25
Okhaldhunga | Gamnangtar | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-21
Okhaldhunga | Gamnangtar | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-25 | 2016-08-25
Okhaldhunga | Gamnangtar | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-08-25
Okhaldhunga | Gamnangtar | 8 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-01
Okhaldhunga | Gamnangtar | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21
Okhaldhunga | Gamnangtar | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-26 | 2016-08-25
Okhaldhunga | Gamnangtar | 9 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01
Okhaldhunga | Harkapur | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Harkapur | ALL | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 25 | 2016-05-12 | 2016-05-18 | mason training implemented by TRACE
Okhaldhunga | Harkapur | ALL | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-01 | 2016-06-07 | mason training implemented by TRACE
Okhaldhunga | Harkapur | ALL | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-09 | 2016-06-15 | mason training implemented by TRACE
Okhaldhunga | Harkapur | ALL | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-27 | 2016-07-03 | mason training implemented by TRACE in rampur( Baruneshore VDC) participants were from Prapcha, Harkapur and Baruneshore
Okhaldhunga | Kalikadevi | 1 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 2 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 3 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 4 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 5 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 6 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 7 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 8 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kalikadevi | 9 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | Kaptigaun(Khigikati) | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Kaptigaun(Khigikati) | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Kaptigaun(Khigikati) | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Kaptigaun(Khigikati) | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Kaptigaun(Khigikati) | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Kaptigaun(Khigikati) | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Kaptigaun(Khigikati) | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Katunje | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Katunje | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 1 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 1 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | KhijiChandeshwori | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 2 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 3 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | KhijiChandeshwori | 3 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | KhijiChandeshwori | 3 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 4 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 5 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | KhijiChandeshwori | 5 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | KhijiChandeshwori | 5 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 6 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | KhijiChandeshwori | 6 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | KhijiChandeshwori | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | KhijiChandeshwori | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 8 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house
Okhaldhunga | KhijiChandeshwori | 8 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | KhijiChandeshwori | 8 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | KhijiChandeshwori | 8 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | KhijiChandeshwori | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | KhijiChandeshwori | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Khijifalate | 1 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house
Okhaldhunga | Khijifalate | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0007/2016
Okhaldhunga | Khijifalate | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0005/2016
Okhaldhunga | Khijifalate | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-08-21
Okhaldhunga | Khijifalate | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21
Okhaldhunga | Khijifalate | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21
Okhaldhunga | Khijifalate | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21
Okhaldhunga | Khijifalate | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Khijifalate | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Khijifalate | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 10 | 10 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0004/2016
Okhaldhunga | Khijifalate | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-22 | 2016-08-21
Okhaldhunga | Kuntadevi | 9 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30
Okhaldhunga | Madhavpur | 1 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29
Okhaldhunga | Madhavpur | 3 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29
Okhaldhunga | Madhavpur | 7 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29
Okhaldhunga | Madhavpur | 8 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29
Okhaldhunga | Moli | 8 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30
Okhaldhunga | Mulkharka | 1 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Mulkharka | 1 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 2 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Mulkharka | 2 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 3 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Mulkharka | 3 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 3 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 4 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 4 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 5 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Mulkharka | 5 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 6 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 6 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Mulkharka | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 7 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Mulkharka | 8 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 8 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 8 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Mulkharka | 9 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-22 | 2016-04-26
Okhaldhunga | Mulkharka | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Narmedeshwor | 1 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 1 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 2 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 2 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 3 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 3 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 3 | 3 | 2016-04-29 | 2016-05-03
Okhaldhunga | Narmedeshwor | 3 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 3 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 4 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 4 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 5 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 5 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 5 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 6 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 6 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 7 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 8 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 8 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 8 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-10 | 2016-05-16
Okhaldhunga | Narmedeshwor | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 9 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 6 | 6 | 2016-04-29 | 2016-05-03
Okhaldhunga | Narmedeshwor | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Narmedeshwor | 9 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16
Okhaldhunga | Palapu | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0010/2015
Okhaldhunga | Palapu | 2 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29
Okhaldhunga | Palapu | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 5 | 5 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0005/2015
Okhaldhunga | Palapu | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0006/2015
Okhaldhunga | Palapu | 3 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29
Okhaldhunga | Palapu | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29
Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 8 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29
Okhaldhunga | Palapu | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2015-12-27 | 2016-02-26
Okhaldhunga | Palapu | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Pokali | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0004/2015
Okhaldhunga | Pokali | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19
Okhaldhunga | Pokali | 3 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-24
Okhaldhunga | Pokali | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Building Electrician Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-01-05 | 2016-02-29 | Event id-efcr-35 Phipi-01-0008/2015
Okhaldhunga | Pokali | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0005/2015
Okhaldhunga | Pokali | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19
Okhaldhunga | Pokali | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-05 | 2016-02-29
Okhaldhunga | Pokali | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0003/2016
Okhaldhunga | Pokali | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Pokali | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19
Okhaldhunga | Pokali | 6 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-24
Okhaldhunga | Pokali | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19
Okhaldhunga | Pokali | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-05 | 2016-02-29
Okhaldhunga | Pokali | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Pokali | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12
Okhaldhunga | Pokali | 8 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-24
Okhaldhunga | Pokali | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-12 | 2016-08-12
Okhaldhunga | Pokali | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Prapcha | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-26 | 2017-04-14 | Planning data - National Level
Okhaldhunga | Prapcha | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Prapcha | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-26 | 2017-04-14 | Planning data - National Level
Okhaldhunga | Prapcha | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Prapcha | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-26 | 2017-04-14 | Planning data - National Level
Okhaldhunga | Prapcha | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Prapcha | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Prapcha | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-26 | 2017-04-14 | Planning data - National Level
Okhaldhunga | Prapcha | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Prapcha | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-27 | 2017-04-14 | Planning data - National Level
Okhaldhunga | Prapcha | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Prapcha | ALL | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-18 | 2016-06-24 | mason training implemented by TRACE
Okhaldhunga | Ragani | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0006/2015
Okhaldhunga | Ragani | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 5 | 5 | 2016-06-10 | 2016-08-10 | Event id-efcr-35 Phipi-01-0007/2016
Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-08-10 | Event id-efcr-35 Phipi-01-0004/2016
Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-08-10 | Event id-efcr-35 Phipi-01-0005/2016
Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-24 | 2016-02-19
Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-23
Okhaldhunga | Ragani | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-10 | 2016-08-10
Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-10
Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-23
Okhaldhunga | Ragani | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-10 | Event Id-Efsr-2JTI-01-0001/2015
Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-08-10
Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-10 | 2016-08-10
Okhaldhunga | Ragani | 6 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-23
Okhaldhunga | Ragani | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Ragani | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-08-10
Okhaldhunga | Ragani | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Ragani | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 9 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 2 | 2 |  |  | Full construction of house
Okhaldhunga | Ragani | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | Ragani | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Ragani | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-08-10
Okhaldhunga | Raniban | 1 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 1 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01
Okhaldhunga | Raniban | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 1 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-21 | 2016-05-27
Okhaldhunga | Raniban | 2 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 2 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 3 | 3 | 2016-05-08 | 2016-05-12
Okhaldhunga | Raniban | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 2 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-21 | 2016-05-27
Okhaldhunga | Raniban | 3 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 3 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01
Okhaldhunga | Raniban | 3 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 3 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-21 | 2016-05-27
Okhaldhunga | Raniban | 4 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 4 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01
Okhaldhunga | Raniban | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 4 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-21 | 2016-05-27
Okhaldhunga | Raniban | 5 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 5 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 6 | 6 | 2016-05-08 | 2016-05-12
Okhaldhunga | Raniban | 5 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 5 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-21 | 2016-05-27
Okhaldhunga | Raniban | 6 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 8 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 8 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01
Okhaldhunga | Raniban | 8 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Raniban | 9 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-21 | 2016-05-27
Okhaldhunga | Rawadolu | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Rawadolu | 2 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house
Okhaldhunga | Rawadolu | 2 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-02-22
Okhaldhunga | Rawadolu | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Rawadolu | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0007/2015
Okhaldhunga | Rawadolu | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Rawadolu | 5 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house
Okhaldhunga | Rawadolu | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19
Okhaldhunga | Rawadolu | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Rawadolu | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self
Okhaldhunga | Rawadolu | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self
Okhaldhunga | Shreechaur | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Shreechaur | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Shreechaur | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Shreechaur | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Shreechaur | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Planning data - National Level
Okhaldhunga | Shreechaur | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-02-19 | 2017-04-09 | Planning data - National Level
Okhaldhunga | Shreechaur | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29
Okhaldhunga | Shreechaur | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  | Planning data - National Level
Okhaldhunga | Siddhicharan N.P. | 1 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 2 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 3 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 4 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 5 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 6 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 7 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 8 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 9 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 10 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 11 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-02 | 2016-04-30
Okhaldhunga | Siddhicharan N.P. | 1 & 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-08 | 2016-07-14 | Mason training implemented by TRACE
Okhaldhunga | Siddhicharan N.P. | 1 & 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-18 | 2016-07-24 | mason training implemented by TRACE
Okhaldhunga | Singhadevi | 1 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27
Okhaldhunga | Singhadevi | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0003/2015
Okhaldhunga | Singhadevi | 2 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 4 | 4 | 2016-05-17 | 2016-05-21
Okhaldhunga | Singhadevi | 3 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26
Okhaldhunga | Singhadevi | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 4 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26
Okhaldhunga | Singhadevi | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0009/2015
Okhaldhunga | Singhadevi | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0004/2015
Okhaldhunga | Singhadevi | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 6 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27
Okhaldhunga | Singhadevi | 6 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 5 | 5 | 2016-05-17 | 2016-05-21
Okhaldhunga | Singhadevi | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 7 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27
Okhaldhunga | Singhadevi | 7 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26
Okhaldhunga | Singhadevi | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 8 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26
Okhaldhunga | Singhadevi | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27
Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-27 | 2016-02-26
Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26
Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-23 | 2016-02-25
Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0006/2016
Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-29 | Event id-efcr-35 Phipi-01-0010/2015
Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 5 | 5 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0002/2016
Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0001/2016
Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-23 | 2016-02-25
Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0003/2015
Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-23 | 2016-02-25
Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19
Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-29
Okhaldhunga | Tarkerabari | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Tarkerabari | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19
Okhaldhunga | Tarkerabari | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-29
Okhaldhunga | Tarkerabari | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-29
Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-23 | 2016-02-25
Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 3 | 2 | 2016-01-07 | 2016-02-29
Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12
Okhaldhunga | Tarkerabari | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Tarkerabari | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12
Okhaldhunga | Thoksel | 1 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04
Okhaldhunga | Thoksel | 2 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04
Okhaldhunga | Thoksel | 3 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04
Okhaldhunga | Thoksel | 6 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04
Okhaldhunga | Ubu | 2 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30
Okhaldhunga | Yasam | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0001/2015
Okhaldhunga | Yasam | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0009/2015
Okhaldhunga | Yasam | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 6 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-26
Okhaldhunga | Yasam | 6 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 4 | 4 | 2016-05-28 | 2016-06-01
Okhaldhunga | Yasam | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0002/2015
Okhaldhunga | Yasam | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 6 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Saipu VDC-Ramechhap district | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Okhaldhunga | Yasam | 7 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-26
Okhaldhunga | Yasam | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 8 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 5 | 5 | 2016-05-28 | 2016-06-01
Okhaldhunga | Yasam | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19
Okhaldhunga | Yasam | 9 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-26
Okhaldhunga | Yasam | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-24 | 2016-02-19
Ramechhap | BamtiBhandar | 2 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 31 | 31 | 2016-01-01 | 2016-02-28
Ramechhap | BamtiBhandar | 3 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 18 | 18 | 2016-01-01 | 2016-02-28
Ramechhap | BamtiBhandar | 5 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | BamtiBhandar | 6 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 132 | 132 | 2016-01-01 | 2016-02-28
Ramechhap | BamtiBhandar | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | BamtiBhandar | 8 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | BamtiBhandar |  | GOAL | CDS | DFID | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 1 | 1
Ramechhap | BamtiBhandar |  | GOAL | CDS | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 28 | 28 | 2016-01-01 | 2016-02-28
Ramechhap | Betali | 1 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 1 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 1 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 4 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 4 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 6 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Betali | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Bethan | 4 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhadaure | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Bhadaure | 7 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhirpani | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Bhirpani | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhirpani | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhirpani | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhirpani | 8 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhirpani | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 50 | 50 | 2016-05-01 | 2016-05-25 | CGI Sheets
Ramechhap | Bhirpani |  | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 4 | 0 |  |  | yet to be approved
Ramechhap | Bhirpani |  | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-04-19
Ramechhap | Bhujee | 1 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 1 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 2 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 2 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 3 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 3 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 4 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 4 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 5 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 5 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 6 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bhujee | 6 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 7 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 7 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 8 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13
Ramechhap | Bhujee | 8 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bhujee | 9 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 16 | 16
Ramechhap | Bhujee | 9 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Bijulikot | 1 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 1 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 2 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 2 | MEDAIR | CDS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-28
Ramechhap | Bijulikot | 2 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31
Ramechhap | Bijulikot | 2 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 153 | 41 | 2016-10-15
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-08-25 | 2016-08-31
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 3 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR 50,000 | # of households | Yes | Ongoing | 153 | 144 | 2016-09-19
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | NPR 80,000 | # of households | Yes | Ongoing | 153 | 25 | 2016-11-20
Ramechhap | Bijulikot | 3 | MEDAIR | CDS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | NPR 70,000 | # of households | Yes | Ongoing | 153 | 6 | 2017-01-02
Ramechhap | Bijulikot | 4 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 4 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 5 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 5 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 5 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 6 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 157 | 58 | 2016-10-15
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-08-25 | 2016-08-31
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR 50,000 | # of households | Yes | Ongoing | 157 | 151 | 2016-09-19
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | NPR 80,000 | # of households | Yes | Ongoing | 157 | 42 | 2016-11-20
Ramechhap | Bijulikot | 6 | MEDAIR | CDS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | NPR 70,000 | # of households | Yes | Ongoing | 157 | 1 | 2017-01-02
Ramechhap | Bijulikot | 7 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 7 | MEDAIR | CDS |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-28
Ramechhap | Bijulikot | 7 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 8 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 8 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13
Ramechhap | Bijulikot | 8 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Bijulikot | 9 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 8 | 8 | 2015-01-27 | 2016-02-02
Ramechhap | Bijulikot | 9 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13
Ramechhap | Chanakhu | 2 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Chanakhu | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Chanakhu | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Chanakhu | 7 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Chanakhu | 7 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Chuchure | 1 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 95 | 95 | 2016-01-01 | 2016-02-28
Ramechhap | Chuchure | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 4 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-01-01 | 2016-02-28
Ramechhap | Chuchure | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 5 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-16 | 2016-02-12
Ramechhap | Chuchure | 7 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-01-01 | 2016-02-28
Ramechhap | Chuchure | 8 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 132 | 132 | 2016-01-01 | 2016-02-28
Ramechhap | Chuchure |  | GOAL | CDS | DFID | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 1 | 1
Ramechhap | Chuchure |  | GOAL | CDS | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 225 | 225 | 2016-01-01 | 2016-02-28
Ramechhap | Dadhuwa | 1 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 2 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 2 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 3 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 3 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 4 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 4 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 5 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 5 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 6 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Dadhuwa | 8 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Dadhuwa | 8 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Dimipokhari | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 2 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 3 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 5 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 5 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 5 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-11
Ramechhap | Dimipokhari | 6 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 6 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 7 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 7 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 8 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 8 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-28 | 2016-08-23
Ramechhap | Dimipokhari | 9 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-28 | 2016-08-23
Ramechhap | Doramba | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Doramba | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Doramba | 8 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Doramba |  | HCI | YSP |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 41 | 41 | 2016-03-15 | 2016-04-30
Ramechhap | Duragau | 1 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 5 | 5 | 2016-01-07 | 2016-02-11
Ramechhap | Duragau | 2 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Duragau | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Duragau | 7 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Saipu VDC | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Duragau | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Duragau | 8 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Farpu | 1 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 2 | HELVETAS | CMES | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 2 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 4 | HELVETAS | CMES | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 4 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 5 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 5 | HELVETAS | CMES | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 5 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 5 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 6 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 6 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 7 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 7 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 7 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 8 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 9 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-09 | 2016-08-08
Ramechhap | Farpu | 9 | HELVETAS | CMES | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 9 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-08 | 2016-02-03
Ramechhap | Farpu | 9 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-09 | 2016-08-08
Ramechhap | Gelu | 1 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 1 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 2 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 2 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 6 | 6 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 3 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 12 | 12 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 3 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 4 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 4 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 5 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 5 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 6 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 11 | 11 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 6 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 7 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 19 | 19 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 8 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 8 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gelu | 9 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 3 | 3 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Gelu | 9 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08
Ramechhap | Gothgau | 4 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Saipu VDC | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Gumdel | 1 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Gumdel | 2 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-01-01 | 2016-02-28
Ramechhap | Gumdel | 3 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 98 | 98 | 2016-01-01 | 2016-02-28
Ramechhap | Gumdel | 3 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Gumdel | 4 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 55 | 55 | 2016-01-01 | 2016-02-28
Ramechhap | Gumdel | 6 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 105 | 105 | 2016-01-01 | 2016-02-28
Ramechhap | Gumdel | 7 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-01-01 | 2016-02-28
Ramechhap | Gumdel | 8 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 69 | 69 | 2016-01-01 | 2016-02-28
Ramechhap | Gumdel |  | GOAL | CDS | DFID | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 1 | 1
Ramechhap | Gumdel |  | GOAL | CDS | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 225 | 225 | 2016-01-01 | 2016-02-28
Ramechhap | GunsiBhadaure | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09
Ramechhap | Gunsibhadaure | 3 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | GunsiBhadaure | 3 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-30 | 2016-09-09
Ramechhap | Gunsibhadaure | 4 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | GunsiBhadaure | 4 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 5 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 8 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 9 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-09-09
Ramechhap | GunsiBhadaure | 9 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-30 | 2016-09-09
Ramechhap | Guptesor | 1 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 1 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 2 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 2 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 3 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 3 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 4 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 4 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 5 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 5 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 6 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 6 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 7 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 7 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 8 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9
Ramechhap | Guptesor | 8 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18
Ramechhap | Guptesor | 9 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 11 | 11
Ramechhap | Guptesor | 9 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18
Ramechhap | Hiledevi | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 1 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 1 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 1 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 2 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 2 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 3 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 3 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 4 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 4 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 5 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 5 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 5 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 6 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 6 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 6 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 4 | 4 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 7 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 7 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 7 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Himganga | 8 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 8 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 9 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-02-22
Ramechhap | Himganga | 9 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21
Ramechhap | Himganga | 9 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Khadadevi | 3 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Khadadevi | 6 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-11
Ramechhap | Khadadevi | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 30 | 30 | 2016-05-01 | 2016-05-25 | CGI Sheets
Ramechhap | Khimti | 1 | HELVETAS | CMES | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 1 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 2 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 3 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 3 | HELVETAS | CMES | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 3 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 4 | HELVETAS | CMES | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 4 | HELVETAS | CMES | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 4 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 5 | HELVETAS | CMES | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 5 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 6 | HELVETAS | CMES | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 6 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 7 | HELVETAS | CMES | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 7 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 7 | HELVETAS | CMES | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti | 8 | HELVETAS | CMES | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08
Ramechhap | Khimti |  | HCI | YSP |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 25 | 25 | 2016-03-01 | 2016-03-31
Ramechhap | Khimti |  | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-01-19 | 2016-04-22
Ramechhap | Kubukasthali | 1 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Kubukasthali | 3 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 193 | 193 | 2016-01-01 | 2016-02-28
Ramechhap | Kubukasthali | 4 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 204 | 207 | 2016-01-01 | 2016-02-28
Ramechhap | Kubukasthali | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-11
Ramechhap | Kubukasthali | 8 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Kubukasthali | 9 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Lakhanpur | 2 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 2 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 3 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 3 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 4 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Lakhanpur | 4 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Lakhanpur | 4 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 5 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 5 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 5 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Lakhanpur | 6 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 7 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 8 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15
Ramechhap | Lakhanpur | 8 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-16 | 2016-08-15
Ramechhap | Majuwa | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 25 | 25 | 2016-05-01 | 2016-05-25 | CGI Sheets
Ramechhap | Manthali N.P. | 1 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 97 | 97 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Others | Others | (Please specify in Activity Detail) | Solar installation in the house suppoted by NRCS |  | No | Planned | 200 | 0 | 2017-01-01 | 2017-12-31
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Others | Others | (Please specify in Activity Detail) | Cash grant for toilet construction |  | No | Planned | 200 | 0 | 2017-01-01 | 2017-12-31
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 1 | 0 | 2016-09-20 | 2016-09-27
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 1 | 0 | 2016-10-01 | 2016-10-12 | PASSA will be done on 3 major settlement at Manthali Municipality - 2 with 30 participants in each training
Ramechhap | Manthali N.P. | 2 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 82 | 82 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-01-15 | 2016-04-29
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-31 | 2016-06-06 | 2nd lot training implemented by TRACE
Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-07 | 2016-07-13 | 6th lot training implemented by TRACE
Ramechhap | Manthali N.P. | 3 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 3 | 3 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Manthali N.P. | 3 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 54 | 54 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Manthali N.P. | 4 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 26 | 26 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Manthali N.P. | 5 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 14 | 14 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Manthali N.P. | 6 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 2 | 2 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Manthali N.P. | 6 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 73 | 73 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Manthali N.P. | 7 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 30 | 30 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Manthali N.P. | 7 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 65 | 65 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Manthali N.P. | 8 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 16 | 16 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Manthali N.P. | 13 | HELVETAS | TRACE | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-06-27 | 2016-08-20
Ramechhap | Manthali N.P. | 13 | HELVETAS | TRACE | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 10 | 10 | 2016-06-27 | 2016-08-20
Ramechhap | Manthali N.P. | 13 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 50 | 50 | 2016-06-27 | 2016-08-20
Ramechhap | Manthali N.P. | 14 | HELVETAS | TRACE | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-27 | 2016-08-20
Ramechhap | Manthali N.P. | 14 | HELVETAS | TRACE | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 4 | 4 | 2016-06-27 | 2016-08-20
Ramechhap | Manthali N.P. | 14 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-06-27 | 2016-08-20
Ramechhap | Manthali N.P. | 15 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 37 | 37 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Manthali N.P. | 15 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 14 | 14 | 2016-03-02 | 2016-03-08
Ramechhap | Manthali N.P. | 16 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 26 | 26 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training
Ramechhap | Manthali N.P. | 16 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 6 | 6 | 2016-03-02 | 2016-03-08
Ramechhap | Manthali N.P. |  | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 20 | 0 |  |  | yet to be approved
Ramechhap | Namadi | 1 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 1 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 101 | 101 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Namadi | 1 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 1 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 1 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 2 | HI | CESVI | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 56 | 56 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Namadi | 2 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 2 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Namadi | 4 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 127 | 127 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Namadi | 6 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 6 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 6 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 7 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 7 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 1 | 1 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries
Ramechhap | Namadi | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 7 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 8 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 8 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 8 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 9 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-24
Ramechhap | Namadi | 9 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Namadi | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-16 | 2016-02-12
Ramechhap | Pakarbas |  | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 5 | 0 |  |  | yet to be approved
Ramechhap | Phulasi | 1 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 1 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 2 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 3 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 4 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 5 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 5 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 6 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 7 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Phulasi | 7 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-06 | 2016-02-20
Ramechhap | Pritee | 2 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 152 | 152 | 2016-01-01 | 2016-02-28
Ramechhap | Pritee | 3 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Pritee | 4 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Pritee | 5 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-01-01 | 2016-02-28
Ramechhap | Pritee | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Pritee | 6 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Pritee | 7 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 142 | 142 | 2016-01-01 | 2016-02-28
Ramechhap | Puranagau | 1 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 138 | 138 | 2016-03-17 | 2016-03-22
Ramechhap | Puranagau | 9 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 122 | 122 | 2016-03-17 | 2016-03-22 | distribution conduceted in beneificiaries Village
Ramechhap | Puranagau |  | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-04-20
Ramechhap | Rakathum | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 25 | 25 | 2016-05-01 | 2016-05-25 | CGI Sheets
Ramechhap | Rakathum |  | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 4 | 0 |  |  | yet to be approved
Ramechhap | Rampur | 2 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Rampur | 3 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Rampur | 4 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Others | Others | (Please specify in Activity Detail) | Solar installation in the house suppoted by NRCS |  | No | Planned | 700 | 0 | 2017-01-01 | 2017-12-31
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Others | Others | (Please specify in Activity Detail) | Cash grant for toilet construction |  | No | Planned | 700 | 0 | 2017-01-01 | 2017-12-31
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 9 | 0 | 2016-10-14 | 2016-11-10 | PASSA will be done on 9 wards of Rampur with 30 participant in each training
Ramechhap | Rampur |  | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-01-22 | 2016-04-25
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-09 | 2016-06-15 | 3rd lot training implemented by TRACE
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-09 | 2016-05-15 | 1st lot training implemented by TRACE
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-17 | 2016-06-23 | 4th lot training implemented by TRACE
Ramechhap | Rampur |  | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-27 | 2016-07-03 | 5th lot training implemented by TRACE
Ramechhap | Rasanalu | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-28 | 2016-09-09
Ramechhap | Rasanalu | 2 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-09-09
Ramechhap | Rasanalu | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-28 | 2016-09-09
Ramechhap | Rasanalu | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-09-09
Ramechhap | Rasanalu | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-28 | 2016-09-09
Ramechhap | Rasanalu | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-09-09
Ramechhap | Rasanalu | 6 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 1 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 1 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 1 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 2 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 2 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 3 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 4 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 4 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 4 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 5 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 5 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 6 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 7 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 7 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 7 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 7 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 7 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 8 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 8 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 8 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 8 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 6 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 8 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11
Ramechhap | Saipu | 9 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu | 9 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 9 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-11-08 | 2016-12-28
Ramechhap | Saipu | 9 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-27 | 2016-05-18
Ramechhap | Saipu |  | KFS |  | KFS | Others | Others | (Please specify in Activity Detail) | Plan is for two secondary school located in ward no. 7 and 8 respectively and health post which represents all the wards |  | Yes | Planned | 2 | 0
Ramechhap | Saipu |  | HCI | YSP |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 41 | 41 | 2016-03-01 | 2016-03-31
Ramechhap | Saipu |  | KFS |  | KFS | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | No | Planned | 590 | 0
Ramechhap | Sanghutar | 1 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 1 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 2 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 2 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 3 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 3 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 4 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 4 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 5 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 5 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 6 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 6 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 7 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 7 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 8 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 8 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-03-06
Ramechhap | Sanghutar | 9 | MEDAIR | CDS |  | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29
Ramechhap | Sanghutar | 9 | MEDAIR | CDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06
Ramechhap | Those | 1 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 133 | 133 | 2016-01-01 | 2016-02-28
Ramechhap | Those | 2 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 88 | 88 | 2016-01-01 | 2016-02-28
Ramechhap | Those | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-16 | 2016-08-04
Ramechhap | Those | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-16 | 2016-08-04
Ramechhap | Those | 3 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 118 | 118 | 2016-01-01 | 2016-02-28
Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-16 | 2016-08-04
Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 7 | 7 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-16 | 2016-08-04
Ramechhap | Those | 4 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 6 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-04
Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-04
Ramechhap | Those | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 8 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12
Ramechhap | Those | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2015-12-16 | 2016-02-12
Ramechhap | Tilpung | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 2 | 2 | 2017-01-27
Ramechhap | Tilpung | 1 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-01-27
Ramechhap | Tilpung | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-01-27
Ramechhap | Tilpung | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 1 | 1 | 2017-01-27
Ramechhap | Tilpung | 4 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-01-27
Ramechhap | Tilpung | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-01-27
Ramechhap | Tilpung | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 1 | 1 | 2017-01-27
Ramechhap | Tilpung | 5 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-27
Ramechhap | Tilpung | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 5 | 5 | 2017-01-27
Ramechhap | Tilpung | 7 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 1 | 1 | 2017-01-27
Ramechhap | Tilpung | 7 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-01-27
Ramechhap | Tilpung | 7 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-01-27
Ramechhap | Tilpung | 8 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 4 | 4 | 2017-01-27
Ramechhap | Tilpung | 8 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-01-27
Ramechhap | Tilpung | 8 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 11 | 11 | 2017-01-27
Ramechhap | Tilpung | 9 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 1 | 1 | 2017-01-27
Ramechhap | Tilpung | 9 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-01-27
Ramechhap | Tilpung | 9 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-01-27
Ramechhap | Tilpung |  | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-01-21 | 2016-04-18
Ramechhap | Tokarpur | 1 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Tokarpur | 3 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 3 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 4 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 5 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-06 | 2016-02-20
Ramechhap | Tokarpur | 5 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 6 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Tokarpur | 6 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 6 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 7 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20
Ramechhap | Tokarpur | 7 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 7 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 8 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Tokarpur | 8 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 8 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-22 | 2016-08-21
Ramechhap | Tokarpur | 9 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20
Ramechhap | Tokarpur | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 50 | 50 | 2016-05-01 | 2016-05-25 | CGI Sheets
Rasuwa | Bhorle | 1 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | No | Planned | 2 | 0 | 2016-12-30
Rasuwa | Bhorle | 1 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-12-30
Rasuwa | Bhorle | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Ongoing | 2 | 0 | 2016-12-23
Rasuwa | Bhorle | 2 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-12-23
Rasuwa | Bhorle | 3 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | No | Planned | 2 | 0 | 2016-12-23
Rasuwa | Bhorle | 3 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-12-23
Rasuwa | Bhorle | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-30
Rasuwa | Bhorle | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-30
Rasuwa | Bhorle | 5 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18
Rasuwa | Bhorle | 5 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18
Rasuwa | Bhorle | 6 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 87 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Bhorle | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18
Rasuwa | Bhorle | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18
Rasuwa | Bhorle | 8 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 5 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Ongoing | 2 | 1 | 2017-01-21
Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-21
Rasuwa | Bhorle | ALL | DEPROCS | DEPROCS | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 1178 | 0
Rasuwa | Bhorle | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 1 | 1
Rasuwa | Bhorle | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-02 | 2016-07-08
Rasuwa | Bridhim | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28
Rasuwa | Bridhim | ALL | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 12 | 0
Rasuwa | Bridhim | ALL | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 60 | 0
Rasuwa | Chilime | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-06-28
Rasuwa | Chilime | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22
Rasuwa | Chilime | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-16 | 2016-05-22
Rasuwa | Chilime | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-22 | 2016-06-28
Rasuwa | Chilime | ALL | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 12 | 0
Rasuwa | Chilime | ALL | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 60 | 0
Rasuwa | Chilime | ALL | LWF | MANEKOR | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Ongoing | 90 | 90 | 2015-09-10 | 2016-05-10
Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training
Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-11 | 2016-02-04 | s
Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-28 | 6-Dce-16
Rasuwa | Dandagoun | 1 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Brick masonary in cement mortar (10*10 Room size) | # of constructions | Yes | Ongoing | 2 | 0 | 2017-01-07
Rasuwa | Dandagoun | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-07
Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-19 | Furniture making Training
Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04
Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-11-29 | 6-Dce-16
Rasuwa | Dandagoun | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16
Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training
Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04
Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-11-30 | 6-Dce-16
Rasuwa | Dandagoun | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16
Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training
Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04
Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 6-Dce-16
Rasuwa | Dandagoun | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .12*12 And 12*12Room Size | # of constructions | Yes | Ongoing | 2 | 1 | 2017-01-07
Rasuwa | Dandagoun | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-07
Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training
Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04
Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-02 | 6-Dce-16
Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-25 | 2016-05-19 | Furniture making Training
Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-11 | 2016-02-04
Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-03 | 6-Dce-16
Rasuwa | Dandagoun | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .10*10 And 12*12Room Size | # of constructions | Yes | Ongoing | 4 | 1 | 2017-01-06
Rasuwa | Dandagoun | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-01-06
Rasuwa | Dandagoun | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-11 | 2016-02-04
Rasuwa | Dandagoun | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10
Rasuwa | Dandagoun | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-04 | 6-Dce-16
Rasuwa | Dandagoun | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .10*10 Room Size | # of constructions | Yes | Ongoing | 2 | 0 | 2017-01-06
Rasuwa | Dandagoun | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-06
Rasuwa | Dandagoun | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16
Rasuwa | Dandagoun | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-05 | 6-Dce-16
Rasuwa | Dandagoun | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-16
Rasuwa | Dandagoun | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-06 | 6-Dce-16
Rasuwa | Dandagoun | ALL | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 654 | 654
Rasuwa | Dandagoun | ALL | LDF | LDF | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 433 | 0
Rasuwa | Dandagoun | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-08 | 2016-05-14
Rasuwa | Dhunche | 1 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 13 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 49 | 49 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 49 | 49 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window
Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 49 | 49 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-24 | 2016-02-28
Rasuwa | Dhunche | 2 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 13 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 4 | 4 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-24 | 2016-02-28
Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 12 | 12 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 37 | 37 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 37 | 37 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 37 | 37 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-02-24 | 2016-02-28
Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-22 | 2016-03-28
Rasuwa | Dhunche | 4 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 38 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 10 | 10 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 40 | 40 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 40 | 40 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 40 | 40 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-02-24 | 2016-02-28
Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-22 | 2016-03-28
Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 51 | 51 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 51 | 51 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window
Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 51 | 51 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 2 | 2 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-22 | 2016-03-28
Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 39 | 39 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 39 | 39 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 39 | 39 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-22 | 2016-03-28
Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 5 | 5 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 62 | 62 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 62 | 62 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 62 | 62 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-22 | 2016-03-28
Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30
Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-22 | 2016-03-28
Rasuwa | Dhunche | ALL | LDF | LDF | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 369 | 0
Rasuwa | Dhunche | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 54 | 54
Rasuwa | Gatlang | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 69 | 69 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 69 | 69 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window
Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 69 | 69 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | 2 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22
Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 48 | 48 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 48 | 48 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 48 | 48 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 7 | 7 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 33 | 33 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 33 | 33 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 33 | 33 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 36 | 36 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 36 | 36 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 36 | 36 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22
Rasuwa | Gatlang | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 57 | 57 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 57 | 57 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 57 | 57 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | 6 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 4 | 4 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 93 | 93 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 93 | 93 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 93 | 93 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | 7 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22
Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 58 | 58 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 58 | 58 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 58 | 58 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-22 | 2016-03-28
Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Technical Assistance | Door-to-door technical assistance | Continuous | 1 sub engineer ,1 SM | # of households | Yes | Ongoing | 79 | 56 | 2016-08-01 | 2017-10-30
Rasuwa | Gatlang | 7 | LWF | MANEKOR | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 18 | 2017-01-22 | 2017-01-28
Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 56 | 52 | 2016-08-01 | 2017-10-30
Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 15 | 4 | 2016-08-01 | 2017-10-30
Rasuwa | Gatlang | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22
Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 2 | 2 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 61 | 61 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 61 | 61 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 61 | 61 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-22 | 2016-03-28
Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Technical Assistance | Door-to-door technical assistance | Continuous | 1 sub engineer , 1 SM | # of households | Yes | Ongoing | 71 | 45 | 2016-08-01 | 2017-10-30
Rasuwa | Gatlang | 8 | LWF | MANEKOR | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 12 | 2017-01-22 | 2017-01-28
Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 16 | 6 | 2016-08-01 | 2017-10-30
Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 45 | 45 | 2016-08-01 | 2017-10-30
Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 25 | 25 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 25 | 25 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window
Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 25 | 25 | 2015-08-01 | 2016-04-30
Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-15 | 2016-01-19
Rasuwa | Gatlang | ALL | DEPROCS | DEPROCS | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 399 | 0
Rasuwa | Gatlang | ALL | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 10 | 0
Rasuwa | Gatlang | ALL | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 50 | 0
Rasuwa | Gatlang | ALL | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 588 | 588 | 2015-06-01 | 2015-10-25
Rasuwa | Goljung | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22
Rasuwa | Goljung | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22
Rasuwa | Goljung | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Goljung | 6 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22
Rasuwa | Goljung | 7 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22
Rasuwa | Goljung | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22
Rasuwa | Goljung | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28
Rasuwa | Goljung | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22
Rasuwa | Goljung | ALL | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 10 | 0
Rasuwa | Goljung | ALL | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 50 | 0
Rasuwa | Goljung | ALL | LWF | MANEKOR | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 90 | 90 | 2015-09-01 | 2016-10-25
Rasuwa | Goljung | ALL | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 355 | 355 | 2015-06-01 | 2015-10-25
Rasuwa | Goljung | ALL | PPY | PPY | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 286 | 0
Rasuwa | Haku | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Haku | 1 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 6 | 0
Rasuwa | Haku | 1 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 30 | 0
Rasuwa | Haku | 2 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Haku | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-04-01 | 2016-06-05
Rasuwa | Haku | 2 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08
Rasuwa | Haku | 2 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2015-09-02 | 2016-04-30
Rasuwa | Haku | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28
Rasuwa | Haku | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 11 | 11 | 2016-04-01 | 2016-06-05
Rasuwa | Haku | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-06-02 | 2016-06-08
Rasuwa | Haku | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-04-01 | 2016-06-05
Rasuwa | Haku | 5 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-02 | 2016-06-08
Rasuwa | Haku | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2016-04-01 | 2016-06-05
Rasuwa | Haku | 6 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-02 | 2016-06-08
Rasuwa | Haku | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-04-01 | 2016-06-05
Rasuwa | Haku | 7 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-02 | 2016-06-08
Rasuwa | Haku | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-10 | 2016-06-16
Rasuwa | Haku | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Haku | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Electrician | CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2016-04-15 | 2016-07-15
Rasuwa | Haku | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 11 | 11 | 2015-09-02 | 2016-04-30
Rasuwa | Haku | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-10 | 2016-06-16
Rasuwa | Haku | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Haku | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Electrician | CTEVT | # of trainees | Yes | Completed | 4 | 4 | 2016-04-15 | 2016-07-15
Rasuwa | Haku | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 10 | 10 | 2015-09-02 | 2016-04-30
Rasuwa | Haku | ALL | DEPROCS | DEPROCS | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 483 | 0
Rasuwa | Haku | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 19 | 19
Rasuwa | Haku | All | OM-N | OM-N | OM-N | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Transportation of Building Materials | # of constructions | No | Planned | 752 | 0 | 2017-03-01 | 2018-12-31
Rasuwa | Haku | All | OM-N | OM-N | OM-N | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | No | Planned | 60 | 0 | 2017-03-01 | 2018-12-31
Rasuwa | Haku | All | OM-N | OM-N | OM-N | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 6 | 0 | 2017-03-01 | 2018-12-31
Rasuwa | Haku | All | OM-N | OM-N | OM-N | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 60 | 0 | 2017-03-01 | 2018-12-31
Rasuwa | Jibjibe(Nilkantha) | 2 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 13 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Jibjibe(Nilkantha) | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 189 | 189
Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 96 | 96
Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 75
Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 13 | 13 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 12 | 12
Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 77 | 77
Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 28 | 28
Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 100
Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 5 | 5 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 101 | 101
Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 22 | 22
Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 17 | 17
Rasuwa | Jibjibe(Nilkantha) | 5 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | No | Ongoing | 2 | 0 | 2016-12-14
Rasuwa | Jibjibe(Nilkantha) | 5 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-11-29
Rasuwa | Jibjibe(Nilkantha) | 5 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 169 | 169
Rasuwa | Jibjibe(Nilkantha) | 5 | Lumanti | Lumanti | CORDAID | Technical Assistance | Demonstration Construction | House | Brick masonary in cement mortar | # of constructions | Yes | Ongoing | 1 | 0 | 2016-04-02 | 2017-12-02 | A Stock Piling building is planned to construct one in VDC
Rasuwa | Jibjibe(Nilkantha) | 5 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 7 | 7 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | No | Completed | 2 | 2 | 2016-11-29 | 2017-01-12
Rasuwa | Jibjibe(Nilkantha) | 6 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-12-14
Rasuwa | Jibjibe(Nilkantha) | 6 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 95 | 95
Rasuwa | Jibjibe(Nilkantha) | 6 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 9 | 9 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | (1.1) Brick Masonry in Cement Mortar. 10'x 10'Room Size | # of constructions | No | Ongoing | 2 | 0 | 2016-01-13
Rasuwa | Jibjibe(Nilkantha) | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-13
Rasuwa | Jibjibe(Nilkantha) | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 183 | 183
Rasuwa | Jibjibe(Nilkantha) | 7 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 13 | 13 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-14
Rasuwa | Jibjibe(Nilkantha) | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-14
Rasuwa | Jibjibe(Nilkantha) | 8 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 129 | 129
Rasuwa | Jibjibe(Nilkantha) | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-14
Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-25
Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-25
Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-14
Rasuwa | Jibjibe(Nilkantha) | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2015-09-02 | 2016-04-30
Rasuwa | Jibjibe(Nilkantha) | ALL | DEPROCS | DEPROCS | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 954 | 0
Rasuwa | Jibjibe(Nilkantha) | ALL | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 1 | 1 |  |  | Hoarding Board size 8'X10' with 17 module design is installed outside VDC office
Rasuwa | Jibjibe(Nilkantha) | All | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 8 | 8 | 2015-12-01 | 2016-01-02
Rasuwa | Jibjibe(Nilkantha) | ALL | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-04 | 2016-08-10 | Kalika Himalaya School, Kalikasthan, Dhaibung
Rasuwa | Laharepouwa | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16
Rasuwa | Laharepouwa | 1 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 204 | 204
Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 193 | 193
Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar | # of constructions | Yes | Completed | 1 | 1 | 2016-04-01 | 2017-12-01 | A Stock Piling building is planned to construct one in VDC
Rasuwa | Laharepouwa | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16
Rasuwa | Laharepouwa | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Laharepouwa | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 164 | 164
Rasuwa | Laharepouwa | 4 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 88 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Laharepouwa | 4 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 17 | 17 | 2015-09-15 | 2016-04-30
Rasuwa | Laharepouwa | 6 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2015-09-15 | 2016-04-30
Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 99
Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2015-09-15 | 2016-04-30
Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 99 | 99
Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 10 | 10
Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 32 | 32
Rasuwa | Laharepouwa | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16
Rasuwa | Laharepouwa | 8 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 183 | 183
Rasuwa | Laharepouwa | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Electrician | CTEVT | # of trainees | Yes | Completed | 9 | 9 | 2016-04-15 | 2016-07-15
Rasuwa | Laharepouwa | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 9 | 9 | 2015-09-15 | 2016-04-30
Rasuwa | Laharepouwa | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 109 | 109
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 95 | 95
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Electrician | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-04-15 | 2016-07-15
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 12 | 12 | 2015-09-15 | 2016-04-30
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 41 | 41
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 5 | 5
Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 14 | 14
Rasuwa | Laharepouwa | ALL | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 12 | 0
Rasuwa | Laharepouwa | ALL | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 60 | 0
Rasuwa | Laharepouwa | All | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 1 | 1 |  |  | Hoarding Board size 8'X10' with 17 module design is installed outside VDC office
Rasuwa | Laharepouwa | All | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 8 | 8 | 2015-12-01 | 2016-01-01
Rasuwa | Laharepouwa | ALL | NAF | NAF | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 1120 | 0
Rasuwa | Laharepouwa | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 6 | 6
Rasuwa | Laharepouwa | ALL | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-11 | 2016-08-17
Rasuwa | Langtang | 2 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (4 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31
Rasuwa | Langtang | 2 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (2 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31
Rasuwa | Langtang | 3 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (4 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31
Rasuwa | Langtang | 4 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (4 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31
Rasuwa | Langtang | 7 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (2 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31
Rasuwa | Langtang | 7 | SP | SP | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 14 | 0
Rasuwa | Langtang | All | OM-N | OM-N | OM-N | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Transportation of Building Materials | # of constructions | Yes | Ongoing | 110 | 110 | 2016-08-01 | 2017-06-30
Rasuwa | Ramche | 1 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 28 | 15 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 1 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | 1 | LWF | BATAS | DEC-ii | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Ongoing | 150 | 0 | 2016-03-15 | 2017-03-15
Rasuwa | Ramche | 2 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 58 | 25 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 2 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 10 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Brick masonary in cement mortar (16.6*11) One room) + Varanda | # of constructions | Yes | Completed | 2 | 2 | 2017-01-14
Rasuwa | Ramche | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar (9*9 Room Size) | # of constructions | No | Ongoing | 2 | 0 | 2017-01-16
Rasuwa | Ramche | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-14
Rasuwa | Ramche | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-16
Rasuwa | Ramche | 2 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | 3 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 96 | 20 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 3 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 50 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 3 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-16
Rasuwa | Ramche | 3 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2017-01-16
Rasuwa | Ramche | 4 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 88 | 18 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 4 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 20 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28
Rasuwa | Ramche | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-16
Rasuwa | Ramche | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-16
Rasuwa | Ramche | 4 | LWF | BATAS | DEC-ii | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15
Rasuwa | Ramche | 5 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 72 | 22 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 5 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 70 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 5 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | 6 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 66 | 12 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 6 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 20 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 6 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | 7 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 52 | 20 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 7 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 20 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 7 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | 8 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 81 | 20 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 8 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 20 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 8 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | 9 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Ongoing | 101 | 35 | 2016-08-01 | 2017-04-30
Rasuwa | Ramche | 9 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 75 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Ramche | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .10*10 And 10*10 Room Size | # of constructions | Yes | Ongoing | 4 | 0 | 2017-01-16
Rasuwa | Ramche | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-01-16
Rasuwa | Ramche | 9 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-05 | 2016-08-11
Rasuwa | Ramche | ALL | NAF | NAF | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 446 | 0
Rasuwa | Saramthali | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-10 | 2017-01-21
Rasuwa | Saramthali | 2 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2016-12-10
Rasuwa | Saramthali | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-25
Rasuwa | Saramthali | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-25
Rasuwa | Saramthali | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | No | Completed | 2 | 2 | 2016-12-03 | 2017-01-20
Rasuwa | Saramthali | 6 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-03
Rasuwa | Saramthali | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Ongoing | 2 | 0
Rasuwa | Saramthali | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0
Rasuwa | Saramthali | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18
Rasuwa | Saramthali | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18
Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18
Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Ongoing | 2 | 0 | 2016-12-25
Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18
Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-12-25
Rasuwa | Saramthali | ALL | LDF | LDF | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 775 | 0
Rasuwa | Saramthali | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 1 | 1
Rasuwa | Saramthali | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-14 | 2016-06-20
Rasuwa | Saramthali | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-22 | 2016-06-28
Rasuwa | Syafru | 1 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 6-Dce-15
Rasuwa | Syafru | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 30 | 30 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 1 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 30 | 30 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 30 | 30 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 6-Dce-15
Rasuwa | Syafru | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-27 | 6-Dce-15
Rasuwa | Syafru | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 56 | 56 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 3 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 56 | 56 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 56 | 56 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-11-27 | 6-Dce-15
Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window
Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 8 | 8 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2015-11-27 | 6-Dce-15
Rasuwa | Syafru | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 35 | 35 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 5 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 35 | 35 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 35 | 35 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 6 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 11 | 11 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 6-Dce-15
Rasuwa | Syafru | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 15 | 15 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 6 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 15 | 15 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 15 | 15 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 22 | 22 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 7 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 22 | 22 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 22 | 22 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 8 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 9 | ACF | LACCOS | ACF | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar . | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-08-30 | Stone Masonary in Mud Mortar .10'x10' Room Size
Rasuwa | syafru | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-06-28
Rasuwa | Syafru | 9 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-11 | 2016-02-04
Rasuwa | Syafru | 9 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-17 | 2016-02-10
Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 108 | 108 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 108 | 108 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period
Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window
Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 108 | 108 | 2015-08-01 | 2016-04-30
Rasuwa | Syafru | ALL | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 620 | 620 | 2016-04-15 | 2016-04-25
Rasuwa | Syafru | ALL | GIZ | GOAL | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 656 | 656
Rasuwa | Syafru | ALL | NAF | NAF | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 390 | 0
Rasuwa | Syafru | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 24 | 24
Rasuwa | Thulogoun | 1 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 9 | 9 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 2 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 10 | 10 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 3 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 7 | 7 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 4 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 4 | 4 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Thulogoun | 5 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 4 | 4 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 6 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Ongoing | 26 | 0 | 2016-09-01 | 2017-06-30
Rasuwa | Thulogoun | 6 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 6 | 6 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 7 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 5 | 5 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | 9 | SAHAS | SAHAS | SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 5 | 5 | 2016-11-23 | 2016-11-28
Rasuwa | Thulogoun | ALL | DEPROCS | DEPROCS | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 333 | 0
Rasuwa | Thulogoun | ALL | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-08-23 | 2016-08-30 | 20 participants from Thulogaun and 10 from Dandagaun, conducted by TRACE Nepal
Rasuwa | Thulogoun | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-08 | 2016-05-14
Rasuwa | Thulogoun | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-13 | 2016-06-19
Rasuwa | Thuman | ALL | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 12 | 0
Rasuwa | Thuman | ALL | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 60 | 0
Rasuwa | Thuman | ALL | PPY | PPY | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 232 | 0
Rasuwa | Yarsa | 1 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 2 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Yarsa | 4 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Yarsa | 5 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 6 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28
Rasuwa | Yarsa | 6 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Cash support for labour (One lakh three thousand twenty eight ) | # of constructions | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Technical Assistance | Community orientation on toilet construction | 2-3 sessions | Engineer, sub-engineer , SM | # of participants | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Technical Assistance | Household reconstruction orientation | 2-3 sessions | Engineer, sub-engineer , SM | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Bricks,Sand,Aggregate,Reinforcement Bar,Cement,Truss,CGI Sheet & Plain Sheet,Shovel, Axe Peak, Layout Thread, Measuring Tape, Tagari | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, sub-engineer , Two trained masion , SM | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Masonry equipments | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-ii | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 8 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 0
Rasuwa | Yarsa | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10
Rasuwa | Yarsa | 9 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2017-03-15
Rasuwa | Yarsa | ALL | DEPROCS | DEPROCS | PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Ongoing | 855 | 0
Rasuwa | Yarsa | ALL | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Planned | 12 | 0
Rasuwa | Yarsa | ALL | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | No | Planned | 60 | 0
Rasuwa | Yarsa | ALL | LWF | MANEKOR | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 91 | 91 | 2015-09-01 | 2016-05-10
Rasuwa | Yarsa | ALL | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 609 | 609 | 2015-09-01 | 2015-10-25
Rasuwa | Yarsa | All | NRCS | NRCS | ARC | Others | Others | (Please specify in Activity Detail) | CGI distribution to Windstrom victim Families |  | Yes | Completed | 1 | 1
Rasuwa | Yarsa | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-28 | 2016-06-03
Rasuwa | Yarsa | All | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-05 | 2016-06-11
Sindhuli | Amale | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Amale | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Amale |  | CW |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0
Sindhuli | Bahuntilpung | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bahuntilpung | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bahuntilpung | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Baseshwor | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Baseshwor | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bastipur | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bastipur | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhadrakali | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhadrakali | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Bhimeshwor | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Bhimeshwor | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BhuwaneshoriGwaltar | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BhuwaneshoriGwaltar | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | BitijorBagaiya | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | BitijorBagaiya |  | CW |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0
Sindhuli | Dadiguranshe | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dadiguranshe | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dadiguranshe | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dudbhanjyang | 1 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 9 | 9 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 1 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 1 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 20 | 2017-03-03 | 2017-03-11
Sindhuli | Dudbhanjyang | 2 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 9 | 3 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 2 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0
Sindhuli | Dudbhanjyang | 2 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7 | 0
Sindhuli | Dudbhanjyang | 3 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 9 | 0
Sindhuli | Dudbhanjyang | 3 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dudbhanjyang | 3 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7 | 0
Sindhuli | Dudbhanjyang | 4 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 9 | 0
Sindhuli | Dudbhanjyang | 4 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dudbhanjyang | 4 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dudbhanjyang | 5 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 9 | 1 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 5 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dudbhanjyang | 5 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7 | 0
Sindhuli | Dudbhanjyang | 6 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 9 | 5 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 6 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 6 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dudbhanjyang | 7 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 9 | 2 | 2017-03-22 | 2017-05-09
Sindhuli | Dudbhanjyang | 7 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Dudbhanjyang | 7 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7 | 0
Sindhuli | Dudbhanjyang | 8 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 8 | 5 | 2017-02-24 | 2017-04-13
Sindhuli | Dudbhanjyang | 8 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-02-24 | 2017-04-13
Sindhuli | Dudbhanjyang | 8 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Dudbhanjyang | 9 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 9 | 15 | 2017-02-24 | 2017-04-13
Sindhuli | Dudbhanjyang | 9 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-02-24 | 2017-04-13
Sindhuli | Dudbhanjyang | 9 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7 | 0
Sindhuli | HariharpurGadhi | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | HariharpurGadhi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | HariharpurGadhi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Jalkanya | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Jalkanya | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | JhangajholiRalmata | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | JhangajholiRalmata | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | JhangajholiRalmata | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 16 | 0
Sindhuli | JhangajholiRalmata | 1 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | JhangajholiRalmata | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 9
Sindhuli | JhangajholiRalmata | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 15 | 0
Sindhuli | JhangajholiRalmata | 2 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2
Sindhuli | JhangajholiRalmata | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 1 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 3 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 16 | 18 | 2017-03-04 | 2017-04-28
Sindhuli | JhangajholiRalmata | 3 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-03-04 | 2017-04-28
Sindhuli | JhangajholiRalmata | 3 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 3 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 4 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 15
Sindhuli | JhangajholiRalmata | 4 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2
Sindhuli | JhangajholiRalmata | 4 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 1 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 5 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 16 | 2 | 2017-03-04 | 2017-04-28
Sindhuli | JhangajholiRalmata | 5 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-03-04 | 2017-04-28
Sindhuli | JhangajholiRalmata | 5 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 8 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 15
Sindhuli | JhangajholiRalmata | 6 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2
Sindhuli | JhangajholiRalmata | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 2 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 16
Sindhuli | JhangajholiRalmata | 7 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | JhangajholiRalmata | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 18 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 15
Sindhuli | JhangajholiRalmata | 8 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2
Sindhuli | JhangajholiRalmata | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 2 | 2017-03-04 | 2017-03-12
Sindhuli | JhangajholiRalmata | 9 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 16
Sindhuli | JhangajholiRalmata | 9 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2
Sindhuli | JhangajholiRalmata | 9 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 5 | 2017-03-04 | 2017-03-12
Sindhuli | Kalpabrishykha | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kalpabrishykha | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kalpabrishykha | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kamalami N.P. | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Sindhuli | Kamalami N.P. | 1 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 3 | 2017-03-06 | 2017-03-14
Sindhuli | Kamalami N.P. | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0
Sindhuli | Kamalami N.P. | 2 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 13 | 2017-03-06 | 2017-03-14
Sindhuli | Kamalami N.P. | 3 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 3 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 3 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 8
Sindhuli | Kamalami N.P. | 4 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 4 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 4 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 8
Sindhuli | Kamalami N.P. | 5 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 20 | 2017-03-08 | 2017-05-04
Sindhuli | Kamalami N.P. | 5 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 2 | 2017-03-08 | 2017-05-04
Sindhuli | Kamalami N.P. | 5 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7
Sindhuli | Kamalami N.P. | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 12 | 2017-02-28 | 2017-04-27
Sindhuli | Kamalami N.P. | 6 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-02-28 | 2017-04-27
Sindhuli | Kamalami N.P. | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 4 | 2017-03-06 | 2017-03-14
Sindhuli | Kamalami N.P. | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 8 | 2017-02-28 | 2017-04-27
Sindhuli | Kamalami N.P. | 7 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-02-28 | 2017-04-27
Sindhuli | Kamalami N.P. | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 8
Sindhuli | Kamalami N.P. | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 8 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7
Sindhuli | Kamalami N.P. | 9 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 9 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 9 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 20 | 2017-03-07 | 2017-03-15
Sindhuli | Kamalami N.P. | 10 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 10 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 10 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 8
Sindhuli | Kamalami N.P. | 11 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 11 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 11 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 8
Sindhuli | Kamalami N.P. | 12 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 12 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 12 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 7
Sindhuli | Kamalami N.P. | 13 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 13 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 13 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 6 | 2017-03-07 | 2017-03-15
Sindhuli | Kamalami N.P. | 14 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2017-03-14 | 2017-05-01
Sindhuli | Kamalami N.P. | 14 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 14 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 1 | 2017-03-07 | 2017-03-15
Sindhuli | Kamalami N.P. | 15 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10
Sindhuli | Kamalami N.P. | 15 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 15 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 8
Sindhuli | Kamalami N.P. | 16 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 20 | 2017-03-14 | 2017-05-01
Sindhuli | Kamalami N.P. | 16 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 16 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 4 | 2017-03-07 | 2017-03-15
Sindhuli | Kamalami N.P. | 17 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 12 | 2017-03-23 | 2017-05-11
Sindhuli | Kamalami N.P. | 17 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 17 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 8 | 2017-03-07 | 2017-03-15
Sindhuli | Kamalami N.P. | 18 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 7 | 2017-03-14 | 2017-05-01
Sindhuli | Kamalami N.P. | 18 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1
Sindhuli | Kamalami N.P. | 18 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 1 | 2017-03-07 | 2017-03-15
Sindhuli | Kapilakot | 1 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 22 | 20 | 2017-02-26 | 2017-04-15
Sindhuli | Kapilakot | 1 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-02-26 | 2017-04-15
Sindhuli | Kapilakot | 1 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 13 | 0
Sindhuli | Kapilakot | 2 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 22 | 20 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 2 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 2 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 14 | 20 | 2017-03-17 | 2017-03-25
Sindhuli | Kapilakot | 3 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 22 | 20 | 2017-02-26 | 2017-04-15
Sindhuli | Kapilakot | 3 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-02-26 | 2017-04-15
Sindhuli | Kapilakot | 3 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Ongoing | 14 | 20 | 2017-03-27 | 2017-04-04
Sindhuli | Kapilakot | 4 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 22 | 20 | 2017-02-28 | 2017-04-27
Sindhuli | Kapilakot | 4 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-02-28 | 2017-04-27
Sindhuli | Kapilakot | 4 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 14 | 0
Sindhuli | Kapilakot | 5 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 23 | 20 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 5 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 2 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 5 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 20 | 2017-02-23 | 2017-03-03
Sindhuli | Kapilakot | 6 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 23 | 14 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 6 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 1 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 6 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 13 | 0
Sindhuli | Kapilakot | 7 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 22 | 6 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 7 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 1 | 2017-02-23 | 2017-04-12
Sindhuli | Kapilakot | 7 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 13 | 0
Sindhuli | Kapilakot | 8 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 22 | 0
Sindhuli | Kapilakot | 8 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 3 | 0
Sindhuli | Kapilakot | 8 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 13 | 0
Sindhuli | Kapilakot | 9 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 22 | 0
Sindhuli | Kapilakot | 9 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 3 | 0
Sindhuli | Kapilakot | 9 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Planned | 13 | 0
Sindhuli | Khangsang | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Khangsang | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Khangsang | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kholagaun | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kholagaun | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | KusesworDumja | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | KusesworDumja | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Kyaneshwor | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Kyaneshwor | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevdada | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevdada | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahadevsthan | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahadevsthan | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Mahendrajhayadi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Mahendrajhayadi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | Majhuwa | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | Majhuwa | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Majhuwa | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Majhuwa | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | PuranoJhangajholi | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | PuranoJhangajholi | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | PuranoJhangajholi | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | PuranoJhangajholi | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ranichuri | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ranichuri | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratanchura | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratanchura | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Ratnawati | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Ratnawati | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Santeswori(Rampur) | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Santeswori(Rampur) |  | CW |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0
Sindhuli | Sitalpati | 9 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | Sitalpati | 9 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 9 | 0
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Planned | 9 | 0
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-05-18
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-29 | 2016-06-04
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-05 | 2016-06-11
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-12 | 2016-06-18
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-20 | 2016-06-26
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-05-18
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-29 | 2016-06-04
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-05 | 2016-06-11
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-12 | 2016-06-18
Sindhuli | Sitalpati | All | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-20 | 2016-06-26
Sindhuli | Solpathana | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Solpathana | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Solpathana | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | SunamPokhari | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | SunamPokhari | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tamajor | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tamajor | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tinkanya | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tinkanya | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhuli | Tosramkhola | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhuli | Tosramkhola | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0
Sindhupalchok | Atarpur | 1 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 31 | 31 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 1 | SABAL | TUKI | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 75 | 40 | 2016-07-25 | 2016-12-31 | 7 days Training
Sindhupalchok | Atarpur | 2 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 17 | 17 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 3 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 20 | 20 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 4 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 21 | 21 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 5 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 17 | 17 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 6 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 7 | 7 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 6 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) | As per Sagun 51 was planned but only 49 distribute due to lack of Government EQ Card but she advised covert 51 into 49 |  | Yes | Completed | 49 | 49 | 2016-01-07 | 2015-01-30
Sindhupalchok | Atarpur | 7 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 22 | 22 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 7 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 47 | 47 | 2016-01-05 | 2015-01-30
Sindhupalchok | Atarpur | 8 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 40 | 40 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | 9 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 50 | 50 | 2017-07-10 | 2017-07-10
Sindhupalchok | Atarpur | All | CA | CA | CA | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 113 | 113 | 2016-01-10 | 2016-04-30
Sindhupalchok | Atarpur | All | CA | CA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 113 | 113 | 2016-01-10 | 2016-06-15
Sindhupalchok | Atarpur | All | CA | CA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2016-01-10 | 2016-08-30
Sindhupalchok | Atarpur | All | CA | CA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 50 | 68 | 2016-01-10 | 2016-06-15
Sindhupalchok | Atarpur |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-07 |  | 50 days Training
Sindhupalchok | Atarpur |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 44
Sindhupalchok | Badegau | 1 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Badegau | 1 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Badegau | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 123
Sindhupalchok | Badegau | 2 | SABAL | TUKI | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 75 | 40 | 2016-07-25 | 2016-12-31 | 50 days Training
Sindhupalchok | Badegau | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Badegau | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Badegau | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 82
Sindhupalchok | Badegau | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Badegau | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Badegau | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Badegau | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-03-02 | 2016-03-04
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 |  |  | Originally planned for 5-11 August but it was postponed.
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-05-18
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-06-01 | 2016-06-07
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-06-09 | 2016-06-15
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-17 | 2016-06-23
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-25 | 2016-07-01
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-04 | 2016-07-10
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-12 | 2016-07-18
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-20 | 2016-07-26
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-28 | 2016-08-03
Sindhupalchok | Badegau | All | NRCS | NRCS | NRC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 6 | 6 | 2015-09-01 | 2016-01-10
Sindhupalchok | Badegau |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 262 | 262 | 2016-01-16 | 2016-01-22
Sindhupalchok | Badegau |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-16 | 2016-01-22 | school for shelter and environment (SSE) Please add
Sindhupalchok | Bahrabise | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 79 | 79 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-01-20
Sindhupalchok | Bahrabise | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 14 | 14 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Barhadevi CBRC
Sindhupalchok | Bahrabise | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Khursanibari CBRC
Sindhupalchok | Bahrabise | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-01-27
Sindhupalchok | Bahrabise | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ward no 2 CBRC
Sindhupalchok | Bahrabise | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-01-27
Sindhupalchok | Bahrabise | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16)
Sindhupalchok | Bahrabise | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Bageshwori CBRC
Sindhupalchok | Bahrabise | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Harabari CBRC
Sindhupalchok | Bahrabise | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 25 | 25 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 14 | 14 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Okhreni CBRC
Sindhupalchok | Bahrabise | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 66 | 66 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 7 | 7 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 71 | 71 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 14 | 14 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 5 | 2017-02-14
Sindhupalchok | Bahrabise | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-11 | 2016-09-28
Sindhupalchok | Bahrabise | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-09-22 | 2016-09-30
Sindhupalchok | Bahrabise | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17)
Sindhupalchok | Bahrabise | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-02-26
Sindhupalchok | Bahrabise |  | JICA |  | JICA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2015-12-01 | 2016-12-31
Sindhupalchok | Bahrabise |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Bahrabise |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 40 | 10 | 2016-11-01 | 2016-12-15
Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 19 | 2016-07-06 | 2016-07-06
Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 10 | 2016-08-10 | 2016-11-15
Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-10
Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 21 | 10 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-24 | 2 events
Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 25 | 2016-07-08 | 2016-07-08
Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 19
Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-06-10
Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 24 | 19 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-12-02
Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 28 | 2016-08-02 | 2016-08-02
Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 31
Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 30 | 31 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 43 | 2016-07-20 | 2016-07-20
Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 3
Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-06-10
Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 62 | 45 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-05 | 2017-04-15
Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 83 | 2016-06-05 | 2016-06-05
Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 0
Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 138 | 0 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 72 | 2016-06-05 | 2016-06-05
Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 0
Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-06-10
Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 150 | 0 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 23 | 2016-06-04 | 2016-06-04
Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 25
Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-10
Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 31 | 25 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 79 | 2016-06-04 | 2016-06-04
Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 63
Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-06-10
Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 90 | 63 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-10 | 2016-06-24
Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 95 | 2016-06-04 | 2016-06-04
Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 0
Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-10
Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 0 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-24
Sindhupalchok | Baramchi | 1 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 2 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 3 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 4 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27
Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27
Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 75 | 75 | 2016-07-01 | 2017-10-30
Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 75 | 6 | 2016-07-01 | 2017-10-30
Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 385 | 300 | 2016-10-10 | 2017-10-01
Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 75 | 2016-10-10
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 335 | 285 | 2016-10-10 | 2017-10-01
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 67 | 67 | 2016-10-10
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 67 | 67 | 2016-07-01 | 2017-10-30
Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 67 | 10 | 2016-07-01 | 2017-10-30
Sindhupalchok | Baramchi | 7 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 8 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | 9 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Baramchi | All | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | Ward wise orientation on BBS | # of participants | Yes | Completed | 600 | 604 | 2016-11-01 | 2016-12-30
Sindhupalchok | Baramchi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Carpenter | 7 days carpentary training | # of trainees | Yes | Completed | 20 | 25 | 2016-03-01
Sindhupalchok | Baramchi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 1 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Baramchi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-01-15
Sindhupalchok | Baramchi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 20 | 2016-09-28 | 2016-10-04
Sindhupalchok | Baramchi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 19 | 2016-12-01 | 2017-01-15
Sindhupalchok | Baramchi |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | Baramchi |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 60
Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 76 | 2016-06-10 | 2016-06-10
Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 26 | 2016-08-01 | 2017-12-15
Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-05-28
Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 71 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 50 | 2016-07-06 | 2016-07-06
Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 14
Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-28
Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 35 | 14 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 74 | 2016-06-04 | 2016-06-04
Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 65
Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 13 | 13 | 2016-05-28
Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 81 | 65 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 36 | 2016-06-04 | 2016-06-04
Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 32
Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-28
Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 39 | 32 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 36 | 2016-07-05 | 2016-07-05
Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 27
Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-28
Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 51 | 27 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-13 | 2017-04-30
Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 26 | 2016-07-04 | 2016-07-04
Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 18
Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-05-28
Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 18 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 70 | 2016-07-11 | 2016-07-11
Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 77
Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-28
Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 78 | 77 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 53 | 2016-07-09 | 2016-07-09
Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 67
Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-28
Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 81 | 67 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-28 | 2016-06-25
Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 48 | 2016-07-13 | 2016-07-13
Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 52
Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 52 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Baruwa |  | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0
Sindhupalchok | Batase | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | PanchaKanya Devi
Sindhupalchok | Batase | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Sera Guru Ganesh
Sindhupalchok | Batase | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 13 | 13 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 59 | 59 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | BK tole CBRC
Sindhupalchok | Batase | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-21 | Chitaeswori CBRC
Sindhupalchok | Batase | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-22 | Shree Ganesh Kharitar CBRC
Sindhupalchok | Batase | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-19 | Kalika Devi CBRC
Sindhupalchok | Batase | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Baluwa Setidevi
Sindhupalchok | Batase | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 7 | 7 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 59 | 59 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-08 | 2017-02-09
Sindhupalchok | Batase | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | GairiGaun CBRC
Sindhupalchok | Batase | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Bhalayakharka CBRC
Sindhupalchok | Batase | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 6 | 2017-02-07 | 2017-02-09
Sindhupalchok | Batase | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-16 | Kitini CBRC
Sindhupalchok | Batase | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 7 | 7 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 11 | 2017-02-07 | 2017-02-07
Sindhupalchok | Batase | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Bhagau CBRC
Sindhupalchok | Batase | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-20 | Gaurati CBRC
Sindhupalchok | Batase | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17)
Sindhupalchok | Batase | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 72 | 72 | 2016-09-26 | 2016-10-03
Sindhupalchok | Batase | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-01-06 | 2017-01-06
Sindhupalchok | Batase | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-17 | Jangali Kali Devi CBRC
Sindhupalchok | Batase | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-18 | Dhaukhani VBRC
Sindhupalchok | Batase |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 82 | 2015-12-01 | 2016-12-31
Sindhupalchok | Batase |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 234 | 234 | 2016-05-24 | 2016-05-30
Sindhupalchok | Batase |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2016-05-24 | 2016-05-30 | school for shelter and environment (SSE) Please add
Sindhupalchok | Batase |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 31
Sindhupalchok | Batase |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40
Sindhupalchok | Batase |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 55
Sindhupalchok | Bhimtar | 9 | WOREC-N | WOREC-N | AEI | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Planned | 54 | 0 | 2016-08-04 | 2018-12-31
Sindhupalchok | Bhimtar |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2017-02-01 |  | 50 days Training
Sindhupalchok | Bhotasipa | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 14 | 14 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Sipa Bikas CBRC
Sindhupalchok | Bhotasipa | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 5 | 2017-01-18
Sindhupalchok | Bhotasipa | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 5 | 2017-01-18
Sindhupalchok | Bhotasipa | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 62
Sindhupalchok | Bhotasipa | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Garigau Lama tole CBRC
Sindhupalchok | Bhotasipa | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34
Sindhupalchok | Bhotasipa | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Batsala Devi Tindhara CBRC
Sindhupalchok | Bhotasipa | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 3 | SABAL | TUKI | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 75 | 53 | 2016-06-16 | 2016-12-31 | 7 days Training
Sindhupalchok | Bhotasipa | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Bhotasipa | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Bhotasipa | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 39
Sindhupalchok | Bhotasipa | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Kalika Devi CBRC
Sindhupalchok | Bhotasipa | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 80
Sindhupalchok | Bhotasipa | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 1 | 1 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Batteshwori CBRC
Sindhupalchok | Bhotasipa | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 90 | 90 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 90 | 90 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Jwalamukhi CBRC
Sindhupalchok | Bhotasipa | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Bhotasipa | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Bhotasipa | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 33
Sindhupalchok | Bhotasipa | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Chandeswori CBRC
Sindhupalchok | Bhotasipa | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 102
Sindhupalchok | Bhotasipa | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Dandagau CBRC
Sindhupalchok | Bhotasipa | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Bhotasipa | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Bhotasipa | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17)
Sindhupalchok | Bhotasipa | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-04 | 2017-02-04
Sindhupalchok | Bhotasipa | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Kali devi CBRC
Sindhupalchok | Bhotasipa | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16
Sindhupalchok | Bhotasipa | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Bhotasipa | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Sindhupalchok | Bhotasipa | 8 and 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Aksehshor CBRC
Sindhupalchok | Bhotasipa |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 60 | 2015-12-01 | 2016-12-31
Sindhupalchok | Bhotasipa |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 60 | 2015-12-01 | 2016-12-31
Sindhupalchok | Bhotasipa |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 231 | 231 | 2016-05-12 | 2016-05-18
Sindhupalchok | Bhotasipa |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-05-18 | school for shelter and environment (SSE) Please add
Sindhupalchok | Bhotechaur | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 9 | 9 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16)
Sindhupalchok | Bhotechaur | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 3 | 2017-02-14
Sindhupalchok | Bhotechaur | 1 | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 50 | 0 |  |  | Date planning to fixed
Sindhupalchok | Bhotechaur | 1 | WVIN |  | ADH | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 252 | 252 | 2016-01-07 | 2016-01-07
Sindhupalchok | Bhotechaur | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 19 | 19 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16)
Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Thulapaata CBRC
Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Mausamtole Toridada CBRC
Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Chapabot-thapatole CBRC
Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Bhumistan jhakritol CBRC
Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Phusretole-Poudelthok CBRC
Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Chisapani Dandathok CBRC
Sindhupalchok | Bhotechaur | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-02-13 | 2017-02-13
Sindhupalchok | Bhotechaur | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 39 | 39 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 5 | 2017-02-14
Sindhupalchok | Bhotechaur | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 1 | 1 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16)
Sindhupalchok | Bhotechaur | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Dandagaun Pipalbot CBRC
Sindhupalchok | Bhotechaur | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-13 | 2017-02-13
Sindhupalchok | Bhotechaur | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 28 | 28 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 18 | 2017-02-08
Sindhupalchok | Bhotechaur | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Dihi-Pipalbot
Sindhupalchok | Bhotechaur | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 18 | 2017-02-08
Sindhupalchok | Bhotechaur | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 14 | 14 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16)
Sindhupalchok | Bhotechaur | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Nibugaun
Sindhupalchok | Bhotechaur | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-13 | 2017-02-13
Sindhupalchok | Bhotechaur | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 3 | 3 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16)
Sindhupalchok | Bhotechaur | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Suyachap CBRC
Sindhupalchok | Bhotechaur | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-13 | 2017-02-13
Sindhupalchok | Bhotechaur | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 43 | 43 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-07
Sindhupalchok | Bhotechaur | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16)
Sindhupalchok | Bhotechaur | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Kabra Bot CBRC
Sindhupalchok | Bhotechaur | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Manakamana CBRC
Sindhupalchok | Bhotechaur | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-13 | 2017-02-13
Sindhupalchok | Bhotechaur | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 5 | 2017-02-15
Sindhupalchok | Bhotechaur | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 1 | 1 | 2016-12-21 | 2016-12-27
Sindhupalchok | Bhotechaur | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Jalpadevi CBRC
Sindhupalchok | Bhotechaur | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-12-21 | 2016-12-27
Sindhupalchok | Bhotechaur | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Tapachuli CBRC
Sindhupalchok | Bhotechaur | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-13 | 2017-02-13
Sindhupalchok | Bhotechaur | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-09-25 | 2016-10-04
Sindhupalchok | Bhotechaur |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 84 | 2015-12-01 | 2016-12-31
Sindhupalchok | BhoteNamlang |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 150 | 2016-05-20 | 2016-05-27
Sindhupalchok | BhoteNamlang |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-20 | 2016-05-27
Sindhupalchok | Chautara N.P. | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 178 | 178 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 2 | 2017-02-11
Sindhupalchok | Chautara N.P. | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2016-12-23 | 2016-12-23
Sindhupalchok | Chautara N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Dakshinkali Tole CBRC
Sindhupalchok | Chautara N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Pragatishil tole CBRC
Sindhupalchok | Chautara N.P. | 1 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 11
Sindhupalchok | Chautara N.P. | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 46
Sindhupalchok | Chautara N.P. | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 177 | 177 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2016-12-24 | 2016-12-24
Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Bhirkuna-Makhlo Gau CBRC
Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Setidevi CBRC
Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Shree Mahadev CBRC
Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Shree Bageswori CBRC
Sindhupalchok | Chautara N.P. | 2 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-26 | 2016-09-13
Sindhupalchok | Chautara N.P. | 2 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-10-30
Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 116
Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 86
Sindhupalchok | Chautara N.P. | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 154 | 154 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 1 | 2017-02-11
Sindhupalchok | Chautara N.P. | 3 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | Brick masonry with cement mortar technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-20 | 2016-12-31
Sindhupalchok | Chautara N.P. | 3 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Ongoing | 1 | 0 | 2016-11-20 | 2017-01-31
Sindhupalchok | Chautara N.P. | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 168 | 168 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 1 | 2017-02-11
Sindhupalchok | Chautara N.P. | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2016-12-23 | 2016-12-23
Sindhupalchok | Chautara N.P. | 4 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Chautara N.P. | 4 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Chautara N.P. | 4 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 17
Sindhupalchok | Chautara N.P. | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 138 | 138 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2016-12-24 | 2016-12-24
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Chature CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Ganeshthan CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Bashpati CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-16 | Chaugule CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Deurali CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Simle CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Lama tole Chaap CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | SauneGhaire CBRC
Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Charchare CBRC
Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 59
Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 61
Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 65
Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 26
Sindhupalchok | Chautara N.P. | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 190 | 190 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 2 | 2017-02-06
Sindhupalchok | Chautara N.P. | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2016-12-24 | 2016-12-24
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Taalchaur CBRC
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Saahu Tole CBRC
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | MajhTole CBRC
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Nepaltole CBRC
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Simpani Pallo Tole CBRC
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Simpani Tallo Tole CBRC
Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Markendanda CBRC
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 45
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 42
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 45
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 42
Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 29
Sindhupalchok | Chautara N.P. | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 154 | 154 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 1 | 2017-02-11
Sindhupalchok | Chautara N.P. | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 28 | 28 | 2016-12-25 | 2016-12-25
Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-16 | GhaleGau CBRC
Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Gairigau CBRC
Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-11 | Hungdrung kalidevi CBRC
Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Bagbazzar CBRC
Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Jugal CBRC
Sindhupalchok | Chautara N.P. | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-13 | 2016-03-19 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 283 | 283 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2016-12-24 | 2016-12-24
Sindhupalchok | Chautara N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Kalleri CBRC
Sindhupalchok | Chautara N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Arubote CBRC
Sindhupalchok | Chautara N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Arrubote CBRC
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.6 Melchaur | # of households | Yes | Completed | 200 | 200 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.6 Chaulagain Tol | # of households | Yes | Completed | 20 | 20 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.8 Bisauna Dada | # of households | Yes | Completed | 38 | 38 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.8 Tallo Arubote | # of households | Yes | Completed | 70 | 70 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-06-15 | 2015-11-30 | Model houses are in old Sanosirubari VDC, now in Chautara N.P
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2015-06-15 | 2015-11-30 | 7 days training
Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 17 | 17 | 2015-06-15 | 2015-11-30 | 50 days Training
Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 73
Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 18
Sindhupalchok | Chautara N.P. | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2015-12-18 | 2015-12-23 | TCN/ERTech, Batch dates combined
Sindhupalchok | Chautara N.P. | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 125 | 125 | 2016-10-19 | 2016-12-14
Sindhupalchok | Chautara N.P. | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 5 | 2017-02-13
Sindhupalchok | Chautara N.P. | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 47 | 47 | 2016-12-21 | 2016-12-21 | Added sanosiruwari in ward no 9
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Bhulbhule Danda CBRC
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Arrubote CBRC
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | MaleDanda CBRC
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-16 | Maguwa CBRC
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Jyadi CBRC
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Neupane Tole CBRC
Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Pauwa CBRC
Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Ferro Cement Tank(18cum) at ward no.5 Nepane Gaun | # of households | Yes | Completed | 135 | 135 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Ferro Cement Tank(10cum) at ward no.5 Jhyandi | # of households | Yes | Completed | 25 | 25 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Lay Poles & Transformer for Lift Project at ward no.9 Pauwa | # of households | Yes | Completed | 160 | 160 | 2016-06-05 | 2016-11-30
Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 6 | 6 | 2015-06-15 | 2015-11-30 | Model houses are in old Sanosirubari VDC, now in Chautara N.P
Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 43 | 43 | 2015-06-15 | 2015-11-30 | 7 days training
Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 43 | 43 | 2015-06-15 | 2015-11-30
Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 34
Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 41
Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 43
Sindhupalchok | Chautara N.P. | 3,7 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 21
Sindhupalchok | Chautara N.P. | ALL | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-02-28 | 2016-03-07
Sindhupalchok | Chautara N.P. |  | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1456 | 1456 | 2016-05-30 | 2016-06-03 | 10 Key Messages
Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 240 | 120 | 2015-12-01 | 2016-12-31
Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-02-28 | 2016-03-07
Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 32 | 32 | 2016-02-28 | 2016-03-07
Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 33 | 33 | 2016-02-28 | 2016-03-07
Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 35 | 35 | 2016-02-28 | 2016-03-07
Sindhupalchok | Chautara N.P. |  | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 405 | 405 | 2015-06-15 | 2015-11-30
Sindhupalchok | Chautara N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 1 | # of trainees | Yes | Completed | 30 | 31 | 2016-09-21 | 2016-09-25
Sindhupalchok | Chautara N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 2 | # of trainees | Yes | Completed | 30 | 31 | 2016-09-26 | 2016-09-30
Sindhupalchok | Chautara N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 3 | # of trainees | Yes | Completed | 30 | 31 | 2016-10-01 | 2016-10-05
Sindhupalchok | Chautara N.P. |  | UNDP | GENESIS | GENESIS | Others | Others | (Please specify in Activity Detail) | Preparation of Risk Sensitive Land Use Planning for Choutara Municipality |  | Yes | Planned | 0 | 0 | 2016-04-20 | 2016-11-10
Sindhupalchok | Chautara N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 32
Sindhupalchok | Chautara N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 47
Sindhupalchok | Chautara N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 110
Sindhupalchok | Choukati | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 116
Sindhupalchok | Choukati | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 5 | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 30 | 0 |  |  | Date planning to fixed
Sindhupalchok | Choukati | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-24 | 2016-06-30
Sindhupalchok | Choukati |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 104 | 104 | 2016-10-01 |  | In clusterwise planning phase
Sindhupalchok | Choukati |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | Dhuyang | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 100
Sindhupalchok | Dhuyang | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 1141 | 0 | 2017-04-15
Sindhupalchok | Dhuyang | All | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30
Sindhupalchok | Dhuyang |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 | 2017-04-15
Sindhupalchok | Dhuyang |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-11 |  | 50 days Training
Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 97 | 2016-06-05 | 2016-06-05
Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 60 | 2016-08-08 | 2016-12-15
Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-12
Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 127 | 60 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 29 | 29 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-08-26 | Dubachaur Ward 1 CBRC
Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 77 | 2016-06-05 | 2016-06-05
Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 28
Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-12
Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 28 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-11-16
Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 7 | 2017-02-08
Sindhupalchok | Dubachour | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-09-18 | Dubachaur Ward 2 CBRC
Sindhupalchok | Dubachour | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 70 | 2016-07-06 | 2016-07-06
Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 30
Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-12
Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 211 | 30 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-03 | 2017-04-30
Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-09
Sindhupalchok | Dubachour | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-09-08 | Dubachaur Ward 3 CBRC
Sindhupalchok | Dubachour | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 32
Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 141 | 2016-07-31 | 2016-07-31
Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 52
Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-12
Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 171 | 87 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-17 | Dubachaur Ward 4 CBRC
Sindhupalchok | Dubachour | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 138 | 2016-07-07 | 2016-07-07
Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 26
Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2016-06-12
Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 203 | 26 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 5 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 5 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 11 | 11 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 5 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-08
Sindhupalchok | Dubachour | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-20 | Dubachaur Ward 5 CBRC
Sindhupalchok | Dubachour | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 156 | 2016-08-01 | 2016-08-01
Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 0
Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 14 | 14 | 2016-06-12
Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 247 | 61 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 4 | 4 | 2016-05-19 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Dubachour | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-21 | Dubachaur Ward 6 CBRC
Sindhupalchok | Dubachour | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 6 | SABAL | TUKI | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 75 | 20 | 2016-06-01 | 2016-12-31 | 50 days Training
Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 123 | 2016-06-08 | 2016-06-08
Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 30
Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2016-06-12
Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 165 | 65 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-04 | Dubachaur Ward 7 CBRC
Sindhupalchok | Dubachour | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 105 | 2016-06-19 | 2016-06-19
Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 78
Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-06-12
Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 204 | 112 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 19 | 2017-02-06
Sindhupalchok | Dubachour | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-24 | Dubachaur Ward 8 CBRC
Sindhupalchok | Dubachour | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 233 | 2016-06-10 | 2016-06-10
Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 0
Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-06-12
Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1 | 1 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-06-26
Sindhupalchok | Dubachour | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 80 | 80 | 2016-11-21 | 2016-12-04
Sindhupalchok | Dubachour | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 9 | 2017-02-07
Sindhupalchok | Dubachour | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-11 | 2017-02-11
Sindhupalchok | Dubachour | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-24 | Dubachaur Ward 9 CBRC
Sindhupalchok | Dubachour | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-16 | 2016-04-22
Sindhupalchok | Dubachour | 1,2,4,5,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 177 | 56 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Dubachour | 1,2,4,5,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 177 | 17 | 2016-05-19 | 2016-11-25
Sindhupalchok | Dubachour |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 83 | 2016-04-01 | 2020-12-31
Sindhupalchok | Dubachour |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 62
Sindhupalchok | Fulpingdandagau | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 39 | 39 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 15 | 15 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | Model house | # of constructions |  | Completed | 1 | 1 | 2016-03-01 | 2017-01-25
Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 15 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 47 | 47 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 13 | 13 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 13 | 13 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 17 | 17 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 17 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 53 | 53 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 11 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-23 | Panchakanya CBRC
Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 8 | 8 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 8 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 19 | 19 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 18 | 18 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 18 | 18 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DEC-II | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 100 | 2017-08-01
Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 15 | 15 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 15 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Setidevi CBRC
Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25
Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 14 | 14 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 14 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 54 | 54 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 5 | 2017-01-31
Sindhupalchok | Fulpingdandagau | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-22 | Jyamire CBRC
Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 10 | 10 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 10 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 29
Sindhupalchok | Fulpingdandagau | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-01 | Barpipal CBRC
Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 9 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-23 | 2016-09-11 | completed in 2 different group in different time
Sindhupalchok | Fulpingdandagau | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-09-25 | 2016-10-03
Sindhupalchok | Fulpingdandagau | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-02-23
Sindhupalchok | Fulpingdandagau | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-02 | Kapileshwor CBRC
Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30
Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  | Donor - DFID/DEC-II
Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 11 | 0 | 2017-02-09
Sindhupalchok | Fulpingdandagau | All | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 0 | 42 | 2017-02-21
Sindhupalchok | Fulpingdandagau | All | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 25 | 0 | 2017-04-15
Sindhupalchok | Fulpingdandagau |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Fulpingdandagau |  | SCI | TUKI | DEC-II | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Ongoing | 3 | 3 | 2016-03-01 | 2017-03-30
Sindhupalchok | Fulpingkatti |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition |  | Yes | Completed | 24 | 24 | 2015-09-01 | 2015-09-30
Sindhupalchok | Fulpingkatti |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 9 | 0
Sindhupalchok | Fulpingkatti |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-05 |  | 50 days Training
Sindhupalchok | Fulpingkot | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 25
Sindhupalchok | Fulpingkot | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 28 | 28 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 61
Sindhupalchok | Fulpingkot | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40
Sindhupalchok | Fulpingkot | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-15 | 2016-09-21
Sindhupalchok | Fulpingkot | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-12-07 | 2016-12-12
Sindhupalchok | Fulpingkot | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-21 | 2017-02-21
Sindhupalchok | Fulpingkot |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Gati | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 108 | 108 | 2016-03-09 | 2016-03-09
Sindhupalchok | Gati | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Kukhure CBRC
Sindhupalchok | Gati | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Khagadal CBRC
Sindhupalchok | Gati | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 118 | 118 | 2016-03-10 | 2016-03-10
Sindhupalchok | Gati | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 118 | 118 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-03
Sindhupalchok | Gati | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Panchkanya CBRC
Sindhupalchok | Gati | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-03-11 | 2016-03-11
Sindhupalchok | Gati | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 68 | 68 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-06
Sindhupalchok | Gati | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Setidevi CBRC
Sindhupalchok | Gati | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 133 | 133 | 2016-03-12 | 2016-03-12
Sindhupalchok | Gati | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 133 | 133 | 2016-03-31 | 2016-03-31 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Sundakali Setidevi CBRC
Sindhupalchok | Gati | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 80 | 80 | 2016-03-13 | 2016-03-13
Sindhupalchok | Gati | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 80 | 80 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-16 | 2017-01-22
Sindhupalchok | Gati | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Namuna CBRC
Sindhupalchok | Gati | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 79 | 79 | 2016-03-14 | 2016-03-14
Sindhupalchok | Gati | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 79 | 79 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 9 | 9 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Balhit CBRC
Sindhupalchok | Gati | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 164 | 164 | 2016-03-15 | 2016-03-15
Sindhupalchok | Gati | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 164 | 164 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Shree Gorakhnath Setidevi CBRC
Sindhupalchok | Gati | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 162
Sindhupalchok | Gati | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 58 | 58 | 2016-03-17 | 2016-03-17
Sindhupalchok | Gati | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 58 | 58 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 9 | 9 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Dandakateri CBRC
Sindhupalchok | Gati | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 114 | 114 | 2016-03-19 | 2016-03-19
Sindhupalchok | Gati | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 114 | 114 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Gati | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 13 | 13 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17)
Sindhupalchok | Gati | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 33 | 33 | 2016-11-21 | 2016-12-05
Sindhupalchok | Gati | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-27 | 2017-02-27
Sindhupalchok | Gati | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-01 | Bhansar CBRC
Sindhupalchok | Gati | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-01 | Dhaneshwor CBRC
Sindhupalchok | Gati |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Gati |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition |  | Yes | Completed | 54 | 54 | 2015-09-01 | 2015-09-30
Sindhupalchok | Gati |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 9 | 0
Sindhupalchok | Gati |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 103
Sindhupalchok | Ghorthali | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 5 | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Reconstruction Support for School constructing 2 rooms for library |  | Yes | Ongoing | 1 | 1
Sindhupalchok | Ghorthali | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Ghorthali | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 592 | 0 | 2017-04-15
Sindhupalchok | Ghorthali |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 | 2017-04-15
Sindhupalchok | Ghuskun | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-01-30
Sindhupalchok | Ghuskun | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Chhemadevi CBRC
Sindhupalchok | Ghuskun | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 17 | 2017-02-07
Sindhupalchok | Ghuskun | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Saat Kanya CBRC
Sindhupalchok | Ghuskun | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Kabhre CBRC
Sindhupalchok | Ghuskun | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-05 | Tallogaun CBRC
Sindhupalchok | Ghuskun | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Mathillogaun CBRC
Sindhupalchok | Ghuskun | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Faparchaur CBRC
Sindhupalchok | Ghuskun | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 5 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 3 | 2017-02-14
Sindhupalchok | Ghuskun | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Urjaa CBRC
Sindhupalchok | Ghuskun | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-13 | 2016-09-19
Sindhupalchok | Ghuskun | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-02-19
Sindhupalchok | Ghuskun | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 55 | 55 | 2016-11-15 | 2016-12-04
Sindhupalchok | Ghuskun | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-01-31
Sindhupalchok | Ghuskun | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Siddhikali CBRC
Sindhupalchok | Ghuskun | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Siddhikali CBRC
Sindhupalchok | Ghuskun |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 12 | 12 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 14 | 14
Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 14 | 9 | 2017-02-08
Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11
Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 11 | 11 | 2017-02-08 | 2017-03-03
Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 13 | 13
Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 13 | 9 | 2017-02-08
Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 7 | 7
Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 8 | 3 | 2017-02-08
Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11
Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 10 | 3 | 2017-03-03
Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 17 | 17
Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 17 | 4 | 2017-02-08
Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 13 | 13
Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 13 | 3 | 2017-03-03
Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 2 | 2 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 10 | 10
Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 10 | 3 | 2017-02-08
Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 4 | 4
Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 4 | 4 | 2017-02-08 | 2017-03-03
Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 100 | 2017-08-01
Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Ongoing | 2 | 1 | 2016-03-01 | 2017-03-30
Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Training | Vocational training | New masons (50 days OJT CTEVT) | 40 days mason training of CTEVT curriculum | # of trainees | Yes | Ongoing | 11 | 10 | 2017-02-21
Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of episodes | Yes | Ongoing | 3 | 3 | 2016-03-01 | 2017-03-30
Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9
Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 9 | 3 | 2017-02-08
Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 5 | 5
Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 5 | 0 | 2017-02-08
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 100 | 2017-08-01
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 12 | 12
Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 12 | 6 | 2017-02-08
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11
Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 11 | 3 | 2017-02-08
Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9
Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 9 | 5 | 2017-02-08
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 12 | 12
Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 12 | 6 | 2017-02-08
Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9
Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 9 | 1 | 2017-02-08
Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09
Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 33 | 33
Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 33 | 22 | 2017-02-08
Sindhupalchok | Gumba | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 5 | 5 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba | 9 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-12 | 2016-05-18
Sindhupalchok | Gumba |  | SCI | TUKI | DEC-II | Training | Vocational training | New masons (50 days OJT CTEVT) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Ongoing | 10 | 8 | 2017-02-21
Sindhupalchok | Gumba |  | SCI | TUKI | DEC-II | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of episodes | Yes | Ongoing | 3 | 3 | 2016-03-01 | 2017-03-30
Sindhupalchok | Gumba |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 39
Sindhupalchok | Gumba |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 70
Sindhupalchok | Gumba |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 38
Sindhupalchok | Gunsakot | 3 | ARSOW | ARSOW | FDF | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 1 | 0 | 2016-08-01
Sindhupalchok | Gunsakot |  | ARSOW | ARSOW | FDF | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 491 | 0 |  |  | Support based on the NRA policy
Sindhupalchok | Gunsakot |  | ARSOW | ARSOW | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 |  |  | Support based on the NRA policy
Sindhupalchok | Gunsakot |  | ARSOW | ARSOW | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 64 | 60 | 2016-07-06 |  | No Contact
Sindhupalchok | Gunsakot |  | ARSOW-ASF | ARSOW | FDF | Training | ToT | Skilled masons |  | # of trainees | Yes | Ongoing | 60 | 30 | 2016-04-01 | 2016-12-30
Sindhupalchok | Hagam | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-14 | 2016-11-20
Sindhupalchok | Hagam | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13
Sindhupalchok | Hagam | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40
Sindhupalchok | Hagam | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 1079 | 0 | 2017-04-15
Sindhupalchok | Hagam |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 | 2017-04-15
Sindhupalchok | Hagam |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 680 | 2016-11-01 | 2016-12-30
Sindhupalchok | Hagam |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Electrician | 7 days house wiring training | # of trainees | Yes | Completed | 20 | 20 | 2017-01-26 | 2017-02-01
Sindhupalchok | Hagam |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 1 | 2016-08-01
Sindhupalchok | Hagam |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-01-15
Sindhupalchok | Hagam |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 20 | 2016-12-01 | 2017-01-15
Sindhupalchok | Hagam |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | Haibung | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Gurung Gau CBRC
Sindhupalchok | Haibung | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 5 | 2017-02-15
Sindhupalchok | Haibung | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 24 | 24 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Majuwa CBRC
Sindhupalchok | Haibung | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 5 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 11 | 2017-02-06
Sindhupalchok | Haibung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Lokeshwori CBRC
Sindhupalchok | Haibung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | DeviDatta CBRc
Sindhupalchok | Haibung | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-06
Sindhupalchok | Haibung | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 6 | SABAL | TUKI | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 75 | 40 | 2016-06-02 | 2016-12-31 | 50 days Training
Sindhupalchok | Haibung | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Haibung Bhumisthan CBRC
Sindhupalchok | Haibung | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-06
Sindhupalchok | Haibung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Haibung Sindhupalchok CBRC
Sindhupalchok | Haibung | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches
Sindhupalchok | Haibung | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 | 2016-10-21 | 2016-10-26
Sindhupalchok | Haibung | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 6 | 2017-02-07
Sindhupalchok | Haibung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mathillo Dahapokhari CBRC
Sindhupalchok | Haibung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Tallo Dahapokhari CBRC
Sindhupalchok | Haibung | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-15 | 2017-02-16
Sindhupalchok | Haibung | 9 | WVIN |  | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 594 | 594 | 2016-01-07 | 2016-01-08
Sindhupalchok | Haibung |  | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1058 | 1058 | 2016-05-16 | 2016-05-20 | 10 Key Messages
Sindhupalchok | Haibung |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Haibung |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-03-01
Sindhupalchok | Helumbu | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-24 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Helumbu | 7 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 18 | 18 | 2016-05-24 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Helumbu | 7 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 8 | 2016-06-05 |  | 51 days vocational training
Sindhupalchok | Helumbu | 1,7,8 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 99 | 31 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Helumbu | 1,7,8 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 99 | 5 | 2016-05-24 | 2016-11-25
Sindhupalchok | Helumbu |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 216 | 0 | 2016-06-01
Sindhupalchok | Helumbu |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 36 | 15 | 2016-08-15 |  | In clusterwise planning phase
Sindhupalchok | Helumbu |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Ichok | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 6 | 6 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Ichok | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-29 |  | 55 days vocational training
Sindhupalchok | Ichok | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 19 | 19 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Ichok | 8 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Ichok | 8 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-29 |  | 56 days vocational training
Sindhupalchok | Ichok | 8 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 16 | 16 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Ichok | 9 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Ichok | 9 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-08-29 |  | 57 days vocational training
Sindhupalchok | Ichok | 9 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Ichok | 9 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-29 |  | 58 days vocational training
Sindhupalchok | Ichok | 1,2,8,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 156 | 127 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Ichok | 1,2,8,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 156 | 22 | 2016-05-27 | 2016-11-25
Sindhupalchok | Irkhu | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-09
Sindhupalchok | Irkhu | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Irkhu Bazzar CBRC
Sindhupalchok | Irkhu | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | NunDanda CBRC
Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of GI Pipe at ward no.1 Irkhu Bazar | # of households | Yes | Completed | 46 | 46 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.1 Mathillo Khadka Tole | # of households | Yes | Completed | 20 | 20 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30
Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-26 | 2016-09-13 | 7 days training
Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 1 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Irkhu | 1 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Irkhu | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 5 | 2017-02-09
Sindhupalchok | Irkhu | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Thapa Gaun CBRC
Sindhupalchok | Irkhu | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | chhipchet CBRC
Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.2 Gaire Dhara | # of households | Yes | Completed | 16 | 16 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Irkhu | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Irkhu | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 12 | 2017-02-10
Sindhupalchok | Irkhu | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Shyangtang CBRC
Sindhupalchok | Irkhu | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Mulabari CBRC
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.3 Chhipichaur | # of households | Yes | Completed | 13 | 13 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.3 kalimatikhola | # of households | Yes | Completed | 35 | 35 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.3 sim khola Bisauna | # of households | Yes | Completed | 16 | 16 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.3 sim khola Vasme | # of households | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.3 Sunar khola | # of households | Yes | Completed | 30 | 30 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Stone Masonry RVT(8cum),HDPE pipe and lift at ward no.3 Deurali Khola | # of households | Yes | Completed | 110 | 110 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Irkhu | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | Irkhu | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 33 | 33 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households |  | Ongoing | 0 | 2 | 2017-02-12
Sindhupalchok | Irkhu | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Tallodip CBRC
Sindhupalchok | Irkhu | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Batase CBRC
Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Stone Masonry RVT(8cum) ,HDPE pipe & Intake at ward no.4 Batase dada | # of households | Yes | Completed | 16 | 16 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) at ward no.4 Batase mul | # of households | Yes | Completed | 22 | 22 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.4 Chyandada | # of households | Yes | Completed | 8 | 8 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.4 Mijar tol | # of households | Yes | Completed | 10 | 10 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 4 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Irkhu | 4 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Sindhupalchok | Irkhu | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 5 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 6 | 2017-02-08
Sindhupalchok | Irkhu | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-11 | Tamang Tole CBRC
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.5 Alumula bari | # of households | Yes | Completed | 11 | 11 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) ,HDPE pipe and Intake at ward no.5 Bagar Mula Bari | # of households | Yes | Completed | 27 | 27 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.5 Dhande Gaun | # of households | Yes | Completed | 35 | 35 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum)+Intake at ward no.5 Dip Mula Bari | # of households | Yes | Completed | 19 | 19 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake ,Relay of HDPE pipe & Tap Stand at ward no.5 Mane Dada | # of households | Yes | Completed | 9 | 9 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 72
Sindhupalchok | Irkhu | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 9 | 2017-02-10
Sindhupalchok | Irkhu | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Diyale CBRC
Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30
Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 55
Sindhupalchok | Irkhu | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Gahatetole CBRC
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.7 Juge khola | # of households | Yes | Completed | 1 | 10 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.7 Dada kanle | # of households | Yes | Completed | 40 | 40 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.7 Tin Dhara | # of households | Yes | Completed | 14 | 14 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) ,Relay of HDPE pipe and lift at ward no.7 Harre | # of households | Yes | Completed | 20 | 20 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Pokhare CBRC
Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) , Relay of HDPE pipe and lift at ward no.8 Simkhet | # of households | Yes | Completed | 62 | 62 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30
Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-08 | 2016-01-14
Sindhupalchok | Irkhu | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-20 | 2016-11-30
Sindhupalchok | Irkhu | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-09
Sindhupalchok | Irkhu | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2016-12-26 | 2016-12-26
Sindhupalchok | Irkhu | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Mandanda CBRC
Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.9 Karkichhap | # of households | Yes | Completed | 15 | 15 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) and Relay of HDPE/GI pipe at ward no.9 Gaje Khola | # of households | Yes | Completed | 46 | 46 | 2016-06-05 | 2016-11-30
Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-26 | 2016-09-13
Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-10-30 | 50 days Training
Sindhupalchok | Irkhu | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 117
Sindhupalchok | Irkhu |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 90 | 2016-04-01 | 2020-12-31
Sindhupalchok | Irkhu |  | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 400 | 380 | 2016-03-01 | 2016-10-30
Sindhupalchok | Jalbire | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 32 | 32 | 2016-02-15 | 2016-02-15
Sindhupalchok | Jalbire | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-03-28 | 2016-03-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Jalbire | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 44 | 44 | 2016-02-19 | 2016-02-20
Sindhupalchok | Jalbire | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 43 | 43 | 2016-03-28 | 2016-03-28
Sindhupalchok | Jalbire | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 42 | 42 | 2016-02-19 | 2016-02-20
Sindhupalchok | Jalbire | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 42 | 42 | 2016-03-28 | 2016-03-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Jalbire | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 33 | 33 | 2016-02-18 | 2016-02-19
Sindhupalchok | Jalbire | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-03-28 | 2016-03-28
Sindhupalchok | Jalbire | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 27 | 27 | 2016-02-18 | 2016-02-19
Sindhupalchok | Jalbire | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 25 | 25 | 2016-03-28 | 2016-03-28
Sindhupalchok | Jalbire | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-17 | 2016-02-18
Sindhupalchok | Jalbire | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-04-16 | 2016-04-16 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Jalbire | All | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 644 | 2016-11-01 | 2016-12-30
Sindhupalchok | Jalbire |  | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1049 | 1049 | 2016-05-21 | 2016-05-25 | 11 Key Messages
Sindhupalchok | Jalbire |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Jalbire |  | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 30 | 0 |  |  | Date planning to fixed
Sindhupalchok | Jalbire |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 43
Sindhupalchok | Jethal | 1 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 86 | 86 | 2016-01-04 | 2015-01-30
Sindhupalchok | Jethal | 2 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 80 | 80 | 2016-01-02 | 2015-01-30
Sindhupalchok | Jethal | 3 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 45 | 45 | 2016-01-02 | 2015-01-30
Sindhupalchok | Jethal | 4 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 50 | 50 | 2015-12-28 | 2015-01-30
Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 200 | 0 | 2017-01-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 | 2017-01-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2017-01-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 20 | 2017-03-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | Jethal |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-26 |  | 50 days Training
Sindhupalchok | Kadambas | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Simle CBRC
Sindhupalchok | Kadambas | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Lapse CBRC
Sindhupalchok | Kadambas | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Kadambas ward-2 & 3
Sindhupalchok | Kadambas | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Kadambas ward-2 & 3
Sindhupalchok | Kadambas | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Kadambas ward-4 CBRC
Sindhupalchok | Kadambas | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 51 | 51 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Kadambas ward-5 CBRC
Sindhupalchok | Kadambas | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 7 | 7 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Siranchaur Mathilo Tole CBRC
Sindhupalchok | Kadambas | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Siranchaur Tallo Tole CBRC
Sindhupalchok | Kadambas | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 73 | 73 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Kadambas ward-7 CBRC
Sindhupalchok | Kadambas | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 20 | 20 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Andheri CBRC
Sindhupalchok | Kadambas | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 | 2016-11-20 | 2016-11-30
Sindhupalchok | Kadambas | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-03 | 2017-01-03
Sindhupalchok | Kadambas | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees |  | Completed | 6 | 6 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in Jan 27- 2 Feb -2017
Sindhupalchok | Kadambas | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Mulkharka CBRC
Sindhupalchok | Kadambas | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Gorkhu CBRC
Sindhupalchok | Kadambas | All | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 465 | 2016-11-01 | 2016-12-30
Sindhupalchok | Kadambas |  | INCLUSIVE |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 51
Sindhupalchok | Kadambas |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 95 | 2016-04-01 | 2020-12-31
Sindhupalchok | Kadambas |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Electrician | 7 days house wiring training | # of trainees | Yes | Planned | 20 | 0 | 2017-02-12 | 2017-02-18 | In clusterwise planning phase
Sindhupalchok | Kadambas |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Kadambas |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-09-07 | 2016-09-14
Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 4 | 4 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 82 | 80 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-07 | 2016-09-14
Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 63 | 61 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-09-07 | 2016-09-14
Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 107 | 105 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-07 | 2016-09-14
Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 61 | 59 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-06 | 2016-09-13
Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 69 | 67 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-09-06 | 2016-09-13
Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 4 | 4 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 92 | 90 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-06 | 2016-09-13
Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 53 | 51 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-06 | 2016-09-13
Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 38 | 36 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-06 | 2016-09-13
Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 88 | 81 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Kalika | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner | # of households | Yes | Ongoing | 653 | 0 | 2016-10-15 |  | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner
Sindhupalchok | Kalika | All | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Suport to house construction | # of households | Yes | Ongoing | 630 | 25 | 2017-03-23
Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) |  | Yes | Completed | 653 | 645 | 2016-07-01 | 2016-08-08
Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) |  | Yes | Ongoing | 653 | 645 | 2016-07-15 | 2016-08-15
Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | VDC coverage | # of households supported | Yes | Planned | 0 | 0 | 2017-03-15 |  | VDC coverage
Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Ongoing | 2 | 2 | 2016-12-05 | 2016-03-10
Sindhupalchok | Kalika |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Kalika |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 40 | 0 | 2016-09-01
Sindhupalchok | Karthali | 1 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2016-10-06
Sindhupalchok | Karthali | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 11 | 11 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17)
Sindhupalchok | Karthali | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-10-01 | 2016-10-04
Sindhupalchok | Karthali | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-01-28
Sindhupalchok | Karthali | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ripar Setidevi CBRC
Sindhupalchok | Karthali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Kalinchwok CBRC
Sindhupalchok | Karthali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Khiping CBRC
Sindhupalchok | Karthali | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 2 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2016-10-06
Sindhupalchok | Karthali | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17)
Sindhupalchok | Karthali | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45
Sindhupalchok | Karthali | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Kabhre Gurung CBRC
Sindhupalchok | Karthali | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 3 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-01 | 2017-01-31
Sindhupalchok | Karthali | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17)
Sindhupalchok | Karthali | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34
Sindhupalchok | Karthali | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-01
Sindhupalchok | Karthali | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Sunkoshi CBRC
Sindhupalchok | Karthali | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Bagar Baseri CBRC
Sindhupalchok | Karthali | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 4 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2016-10-06
Sindhupalchok | Karthali | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-07-06
Sindhupalchok | Karthali | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 53 | 53
Sindhupalchok | Karthali | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Mahankali CBRC
Sindhupalchok | Karthali | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 5 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2016-10-06
Sindhupalchok | Karthali | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-07-06
Sindhupalchok | Karthali | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61
Sindhupalchok | Karthali | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Seti devi CBRC
Sindhupalchok | Karthali | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Latteswori mahadev CBRC
Sindhupalchok | Karthali | 5 | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Constructing truss structure 3 rooms for Shree Nepal Rastriya Secendary School |  | Yes | Ongoing | 1 | 1
Sindhupalchok | Karthali | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 6 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2016-10-06
Sindhupalchok | Karthali | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17)
Sindhupalchok | Karthali | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63
Sindhupalchok | Karthali | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Lali Gurans CBRC
Sindhupalchok | Karthali | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 7 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-01-26 | 2016-10-06
Sindhupalchok | Karthali | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-07-06
Sindhupalchok | Karthali | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 54 | 54
Sindhupalchok | Karthali | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Sundaridevi CBRC
Sindhupalchok | Karthali | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 8 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2016-10-06
Sindhupalchok | Karthali | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 12 | 12 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17)
Sindhupalchok | Karthali | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36
Sindhupalchok | Karthali | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Aakashwani Devi CBRC
Sindhupalchok | Karthali | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | 9 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-03 | 2017-01-31
Sindhupalchok | Karthali | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17)
Sindhupalchok | Karthali | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 41 | 41
Sindhupalchok | Karthali | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18
Sindhupalchok | Karthali | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Shree Kamala Devi CBRC
Sindhupalchok | Karthali | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01
Sindhupalchok | Karthali | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 1032 | 0 | 2017-04-15
Sindhupalchok | Karthali |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Karthali |  | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 26 | 26 | 2016-07-09 | 2016-07-15
Sindhupalchok | Karthali |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 | 2017-04-15
Sindhupalchok | Kiwool | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Kiwool | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 15 | 15 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Kiwool | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-08-22 |  | 52 days vocational training
Sindhupalchok | Kiwool | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-22 |  | 53 days vocational training
Sindhupalchok | Kiwool | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 6 | 2016-08-22 |  | 54 days vocational training
Sindhupalchok | Kiwool | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 20 | 20 | 2016-05-27 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Kiwool | 1,2,4 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 112 | 68 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Kiwool | 1,2,4 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 112 | 21 | 2016-05-27 | 2016-11-25
Sindhupalchok | Kiwool | All | OXFAM-GB | MANK | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2016-11-11 | 2016-11-17
Sindhupalchok | Kiwool |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 216 | 0 | 2016-06-01
Sindhupalchok | Kiwool |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Planned | 36 | 0 | 2016-08-15 |  | In clusterwise planning phase
Sindhupalchok | Kiwool |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | Kiwool |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Kunchok | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 1 | SABAL | TUKI | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 75 | 40 | 2016-05-27 | 2016-12-31 | 50 days Training
Sindhupalchok | Kunchok | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-03-02 | 2016-03-04
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 28 | 2016-05-12 | 2016-05-18
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 32 | 2016-06-01 | 2016-06-07
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-06-09 | 2016-06-15
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-17 | 2016-06-23
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-06-25 | 2016-07-01
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-04 | 2016-07-10
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-12 | 2016-07-18
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-20 | 2016-07-26
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 | 2016-07-28 | 2016-08-03
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-08-05 | 2016-08-11
Sindhupalchok | Kunchok | All | NRCS | NRCS | NRC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 6 | 6 | 2015-09-01 | 2016-01-10
Sindhupalchok | Kunchok |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 458 | 458 | 2016-06-01
Sindhupalchok | Kunchok |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 36 | 15 | 2016-08-15 |  | In clusterwise planning phase
Sindhupalchok | Kunchok |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Kunchok |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 40 | 2016-12-20 | 2016-12-26 | 7 days Training
Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 73 | 2016-06-01 | 2016-06-01
Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 117 | 2016-08-01 | 2016-12-20
Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 21 | 21 | 2016-05-25
Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 155 | 117 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-17 | 2017-04-30
Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 21 | 21 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 34 | 2016-06-02 | 2016-06-02
Sindhupalchok | Lagarche | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 0
Sindhupalchok | Lagarche | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 129 | 97 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 22 | 2016-06-01 | 2016-06-01
Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 32
Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-25
Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 32 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 29 | 2016-06-01 | 2016-06-01
Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 0
Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-25
Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 43 | 30 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 37 | 2016-07-06 | 2016-07-06
Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 30
Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25
Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 30 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 40 | 2016-07-06 | 2016-07-06
Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 35
Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-25
Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 102 | 35 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 55 | 2016-07-05 | 2016-07-05
Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 28
Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-25
Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 28 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 37 | 2016-07-05 | 2016-07-05
Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 37
Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25
Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 83 | 37 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-11-17
Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 58 | 2016-07-04 | 2016-07-04
Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 75
Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-25
Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 116 | 75 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16
Sindhupalchok | Lisankhu | 1 | SABAL | TUKI | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 75 | 40 | 2016-05-29 | 2016-12-31 | 7 days Training
Sindhupalchok | Lisankhu |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-06 |  | 50 days Training
Sindhupalchok | Lisankhu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 36
Sindhupalchok | Listikot |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition |  | Yes | Completed | 36 | 36 | 2015-09-01 | 2015-09-30
Sindhupalchok | Listikot |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 9 | 9 | 2016-05-01 | 2016-05-05
Sindhupalchok | Listikot |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-03-01
Sindhupalchok | Listikot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 25
Sindhupalchok | Mahankal | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-06-01 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Mahankal | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-11-28 |  | 59 days vocational training
Sindhupalchok | Mahankal | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 30 | 30 | 2016-06-01 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Mahankal | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 66
Sindhupalchok | Mahankal | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-06-01 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Mahankal | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-06-01 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Mahankal | 6 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-11-28 |  | 60 days vocational training
Sindhupalchok | Mahankal | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 43
Sindhupalchok | Mahankal | 3,6,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 134 | 0 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Mahankal | 3,6,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 134 | 25 | 2016-06-01 | 2016-11-25
Sindhupalchok | Maneswor | 1 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-13 | 2016-11-10
Sindhupalchok | Maneswor | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 66 | 66 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 2 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 76 | 76 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Sangbari CBRC
Sindhupalchok | Maneswor | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 3 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Ghude CBRC
Sindhupalchok | Maneswor | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Maneswnara CBRC
Sindhupalchok | Maneswor | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 4 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 5 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 41 | 41 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-07
Sindhupalchok | Maneswor | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 7 | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 31 | 31 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Borabari CBRC
Sindhupalchok | Maneswor | 7 | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Reconstruction Support for School for retrofiting and 1 floor wall coverage with 2 rooms prefack construction in Bhadrakali Secondary School |  | Yes | Ongoing | 1 | 1
Sindhupalchok | Maneswor | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-08
Sindhupalchok | Maneswor | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Subeditol CBRC
Sindhupalchok | Maneswor | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-19 | 2016-07-25
Sindhupalchok | Maneswor | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-10-19 | 2016-11-10
Sindhupalchok | Maneswor | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-02
Sindhupalchok | Maneswor | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-28 | 2017-02-28
Sindhupalchok | Maneswor | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Kharibote CBRC
Sindhupalchok | Maneswor | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Maneswor | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 912 | 0 | 2017-04-15
Sindhupalchok | Maneswor |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Maneswor |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 | 2017-04-15
Sindhupalchok | Maneswor |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40
Sindhupalchok | Maneswor |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 85
Sindhupalchok | Mankha | 1 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 87 | 87 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-02
Sindhupalchok | Mankha | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Lamosanghu CBRC
Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Phantbasti CBRC
Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Baseri CBRC
Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Topka CBRC
Sindhupalchok | Mankha | 2 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 69 | 69 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-08
Sindhupalchok | Mankha | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Paharigaun CBRC
Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 3 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mathillogaun Bamjantol CBRC
Sindhupalchok | Mankha | 3 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 3 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 4 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-09
Sindhupalchok | Mankha | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mankha-4 CBRC
Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 5 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 5 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-09
Sindhupalchok | Mankha | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Kafalbot CBRC
Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 6 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 33 | 33 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-06
Sindhupalchok | Mankha | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Sunkoshi CBRC
Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 7 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-07
Sindhupalchok | Mankha | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Mankha CBRC
Sindhupalchok | Mankha | 8 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-07
Sindhupalchok | Mankha | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Bandarpa CBRC
Sindhupalchok | Mankha | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23
Sindhupalchok | Mankha | 9 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 57 | 57 | 2016-09-27 | 2016-10-04
Sindhupalchok | Mankha | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-15 | 2016-09-11
Sindhupalchok | Mankha | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-07
Sindhupalchok | Mankha | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-24 | 2017-02-24
Sindhupalchok | Mankha | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jaalbari CBRC
Sindhupalchok | Mankha | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09
Sindhupalchok | Mankha |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Mankha |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 38
Sindhupalchok | Mankha |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 87
Sindhupalchok | Marming | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 108 | 108 | 2016-04-20 | 2016-04-20
Sindhupalchok | Marming | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 120 | 120 | 2016-04-21 | 2016-04-21
Sindhupalchok | Marming | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 120 | 120 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 53 | 53 | 2016-04-22 | 2016-04-22
Sindhupalchok | Marming | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 53 | 53 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 88 | 88 | 2016-04-23 | 2016-04-23
Sindhupalchok | Marming | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 88 | 88 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 108 | 108 | 2016-04-24 | 2016-04-24
Sindhupalchok | Marming | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 35 | 35 | 2016-04-25 | 2016-04-25
Sindhupalchok | Marming | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 83 | 83 | 2016-04-26 | 2016-04-26
Sindhupalchok | Marming | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 83 | 83 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 89 | 89 | 2016-04-27 | 2016-04-27
Sindhupalchok | Marming | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 89 | 89 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 35 | 35 | 2016-04-28 | 2016-04-28
Sindhupalchok | Marming | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Marming |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 40 | 2016-12-12 | 2016-12-18 | 7 days Training
Sindhupalchok | Marming |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 58
Sindhupalchok | Melamchi N.P. | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 11 | 2017-02-09
Sindhupalchok | Melamchi N.P. | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2016-07-29 | 2017-01-09 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-08 | Dunganabesi CBRC
Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-02 | Batase CBRC
Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-12 | Tar CBRC
Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-13 | Kole chaur CBRC
Sindhupalchok | Melamchi N.P. | 1 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 7 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 35
Sindhupalchok | Melamchi N.P. | 2 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 7 | 7 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 2 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 15 | 15 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 18 | 2017-01-27
Sindhupalchok | Melamchi N.P. | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 36 | 36 | 2016-07-29 | 2017-01-22 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-01 | Derali CBRC
Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-02 | Chapabot CBRC
Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-06 | panchakanya CBRC
Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-12 | ludetol Dhara CBRC
Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-10 | Deuja tole CBRC
Sindhupalchok | Melamchi N.P. | 2 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 14 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 2 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 75 |  | 2016-12-22
Sindhupalchok | Melamchi N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 93
Sindhupalchok | Melamchi N.P. | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 3 | 3 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-08 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 9 | 2017-02-07
Sindhupalchok | Melamchi N.P. | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 25 | 25 | 2016-03-30 | 2016-12-16 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-08 | Sindhukot ward 1 CBRC
Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Sindhukot ward 4 CBRC
Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Sindhukot ward 5 CBRC
Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-06 | Sindhukot ward 9 CBRC
Sindhupalchok | Melamchi N.P. | 3 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 2 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 3 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 29 |  | 2016-12-11
Sindhupalchok | Melamchi N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 28
Sindhupalchok | Melamchi N.P. | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 19 | 19 | 2016-08-31 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 17 | 2017-02-07
Sindhupalchok | Melamchi N.P. | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 30 | 30 | 2016-04-16 | 2016-12-16 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-06 | Sindhukot ward 2 CBRC
Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-09 | Sindhukot ward 3 CBRC
Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-10 | Sindhukot ward 6 CBRC
Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-10 | Sindhukot ward 7 CBRC
Sindhupalchok | Melamchi N.P. | 4 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 10 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 105 |  | 2016-09-11
Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 36
Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34
Sindhupalchok | Melamchi N.P. | 5 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 16 | 2017-02-05
Sindhupalchok | Melamchi N.P. | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 19 | 19 | 2016-04-16 | 2016-12-27 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Majha tol CBRC
Sindhupalchok | Melamchi N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Daduwa CBRC
Sindhupalchok | Melamchi N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Sindhukot ward 8 CBRC
Sindhupalchok | Melamchi N.P. | 5 | SABAL | TUKI | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 75 | 40 | 2016-06-02 | 2016-12-31 | 7 days Training
Sindhupalchok | Melamchi N.P. | 5 | SABAL | TUKI | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 75 | 40 | 2016-05-29 | 2016-12-31 | 50 days Training
Sindhupalchok | Melamchi N.P. | 5 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 3 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 44
Sindhupalchok | Melamchi N.P. | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 24 | 2017-01-30
Sindhupalchok | Melamchi N.P. | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 13 | 13 | 2016-04-16 | 2016-12-27 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Katunje dulal tole CBRC
Sindhupalchok | Melamchi N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Kartike simpani CBRC
Sindhupalchok | Melamchi N.P. | 6 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 18 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 7 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 4 | 4 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 7 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-17 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-01-31
Sindhupalchok | Melamchi N.P. | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees |  | Ongoing | 9 | 9 | 2016-04-16 | 2017-01-09 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Arukharka CBRC
Sindhupalchok | Melamchi N.P. | 7 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 7 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | Brick masonry with cement mortar technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-20 | 2016-12-31
Sindhupalchok | Melamchi N.P. | 8 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 8 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 8 | 8 | 2016-09-17 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 1 | 2017-02-15
Sindhupalchok | Melamchi N.P. | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 17 | 17 | 2016-08-02 | 2017-01-22 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Aapchaur CBRC
Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-10 | Bansbari ward 5 CBRC
Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Bansbari ward 6 CBRC
Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-01 | Bansbari ward 7 CBRC
Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 11 | 11 | 2016-04-03 | 2016-04-09
Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 13 | 13 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 11 | 11 | 2016-04-03 | 2016-04-09
Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 13 | 13 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 8 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 1 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 9 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 9 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-01
Sindhupalchok | Melamchi N.P. | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 9 | 9 | 2016-08-02 | 2017-01-22 | mason training completed in different lots
Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-05 | Bansbari ward 3 CBRC
Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-05 | Bansbari ward 4 CBRC
Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-04 | Bansbari ward 8 CBRC
Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-03 | Bansbari ward 9 CBRC
Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 12 | 12 | 2016-04-03 | 2016-04-09
Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 20 | 20 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 12 | 12 | 2016-04-03 | 2016-04-09
Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 20 | 20 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 9 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 1 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 10 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 1 | 1 | 2016-09-23 | 2016-09-29
Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Fatakshila ward 1 CBRC
Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Fatakshila ward 2 CBRC
Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-25 | Fatakshila ward 3 CBRC
Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-25 | Fatakshila ward 4 CBRC
Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 21 | 21 | 2016-04-06 | 2016-04-12
Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 21 | 21 | 2016-04-06 | 2016-04-12
Sindhupalchok | Melamchi N.P. | 11 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 5 | 5 | 2016-09-23 | 2016-09-29
Sindhupalchok | Melamchi N.P. | 11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Fatakshila ward 5 CBRC
Sindhupalchok | Melamchi N.P. | 11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-26 | Fatakshila ward 8 CBRC
Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-06 | 2016-04-12
Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23
Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-04-06 | 2016-04-12
Sindhupalchok | Melamchi N.P. | 12 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 22 | 22 | 2016-08-02 | 2016-08-08
Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-27 | Sikharpur ward 4 CBRC
Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-29 | Sikharpur ward 6 CBRC
Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Sikharpur ward 7 CBRC
Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Acharya tole CBRC
Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-01 | Sikharpur ward 8 CBRC
Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-02 | Sikharpur ward 9 CBRC
Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-03-04
Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-06-15
Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-01 | 2016-06-06
Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-01 | 2016-01-10
Sindhupalchok | Melamchi N.P. | 12 | ROTARY | NTA | ROTARY | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 42 | 42 | 2016-02-01 | 2016-06-01 | Majhitar
Sindhupalchok | Melamchi N.P. | 12 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 22 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 12 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Ongoing | 1 | 0 | 2016-11-20 | 2017-01-31
Sindhupalchok | Melamchi N.P. | 12 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 154 |  | 2016-12-08
Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-04 | Hileykholapari CBRC
Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Rampur CBRC
Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-03 | Sikharpur ward 1 CBRC
Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Sikharpur ward 2 CBRC
Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-05 | Sikharpur ward 3 CBRC
Sindhupalchok | Melamchi N.P. | 13 | NRCS | NRCS | NRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-03-04
Sindhupalchok | Melamchi N.P. | 13 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-09 | 2016-06-15
Sindhupalchok | Melamchi N.P. | 13 | NRCS | NRCS | NRC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-01 | 2016-01-10
Sindhupalchok | Melamchi N.P. | 13 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 13 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 100 |  | 2016-12-12
Sindhupalchok | Melamchi N.P. | 14 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 25 | 25 | 2016-08-06 | 2016-08-12
Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | sunkhani CBRC
Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Ratmata CBRC
Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-24 | Tinkanya CBRC
Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-24 | Golmeshwori Manedada CBRC
Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Gupha CBRC
Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-25 | paiyatol CBRC
Sindhupalchok | Melamchi N.P. | 15 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 3 | 3 | 2016-09-23 | 2016-09-29
Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Milanchowk CBRC
Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-27 | Golmasthan CBRC
Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-27 | khadkathok CBRC
Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-28 | chyankhu CBRC
Sindhupalchok | Melamchi N.P. | 15 | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 1 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch
Sindhupalchok | Melamchi N.P. | 15 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 88 |  | 2016-12-14
Sindhupalchok | Melamchi N.P. | 10, 11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Fatakshila ward 2 and 7 CBRC
Sindhupalchok | Melamchi N.P. | 10,11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-26 | Fatakshila ward 7 and 9 CBRC
Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 250 | 174 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 250 | 14 | 2016-08-01 | 2016-11-25
Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 28 | 28 | 2017-02-06 | 2017-02-06 | Data of Talamrang VDC
Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 34 | 34 | 2017-02-07 | 2017-02-07 | Data of Jyamire VDC
Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 25 | 25 | 2017-02-08 | 2017-02-08 | Data of Shikharpur VDC
Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 28 | 28 | 2017-02-09 | 2017-02-09 | Data of Bansbari VDC
Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 26 | 26 | 2017-02-10 | 2017-02-10 | Data of Fataksila VDC
Sindhupalchok | Melamchi N.P. |  | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 6 | 6 | 2016-09-01 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. |  | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-09-17 |  | 50 days vocational training
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 277 | 277 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 273 | 273 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 199 | 199 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 244 | 244 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 294 | 294 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 247 | 247 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 274 | 274 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 258 | 258 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 207 | 207 | 2016-09-22 | 2016-12-21
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 560 | 80 | 2016-04-01 | 2020-12-31
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-07-10 | 2016-07-16
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-08-23 | 2016-08-29
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 22 | 22 | 2016-07-31 | 2016-08-06
Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 1 | 1 | 2016-03-30 | 2016-12-31 | As RajanJi (JICA) It is verified but …
Sindhupalchok | Melamchi N.P. |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 372 | 372 | 2015-09-27 | 2015-10-04
Sindhupalchok | Melamchi N.P. |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 60 | 2015-09-27 | 2015-10-04
Sindhupalchok | Melamchi N.P. |  | UNDP | UNDP | UNDP | Others | Others | (Please specify in Activity Detail) | Support to develop housing models/ settlement plans for Economically Weaker Sections through Design Contest |  | Yes | Planned | 0 | 0
Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 92 | 2016-06-04 | 2016-06-04
Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 37 | 2016-08-01 | 2016-12-15
Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 18 | 18 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 37 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 33 | 2016-06-03 | 2016-06-03
Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 60
Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 94 | 60 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-11-21
Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 39 | 2016-07-05 | 2016-07-05
Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 31
Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 43 | 31 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 38 | 2016-11-18 | 2016-11-18
Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 34
Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 34 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 59 | 2016-06-01 | 2016-06-01
Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 39
Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 22 | 22 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 39 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Ongoing | 1 | 1 | 2017-02-05 | 2017-05-15
Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 35 | 2016-07-15 | 2016-07-15
Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 24
Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16
Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 54 | 24 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16
Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 49 | 2016-06-02 | 2016-06-02
Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 34
Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 34 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 100 | 2016-07-06 | 2016-07-06
Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 49
Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 13 | 13 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 49 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 22 | 2016-06-02 | 2016-06-02
Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 51
Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 12 | 12 | 2016-05-25 | 2017-03-04
Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 51 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-25 | 2017-03-04
Sindhupalchok | Nawalpur | 1 | SABAL | TUKI | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 75 | 20 | 2016-05-28 | 2016-12-31 | 50 days Training
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2016-03-02 | 2016-03-04
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-17 | 2016-06-23
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 28 | 2016-06-25 | 2016-07-01
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-04 | 2016-07-10
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-12 | 2016-07-18
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2016-07-20 | 2016-07-26
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-07-28 | 2016-08-03
Sindhupalchok | Nawalpur | All | NRCS | NRCS | NRC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 6 | 6 | 2015-09-01 | 2016-01-10
Sindhupalchok | Nawalpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 453 | 453 | 2016-06-01
Sindhupalchok | Nawalpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 36 | 15 | 2016-08-15 |  | In clusterwise planning phase
Sindhupalchok | Nawalpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Pagretar | 1 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 32 | 32 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 2 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 53 | 53 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 2 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 12 | 12 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 3 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 70 | 70 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 3 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 27 | 27 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 4 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 50 | 50 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 4 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 21 | 21 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 5 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 60 | 60 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 5 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 20 | 20 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 6 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 41 | 41 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 6 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 28 | 28 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 7 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 55 | 55 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 7 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 12 | 12 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 8 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 85 | 85 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 8 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 37 | 37 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 9 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 41 | 41 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | 9 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 34 | 34 | 2017-07-10 | 2017-07-10
Sindhupalchok | Pagretar | All | CA | CA | CA | Others | Others | (Please specify in Activity Detail) |  |  | Yes | Completed | 650 | 650 | 2016-01-10 | 2016-04-30
Sindhupalchok | Pagretar | All | CA | CA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 650 | 650 | 2016-01-10 | 2016-06-15
Sindhupalchok | Pagretar | All | CA | CA | CA | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 117 | 117 | 2016-01-10 | 2016-06-15
Sindhupalchok | Pagretar | All | CA | CA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2016-01-10 | 2016-08-30
Sindhupalchok | Pagretar |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 150 | 141 | 2016-10-01 |  | In clusterwise planning phase
Sindhupalchok | Pagretar |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 20 | 2016-09-01
Sindhupalchok | Palchok | 1 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-02-05 |  | 50 days vocational training
Sindhupalchok | Palchok | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 3 | 3 | 2016-02-05 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Palchok | 3 | HELVETAS | CDECF | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-02-05 |  | 50 days vocational training
Sindhupalchok | Palchok | 4 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 6 | 6 | 2016-02-05 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Palchok | 5 | HELVETAS | CDECF | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 1 | 1 | 2016-02-05 | 2016-11-25 | 50 days vocational training
Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 72 | 0 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC
Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 72 | 7 | 2016-02-05 | 2016-11-25
Sindhupalchok | Palchok |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-14 |  | 50 days Training
Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 627 | 2016-11-01 | 2016-12-30
Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 30 | 30 | 2016-06-09 | 2016-06-15
Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 64 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-01-15
Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-09 | 2016-06-15
Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 20 | 2016-12-01 | 2017-01-15
Sindhupalchok | Pangtang |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | Pangtang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 56
Sindhupalchok | Pangtang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34
Sindhupalchok | Petaku | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-04-07 | 2016-04-07
Sindhupalchok | Petaku | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-19 | 2016-04-19
Sindhupalchok | Petaku | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 60 | 60 | 2016-04-05 | 2016-04-05
Sindhupalchok | Petaku | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 60 | 60 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Petaku | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 32 | 32 | 2016-04-05 | 2016-04-05
Sindhupalchok | Petaku | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Petaku | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 47 | 47 | 2016-04-05 | 2016-04-05
Sindhupalchok | Petaku | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-04-19 | 2016-04-19
Sindhupalchok | Petaku | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-04-07 | 2016-04-07
Sindhupalchok | Petaku | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 68 | 68 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Petaku | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 35 | 35 | 2016-04-06 | 2016-04-06
Sindhupalchok | Petaku | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Petaku | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 38 | 38 | 2016-04-06 | 2016-04-06
Sindhupalchok | Petaku | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 38 | 38 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Petaku | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 44 | 44 | 2016-04-08 | 2016-04-08
Sindhupalchok | Petaku | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 44 | 44 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Petaku | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 56 | 56 | 2016-04-08 | 2016-04-08
Sindhupalchok | Petaku | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 56 | 56 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Piskar | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 132
Sindhupalchok | Piskar |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition |  | Yes | Completed | 84 | 84 | 2015-09-01 | 2015-09-30
Sindhupalchok | Piskar |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 9 | 0
Sindhupalchok | Ramche | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-08 | 2016-11-17
Sindhupalchok | Ramche | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-20 | Damar CBRC
Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-21 | Chulthe CBRC
Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-22 | Thotnari CBRC
Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-23 | Ratamata CBRC
Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-27 | Aarukharka CBRC
Sindhupalchok | Ramche | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60
Sindhupalchok | Ramche | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40
Sindhupalchok | Ramche | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45
Sindhupalchok | Ramche | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-09
Sindhupalchok | Ramche | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Okharbote CBRC
Sindhupalchok | Ramche | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60
Sindhupalchok | Ramche | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-14 | Gairigaun CBRC
Sindhupalchok | Ramche | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-17 | Setidevi CBRC
Sindhupalchok | Ramche | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50
Sindhupalchok | Ramche | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-01-26
Sindhupalchok | Ramche | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Badahare CBRC
Sindhupalchok | Ramche | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45
Sindhupalchok | Ramche | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-01-28
Sindhupalchok | Ramche | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Saalbisauna CBRC
Sindhupalchok | Ramche | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40
Sindhupalchok | Ramche | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Tand Bisauna CBRC
Sindhupalchok | Ramche | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Saubesi CBRC
Sindhupalchok | Ramche | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-08-30
Sindhupalchok | Ramche | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35
Sindhupalchok | Ramche | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-03-01 | 2017-03-01
Sindhupalchok | Ramche | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-02 | Bhatte CBRC
Sindhupalchok | Ramche | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20
Sindhupalchok | Ramche | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 885 | 0 | 2017-04-15
Sindhupalchok | Ramche |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Ramche |  | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 60 | 2016-04-01 | 2020-12-31
Sindhupalchok | Ramche |  | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Construction Support for School constructing 2 rooms for library in Shree Sarashwati Secondary school |  | Yes | Planned | 1 | 1
Sindhupalchok | Ramche |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 | 2017-04-15
Sindhupalchok | Ramche |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Ramche |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 40 | 0 | 2016-09-01
Sindhupalchok | Ramche |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 90
Sindhupalchok | Sangachok | 1 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-01 | 2016-06-07
Sindhupalchok | Sangachok | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 73 | 73 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Sukute tole CBRC
Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Khatrithok CBRC
Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | SatthiMure CBRC
Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Karkitar CBRC
Sindhupalchok | Sangachok | 2 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13
Sindhupalchok | Sangachok | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 2 | 2017-02-10
Sindhupalchok | Sangachok | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Dhara Pani
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Deurali CBRC
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Rakhaltole CBRC
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Gairitole CBRC
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-27 | MajhGaun CBRC
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-27 | Harre CBRC
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-27 | Holka CBRC
Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-05 | Kande CBRC
Sindhupalchok | Sangachok | 3 | BC | ARSOW | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 64 | 64 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-06
Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-04 | 2017-01-04
Sindhupalchok | Sangachok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Pallatole CBRC
Sindhupalchok | Sangachok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Swarathok CBRC
Sindhupalchok | Sangachok | 3 | SCI | TUKI | ITV | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 143 | 2016-08-15
Sindhupalchok | Sangachok | 4 | BC | ARSOW | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 4 | BC | BC | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 0 | 0 | 2016-08-01
Sindhupalchok | Sangachok | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-04 | 2017-01-04
Sindhupalchok | Sangachok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Kotthok CBRC
Sindhupalchok | Sangachok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Chhap CBRC
Sindhupalchok | Sangachok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Sangachowk Bhanjhyang CBRC
Sindhupalchok | Sangachok | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34
Sindhupalchok | Sangachok | 5 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17
Sindhupalchok | Sangachok | 5 | BC | ARSOW | WVIN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2017-03-10
Sindhupalchok | Sangachok | 5 | BC | ARSOW | WVIN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 136 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 5 | BC | BC | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 0 | 0 | 2016-08-01
Sindhupalchok | Sangachok | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 71 | 71 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-05 | Jyoti Danda CBRC
Sindhupalchok | Sangachok | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Simlay CBRC
Sindhupalchok | Sangachok | 5 | WVIN | DEPROSC | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 136 | 103 | 2016-10-25
Sindhupalchok | Sangachok | 6 | BC | ARSOW | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 78 | 78 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-03
Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-04 | 2017-01-04
Sindhupalchok | Sangachok | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | RanaThok- Kharka CBRC
Sindhupalchok | Sangachok | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Chootedanda- NayaGuan CBRC
Sindhupalchok | Sangachok | 7 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15
Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 105 | 105 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-01
Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-04 | 2017-01-04
Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | BhaunGau CBRC
Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | PariGau CBRC
Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Chapabota CBRC
Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Gaurigau-Jalkeni CBRC
Sindhupalchok | Sangachok | 8 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2
Sindhupalchok | Sangachok | 8 | BC | ARSOW | WVIN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 1 | 2016-03-29 | 2017-02-28
Sindhupalchok | Sangachok | 8 | BC | ARSOW | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 8 | BC | ARSOW | WVIN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 143 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 8 | BC | BC | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 0 | 0 | 2016-08-01
Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 74 | 74 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 4 | 2017-02-15
Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-01-04 | 2017-01-04
Sindhupalchok | Sangachok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Falate CBRC
Sindhupalchok | Sangachok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Kavre CBRC
Sindhupalchok | Sangachok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Saithok CBRC
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 75 | 75 | 2016-08-01
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Ongoing | 3 | 0 | 2016-04-01 | 2017-02-28 | 5 in 8,9
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Training | Vocational training | New masons (50 days OJT CTEVT) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 11 | 2016-11-20 | 2016-12-30
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | ward coverage | # of households | Yes | Completed | 75 | 75 | 2016-11-24 | 2017-02-10
Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 75 | 22 | 2017-02-10
Sindhupalchok | Sangachok | 8 | WVIN | DEPROSC | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 40 | 38 | 2016-10-25
Sindhupalchok | Sangachok | 9 | BC | ARSOW | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6
Sindhupalchok | Sangachok | 9 | BC | ARSOW | WVIN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 28 | 0 | 2017-03-25
Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 39 | 39 | 2016-09-28 | 2016-10-04
Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 6 | 2017-02-13
Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-06 | 2016-03-12
Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-01-04 | 2017-01-04
Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Jamaune CBRC
Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Katunje Pani CBRC
Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mahadevtar
Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-14 | Pokhare CBRC
Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Ekle CBRC
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 68 | 68 | 2016-08-01
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Ongoing | 2 | 0 | 2016-04-01 | 2017-02-28 | 5 in 8,9
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Training | Vocational training | New masons (50 days OJT CTEVT) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 9 | 2016-11-20 | 2016-12-30
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | ward coverage | # of households | Yes | Completed | 68 | 68 | 2016-11-25 | 2017-02-10
Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 68 | 57 | 2017-03-23
Sindhupalchok | Sangachok | 9 | WVIN | DEPROSC | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 131 | 121 | 2016-10-25
Sindhupalchok | Sangachok | 5,8,9 | BC | ARSOW | BC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 4 | 0 | 2016-12-01
Sindhupalchok | Sangachok | 8 & 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Bhimtar CBRC
Sindhupalchok | Sangachok |  | BC | ARSOW | BC | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 440 | 1866 | 2016-08-08 | 2016-09-07 | 10 Key Messages
Sindhupalchok | Sangachok |  | BC | ARSOW | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1530 | 1530 | 2016-03-29 | 2016-07-04 | 10 Key Messages
Sindhupalchok | Sangachok |  | BC | ARSOW | BC | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 20 | 20 | 2016-08-08 | 2016-09-07 | Community Ambassador skill development on BBS
Sindhupalchok | Sangachok |  | BC | ARSOW | WVIN | Training | Other trainings | Other trainings (specify in Activity Detail) | Training on how to build house using block | # of trainees | Yes | Ongoing | 5 | 5 | 2017-02-20
Sindhupalchok | Sangachok |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 | 2016-04-01 | 2020-12-31
Sindhupalchok | Sangachok |  | SCI | TUKI | ITV | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of episodes | Yes | Ongoing | 1 | 1 | 2016-04-01 | 2016-02-28
Sindhupalchok | Selang | 1 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 2 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 3 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 4 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 5 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 6 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 7 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 8 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27
Sindhupalchok | Selang | 9 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-09-27 | 2015-10-27
Sindhupalchok | SipalKavre |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 208 | 208 | 2016-01-04 | 2016-01-11
Sindhupalchok | SipalKavre |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-04 | 2016-01-11
Sindhupalchok | SipalKavre |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 40 | 2016-12-20 | 2016-12-26 | 7 days Training
Sindhupalchok | SipalKavre |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-12 |  | 50 days Training
Sindhupalchok | SipaPokhare | 1 | SABAL | TUKI | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 75 | 47 | 2016-05-28 | 2016-12-31 | 7 days Training
Sindhupalchok | SipaPokhare | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 49
Sindhupalchok | SipaPokhare | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | SipaPokhare | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | SipaPokhare | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 18
Sindhupalchok | SipaPokhare | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | SipaPokhare | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | SipaPokhare | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | SipaPokhare | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0
Sindhupalchok | SipaPokhare | 8 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 64
Sindhupalchok | SipaPokhare | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0
Sindhupalchok | SipaPokhare | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0
Sindhupalchok | SipaPokhare | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 57
Sindhupalchok | Sunkhani | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 41 | 41 | 2016-05-17 | 2016-05-17
Sindhupalchok | Sunkhani | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 41 | 41 | 2016-05-20 | 2016-05-20 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Sunkhani | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 172 | 172 | 2016-05-11 | 2016-05-11
Sindhupalchok | Sunkhani | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 165 | 165 | 2016-05-20 | 2016-05-20
Sindhupalchok | Sunkhani | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 71 | 71 | 2016-05-12 | 2016-05-12
Sindhupalchok | Sunkhani | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 67 | 67 | 2016-05-20 | 2016-05-20
Sindhupalchok | Sunkhani | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 48 | 48 | 2016-05-12 | 2016-05-12
Sindhupalchok | Sunkhani | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 45 | 2016-05-20 | 2016-05-20
Sindhupalchok | Sunkhani | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 45 | 2016-05-13 | 2016-05-13
Sindhupalchok | Sunkhani | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 45 | 2016-05-20 | 2016-05-20 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Sunkhani | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 45 | 2016-05-13 | 2016-05-13
Sindhupalchok | Sunkhani | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 44 | 44 | 2016-05-20 | 2016-05-20
Sindhupalchok | Sunkhani | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 123 | 123 | 2016-05-09 | 2016-05-09
Sindhupalchok | Sunkhani | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 118 | 118 | 2016-05-19 | 2016-05-19
Sindhupalchok | Sunkhani | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 57 | 57 | 2016-05-10 | 2016-05-10
Sindhupalchok | Sunkhani | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 55 | 55 | 2016-05-19 | 2016-05-19
Sindhupalchok | Sunkhani | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 123 | 123 | 2016-05-13 | 2016-05-13
Sindhupalchok | Sunkhani | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 117 | 117 | 2016-05-19 | 2016-05-19
Sindhupalchok | Sunkhani |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 399 | 2016-10-01 |  | In clusterwise planning phase
Sindhupalchok | Sunkhani |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 40 | 0 | 2016-09-01
Sindhupalchok | Sunkhani |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20
Sindhupalchok | SyauleBazar | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 2 | 2 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 10 | 2017-01-27
Sindhupalchok | SyauleBazar | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Seti Bhumi CBRC
Sindhupalchok | SyauleBazar | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | JayangderGongbo CBRC
Sindhupalchok | SyauleBazar | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Chhangba Ningba Gunba CBRC
Sindhupalchok | SyauleBazar | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 6 | 6 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-03
Sindhupalchok | SyauleBazar | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Mangala Bhairavi Devi CBRC
Sindhupalchok | SyauleBazar | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Shree Ganesh CBRC
Sindhupalchok | SyauleBazar | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 49 | 49 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 8 | 2017-02-01
Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-01
Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Satkanya Mangala devi CBRC
Sindhupalchok | SyauleBazar | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Pach Mangala Devi CBRC
Sindhupalchok | SyauleBazar | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 62 | 62 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Khorang Yarsa CBRC
Sindhupalchok | SyauleBazar | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Pachpokhari CBRC
Sindhupalchok | SyauleBazar | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 3 | 3 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 47 | 47 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Shree Kalika Devi CBRC
Sindhupalchok | SyauleBazar | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 12 | 12 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-01-25
Sindhupalchok | SyauleBazar | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Shree Bhairavi CBRC
Sindhupalchok | SyauleBazar | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 66 | 66 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Shree Bangbaa CBRC
Sindhupalchok | SyauleBazar | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 54 | 54 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-06
Sindhupalchok | SyauleBazar | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Harlang Barlang CBRC
Sindhupalchok | SyauleBazar | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jayashwori Bhanjhyang CBRC
Sindhupalchok | SyauleBazar | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Basuki Devi CBRC
Sindhupalchok | SyauleBazar | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2017-02-07 | 1st lot in Feb 1-7, 2016 and 2nd in Feb 1-7-2017
Sindhupalchok | SyauleBazar | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-24 | 2016-10-04
Sindhupalchok | SyauleBazar | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 9 | 2017-02-15
Sindhupalchok | SyauleBazar | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-02 | 2017-02-02
Sindhupalchok | SyauleBazar | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Rakta kailka CBRC
Sindhupalchok | SyauleBazar | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-16 | Kaushi-Ghar Mulabari CBRC
Sindhupalchok | SyauleBazar |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 82 | 2016-04-01 | 2020-12-31
Sindhupalchok | SyauleBazar |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 173 | 173 | 2015-12-24 | 2015-12-30
Sindhupalchok | SyauleBazar |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2015-12-24 | 2015-12-30
Sindhupalchok | Tatopani | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 65
Sindhupalchok | Tatopani | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02
Sindhupalchok | Tatopani |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase
Sindhupalchok | Tatopani |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 40 | 0 | 2016-09-01
Sindhupalchok | Tatopani |  | OXFAM-GB |  | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 15 | 15
Sindhupalchok | Tauthali |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-26 |  | 50 days Training
Sindhupalchok | Tekanpur | 1 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 20 | 20 | 2017-07-10 | 2017-07-10
Sindhupalchok | Tekanpur | All | CA | CA | CA | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-10 | 2016-06-15
Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 63 | 2016-06-02 | 2016-06-02
Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 44 | 2016-08-01 | 2017-12-20
Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-01
Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 81 | 44 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-08-24
Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 | 3 events
Sindhupalchok | Thakani | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 9 | 2017-02-07
Sindhupalchok | Thakani | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-08-28 | Chhapeli CBRC
Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 60 | 2016-06-05 | 2016-06-05
Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 66
Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-05-01
Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 66 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-09
Sindhupalchok | Thakani | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30
Sindhupalchok | Thakani | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-02-12
Sindhupalchok | Thakani | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-04 | Barse Dhunga CBRC
Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 35 | 2016-06-03 | 2016-06-03
Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 28
Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-01
Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 92 | 28 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-09
Sindhupalchok | Thakani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-03 | Thakani Ward 3 CBRC
Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 88 | 2016-06-01 | 2016-06-01
Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 86
Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-01
Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 130 | 86 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 1 | 2017-02-06
Sindhupalchok | Thakani | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30
Sindhupalchok | Thakani | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-02-12
Sindhupalchok | Thakani | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-23 | Chandeshwori Mahadev CBRC
Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 76 | 2016-06-05 | 2016-06-05
Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 57
Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 21 | 21 | 2016-05-01
Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 118 | 57 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Ongoing | 1 | 1 | 2017-01-15 | 2017-04-30
Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 21 | 21 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-08-30
Sindhupalchok | Thakani | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-12 | 2017-02-12
Sindhupalchok | Thakani | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-09-02 | Okhereni Chaur CBRC
Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 114 | 2016-07-10 | 2016-07-10
Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 75
Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-01
Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 127 | 75 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-06
Sindhupalchok | Thakani | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-21 | Thakani Ward 6 CBRC
Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 30 | 2016-06-05 | 2016-06-05
Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 24
Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-01
Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 35 | 24 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2016-08-30
Sindhupalchok | Thakani | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-12 | 2017-02-12
Sindhupalchok | Thakani | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-08-31 | Dhauleshwori CBRC
Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 135 | 2016-04-30 | 2016-04-30
Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 112
Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 19 | 19 | 2016-05-01
Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 202 | 131 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 10 | 2017-02-14
Sindhupalchok | Thakani | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-08-24 | 2016-08-30
Sindhupalchok | Thakani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-25 | Thakani Ward 8 CBRC
Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 91 | 2016-06-26 | 2016-06-26
Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 80
Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-01
Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 129 | 80 |  |  | Marked as 1 to indicate the activity is going on
Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-01 | 2016-06-25
Sindhupalchok | Thakani | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 20 | 20 | 2016-11-25 | 2016-12-05
Sindhupalchok | Thakani | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 4 | 2017-02-14
Sindhupalchok | Thakani | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-24 | 2016-08-30
Sindhupalchok | Thakani | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-19 | Thakani Ward 9 CBRC
Sindhupalchok | Thakani |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31
Sindhupalchok | Thakani |  | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-02-12 | 2017-02-12
Sindhupalchok | Thakani |  | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-12 | 2017-02-12
Sindhupalchok | Thakani |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 57
Sindhupalchok | ThampalChhap | 1 | ARSOW | ARSOW | FDF | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 1 | 0 | 2016-08-01
Sindhupalchok | ThampalChhap |  | ARSOW | ARSOW | FDF | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 1006 | 0 |  |  | Support based on the NRA policy
Sindhupalchok | ThampalChhap |  | ARSOW | ARSOW | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 |  |  | Support based on the NRA policy
Sindhupalchok | ThampalChhap |  | ARSOW | ARSOW | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 116 | 60 | 2016-07-25 |  | No Contact
Sindhupalchok | ThampalChhap |  | ARSOW-ASF | ARSOW | FDF | Training | ToT | Skilled masons |  | # of trainees | Yes | Planned | 60 | 0 | 2016-04-01 | 2016-12-30
Sindhupalchok | Thanpalkot | 4 | ARSOW |  | FDF | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 1 | 0 | 2016-08-01
Sindhupalchok | Thanpalkot |  | ARSOW | ARSOW | FDF | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 862 | 0 |  |  | Support based on the NRA policy
Sindhupalchok | Thanpalkot |  | ARSOW | ARSOW | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 |  |  | Support based on the NRA policy
Sindhupalchok | Thanpalkot |  | ARSOW | ARSOW | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 80 | 49 | 2016-06-23 |  | No Contact
Sindhupalchok | Thanpalkot |  | ARSOW-ASF | ARSOW | FDF | Training | ToT | Skilled masons |  | # of trainees | Yes | Ongoing | 60 | 30 | 2016-04-01 | 2016-12-30
Sindhupalchok | Thanpalkot |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-03-01
Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 111 | 105 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 166 | 160 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 186 | 180 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 6 | 6 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 134 | 128 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 179 | 173 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 4 | ROTARY | ROTARY | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 30 | 0 |  |  | Date planning to fixed
Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 6 | 6 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 81 | 75 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 86 | 80 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 87 | 81 | 2016-10-15 |  | VDC coverage
Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 107 | 101 | 2016-10-15 |  | Ward level construction committee formation
Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage
Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-09-20 | 2016-09-27
Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee
Sindhupalchok | Thokarpa | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner | # of households | Yes | Ongoing | 1137 | 1 | 2016-10-15 |  | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | support to house construction | # of households | Yes | Ongoing | 1137 | 30 | 2017-03-23
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) |  | Yes | Completed | 1137 | 1107 | 2016-07-26 | 2016-08-16
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) |  | Yes | Completed | 1137 | 1103 | 2016-07-15 | 2016-08-20
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | VDC coverage | # of households supported | Yes | Planned | 0 | 0 | 2017-03-15 |  | VDC coverage
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Ongoing | 2 | 2 | 2016-12-13
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 38 | 38 | 2016-10-04 | 2016-10-23 | Tole level construction group formation
Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 9 | 9 | 2016-10-04 | 2016-10-23 | Ward level construction committee formation
Sindhupalchok | ThuloDhading | 1 | SABAL | TUKI | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 75 | 40 | 2016-06-01 | 2016-12-31 | 7 days Training
Sindhupalchok | ThuloDhading | 2,4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 70 | 70 | 2016-05-19 | 2016-05-19
Sindhupalchok | ThuloDhading | 3,5,8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 43 | 43 | 2016-05-18 | 2016-05-18
Sindhupalchok | ThuloDhading | 6,4,1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 64 | 64 | 2016-05-19 | 2016-05-19
Sindhupalchok | ThuloDhading | 7,9,6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 106 | 106 | 2016-05-20 | 2016-05-20
Sindhupalchok | ThuloDhading |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Ongoing | 40 | 40 | 2016-12-07 |  | 50 days Training
Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 200 | 0 | 2017-01-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 | 2017-01-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2017-01-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 20 | 2017-03-01 | 2017-05-01 | Ward yet to confirm
Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 175 | 175 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 5 | 2017-01-19
Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 2 | 2 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Kotdanda CBRC
Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 84 | 84 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 3 | 2017-02-13
Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Saune Chaur CBRC
Sindhupalchok | Thulosirubari | 3 | Help | TUKI | ADH | Technical Assistance | Demonstration Construction | House | Demo house construction | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-02-25
Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 64 | 64 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 3 | 2017-02-15
Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Narayan Devi CBRC
Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 92 | 92 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-02
Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 2 | 9 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Kundali Devi CBRC
Sindhupalchok | ThuloSirubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Markandi Devi CBRC
Sindhupalchok | ThuloSirubari | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 10 | 10 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Suganda CBRC
Sindhupalchok | Thulosirubari | 6 | HELP | TUKI | ADH | Technical Assistance | Demonstration Construction | House | Demo house construction | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-02-25 | 2 house on progress 22.11.16 to25.12.16 / to be used as community building
Sindhupalchok | ThuloSirubari | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 69 | 69 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 5 | 2017-01-19
Sindhupalchok | ThuloSirubari | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Satdobato CBRC
Sindhupalchok | ThuloSirubari | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 49 | 49 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 3 | 3 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | ShreeRam CBRC
Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 71 | 71 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-01-20
Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-17 | Ranitar CBRC
Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-09-25 | 2016-10-04
Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 4 | 2017-01-20
Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 2 | 2 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017
Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-05 | 2017-01-05
Sindhupalchok | ThuloSirubari | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-16 | Kali Devi CBRC
Sindhupalchok | Thulosirubari | All | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 0 | 0 | 2017-03-07
Sindhupalchok | Thulosirubari | ALL | HELP | TUKI | ADH | Technical Assistance | Demonstration Construction | House | Planned for 7 model house construction | # of constructions | Yes | Planned | 7 | 0 | 2017-04-01 | 2017-12-01
Sindhupalchok | Thulosirubari |  | HELP | TCM | ADH | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-23 | 2015-11-29 | 2 Help engineers, provided by NSET
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Others | Others | (Please specify in Activity Detail) | 4 schools on-going / reconstruction of 10 schools and 2 ECD. Beneficiaries : 2110 students and 45 teachers |  | Yes | Ongoing | 12 | 4 | 2016-05-01 | 2018-08-30
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Others | Others | (Please specify in Activity Detail) | One day Orientation on DRR |  | Yes | Completed | 92 | 92 | 2016-08-01 | 2016-08-01
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA training provided by IFRC, shelter Cluster | # of participants | Yes | Completed | 2 | 2 | 2015-12-01 | 2015-12-01 | PASSA training provided by IFRC, shelter Cluster
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Suport to house construction | # of kits | Yes | Completed | 114 | 54 | 2016-03-14 | 2016-09-30 | Training provided by Traininc Center Nepal - TCN
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Training | Short training | Carpenter |  | # of trainees | Yes | Ongoing | 45 | 10 | 2016-11-22 | 2017-06-30 | short training hands-on on the model house
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Suport to house construction | # of households | Yes | Completed | 1789 | 1789 | 2015-05-01 | 2015-11-01 | tools purchased localy
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 18 | 2 | 2016-11-22 | 2017-06-30 | short training hands-on on the model house
Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 54 | 54 | 2016-03-14 | 2016-03-31 | Training provided by Traininc Center Nepal - TCN.
Sindhupalchok | ThuloSirubari |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 | 2016-04-01 | 2020-12-31
Sindhupalchok | Thulosirubari |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 53
Sindhupalchok | Yamunadanda | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 28 | 28 | 2016-01-22 | 2016-01-23
Sindhupalchok | Yamunadanda | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 28 | 28 | 2016-03-25 | 2016-03-25 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Yamunadanda | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-10 | 2016-02-10
Sindhupalchok | Yamunadanda | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-03-28 | 2016-03-28 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Yamunadanda | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-10 | 2016-02-10
Sindhupalchok | Yamunadanda | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-04-16 | 2016-04-16 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Yamunadanda | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 113 | 113 | 2016-02-13 | 2016-02-13
Sindhupalchok | Yamunadanda | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 116 | 116 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Yamunadanda | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 34 | 34 | 2016-02-11 | 2016-02-11
Sindhupalchok | Yamunadanda | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 34 | 34 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Yamunadanda | 2,3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-09 | 2016-02-09
Sindhupalchok | Yamunadanda | 2,3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-03-26 | 2016-03-26 | Verified by Badri Ji Senior Shelter Engineer
Sindhupalchok | Yamunadanda | 6,7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 32 | 32 | 2016-02-11 | 2016-02-11
Sindhupalchok | Yamunadanda | 6,7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-03-29 | 2016-03-29 | Verified by Badri Ji Senior Shelter Engineer